## All
[14 empty] | 54.16% | 52.72% | 48.41% |  | 63.64%
|  | s | Project Status | Project Type | Project Category | Project Code | Project Name | Project Mnager | Cost Engineer | Original Contract Value | Change Order Submitted | Change Order Approved | Rev. Project Value | Submitted Invoices | Approved Invoices | Collected amount | Budget | Actual Cost | Commitment | POC plan % June-26 | POC plan % 2026 | POC % Actual | POC Variance | Cash Inflow | Cash Outflow | Original Profit % | Current Profit % | Original Profit (Amount) | Current Profit (Amount)
0
[7 empty] | WESTERN REGION UNIT |  |  | 13883866952 |  | -14700865 | 13869166087 | 7512121686.2154 | 7311159550.7954 | 6713420170.0953 | 11725160248.52 | 7462360113.58 | 1988951442.87 | 74.02% | 81.04% | 66.94% | -4.237% | 6771889893.4234 | 7239901237.7748 | 8.811% | 13.84% | 1116619133.5998 | 1522487560.48 | -468011344.3514
SEC |  | 1 | Closed | Substation | 380kv ex | PE-221 | PE-221: Expansions of 380 KV Yanbu Central, Umluj North and Madain BSP | Mohamed Omar | Ganesh | 162014728 |  | 0 | 162014728 | 162014729 | 162014729 | 159023404 | 159831220.92 | 159137158.37 | 102034.06 | 100% | 100% | 99.56% | -0.44% | 159023404 | 159023404 | 2.57% | 1.348% | 4163779 | 2183507.08
SEC |  | 2 | Closed | Substation | 380kv ex | PE-182 | PE-182: Design and Construction of 8H Substation (PIC P-7705) | Mohamed Omar | Ganesh | 377381260 |  | 0 | 377381260 | 358662137 | 358662137 | 355663326.552 | 311891227.12 | 309421118.37 | 842015.85 | 100% | 100% | 99.21% | -0.79% | 355663326.552 | 303874129.6 | 7.45% | 17.35% | 28114904 | 65490032.88
SEC |  | 7 | Closed | UGC | UGC | PE-118 | PE-118 : 380 KV U/G Cable Makkah Central BSP | Bandar Khalid Al Qalah | Azeem | 525841349 |  | -95584121 | 430257228 | 410047494 | 410047494 | 410047581.988 | 462699641.77 | 459997092.88 | 3053161.68 | 100% | 100% | 99.38% | -0.62% | 410047581.988 | 458424433.9143 | 12.1% | -7.54% | 52061125 | -32442413.77
SEC |  | 8 | Closed | Substation | 132kv ex | PE-261 | PE-261: Reinf. of Misfilah-2 & 3 | Khaled Abdelaty | Hasan | 30000000 |  | 0 | 30000000 | 26768030 | 26768030 | 23768031.3982 | 17791251.7 | 18019713.46 | 369500 | 100% | 100% | 99.88% | -0.12% | 23768031.3982 | 17768675.7 | 22.04% | 40.7% | 6612000 | 12208748.3
SEC |  | 3 | Closed | Substation | DRPC | PE-243 | PE-243: Installation of Dynamic Reactive Power Compensation(DRPC) at Tabuk 380KV BSP | Shafqat Zia | Ganesh | 168693200 |  | 0 | 168693200 | 151823882 | 151823882 | 149469986.3233 | 167322655.7 | 163804529.14 | 2829957.29 | 100% | 100% | 97.89% | -2.11% | 149469986.3233 | 160074845.5178 | 3.85% | 0.8124% | 6494688 | 1370544.3
NEOM |  | 4 | Closed | Substation | 380kv | PE-241 | PE-241: Expansion of Existing Yanbu Central (YCNT) 380KV BSP, Umluj North (UMN) 380KV BSP and Al-Wajh (WJH) 380KV BSP – (PHASE-I) | Zohaib | Hasan | 452757500 |  | 0 | 452757500 | 402240395 | 402240395 | 402240395.4211 | 429128818.88 | 425107353.44 | 4287061.44 | 100% | 100% | 99.06% | -0.94% | 402240395.4211 | 395200857.6091 | 4.87% | 5.219% | 22049290 | 23628681.12
SEC |  | 5 | Closed | Substation | 380kv ex | PE-257 | PE-257: Expansions of Existing MHD 380 KV BSP | Mohamed Omar | Nishi | 125309260 |  | 0 | 125309260 | 112778334 | 112778334 | 100247407.996 | 112656451.85 | 112099243.08 | 538494.36 | 100% | 100% | 99.44% | -0.56% | 100247407.996 | 111914815.86 | 5.7% | 10.1% | 7092504 | 12652808.15
SEC |  | 6 | Closed | Substation | 110kv ex | PE-258 | PE-258: Taif East Governorate Project | Khaled Abdelaty | Hasan | 31600000 |  | 0 | 31600000 | 23882331 | 23882331 | 21896299.5126 | 18032438.02 | 17447906.22 | 693038.27 | 100% | 100% | 96.76% | -3.24% | 21896299.5126 | 17967523.1157 | 24.38% | 42.94% | 7704080 | 13567561.98
SEC |  | 9 | Closed | Substation | 110KV | PE-270 | 110/13.8KV HARAZAT SUB JEDDAH | Muhammed Ilyas | Aush Ranjan | 119195073 |  | 2662905 | 121857978 | 110072180 | 110072180 | 110072180.4123 | 100963743 | 97382403.28 | 129212.13 | 100% | 95% | 96.17% | -3.83% | 110072180.4123 | 97289179.5743 | 5.17% | 17.15% | 6159799 | 20894235
SEC | Egypt Office | 10 | Closed | Substation | 110KV | PE-290 | Fadelah 110/13.8KV SS - JEDDAH | Khaled Abdelaty | Badr Eldin khaled | 126251953 | 8324565 | 3370815 | 129622768 | 113332208 | 113332208 | 113332208.009 | 108362187.34 | 103560695 | 2993384.46 | 100% | 100% | 95.56% | -4.44% | 113332208.009 | 101308672.527 | 5.3% | 16.4% | 6870007 | 21260580.66
SEC |  | 11 | Closed | Substation | 380kV | PE-254 | HENAKIYAH BSP 380 KV | Mahmoud sobhy | Marwan | 579828000 |  | 32156056 | 611984056 | 550385576 | 550385576 | 549320450.7214 | 570024950 | 563790600.54 | 4825493.53 | 100% | 100% | 98.69% | -1.31% | 549320450.7214 | 559882667.6243 | 4.77% | 6.856% | 29191639 | 41959106
SEC | Egypt Office | 12 | Closed | UGC | UGC | PE-260 | Sanabel con.at Jeddah | Abdelazeem Morsy | Karim Ahmed | 22632720 |  | 0 | 22632720 | 20332830 | 20332830 | 18105216.2558 | 14631659.15 | 13921556.3 | 260218.39 | 100% | 100% | 94.97% | -5.03% | 18105216.2558 | 14288617 | 10.93% | 35.35% | 2473940 | 8001060.85
SEC | Egypt Office | 13 | Closed | UGC | UGC | PE-262 | Reinf. of Thuwal Town KAUST 2 | Abdelazeem Morsy | Karim Ahmed | 33637620 |  | 0 | 33637620 | 30076208 | 30076208 | 26769109.1501 | 26771325.07 | 26000800.95 | 186200.77 | 100% | 100% | 97.07% | -2.93% | 26769109.1501 | 26527102.65 | 10.76% | 20.41% | 3619408 | 6866294.93
SEC |  | 14 | Closed | Substation | 110KV | PE-296 | Waly Alahad-4 110/13.8KV SS | Moustafa Elkayyal | Nishi | 130635969 |  | -1671201 | 128964768 | 112101198 | 112101198 | 98198497.7601 | 94570747.76 | 91471292.35 | 2340984.27 | 100% | 100% | 96.65% | -3.35% | 98198497.7601 | 92006485.8239 | 6.63% | 26.67% | 8546279 | 34394020.24 | -6192011.9362
SEC |  | 15 | Closed | Substation | 110KV | PE-281 | 110KV SS - KAEC-3 | Hossam Mahrous | Abhinav | 127230866 |  | 2138906 | 129369772 | 113267888 | 113267888 | 100611364.9432 | 98200658.21 | 96063547.56 | 1090926.7 | 100% | 100% | 97.68% | -2.32% | 100611364.9432 | 83501920.6274 | 7.41% | 24.09% | 9586300 | 31169113.79 | Substation Energized. TCC Received
SEC |  | 16 | Closed | Substation | 110KV | PE-280 | 110KV SS - KAEC-2 | Hossam Mahrous | Abhinav | 120233866 |  | 535843 | 120769709 | 106092130 | 106092130 | 73373249.352 | 92570395.55 | 90747657.88 | 843077.35 | 100% | 100% | 97.96% | -2.04% | 73373249.352 | 85802992.8617 | 7.41% | 23.35% | 8949035 | 28199313.45 | All works completed. Exp. Energization by 07-01-26
Masar |  | 17 | Closed | Substation | 0 | PE-185 | NG Taif | Omar Samman | Azeem | 151200000 |  | 0 | 151200000 | 136677775 | 136677775 | 136766926.6133 | 179140446.91 | 178420398.8 | 1005154.46 | 100% | 100% | 99.11% | -0.89% | 136766926.6133 | 177656495.5787 | 0% | -18.48% | - | -27940446.91
SEC |  | 18 | Closed | Substation | 380KV | PE-267 | CONST KAR 380 110KV BSP | Bandar Khalid Al Qalah | Azeem | 383000000 |  | 0 | 383000000 | 343679335.49 | 343679335.49 | 314588822.1034 | 335815067 | 333308901.06 | 2073191.76 | 100% | 100% | 99.12% | -0.88% | 314588822.1034 | 321924642.6609 | 7.41% | 12.32% | 28384288 | 47184933
SEC |  | 19 | Closed | Substation | 110KV | PE-291 | HAMRA AL ASAD 110/13.8 KV SUB | Mohamed Omar | Nishi | 121141296 |  | 0 | 121141296 | 95727491 | 95727491 | 94752042.0846 | 107618108.03 | 105993292.05 | 435789.6 | 100% | 100% | 98.31% | -1.69% | 94752042.0846 | 102209933.5443 | 9.87% | 11.16% | 11962119 | 13523187.97
SEC |  | 20 | Closed | Substation | 110KV | PE-292 | Shoran-2 110/13.8 KV - Madinah | Mohamed Omar | Ayush Ranjan | 119245157 |  | 0 | 119245157 | 93281367 | 93281367 | 92920111.715 | 101735210.01 | 98956272.91 | 859342.87 | 100% | 95% | 97.07% | -2.93% | 92920111.715 | 98782085.2283 | 6.29% | 14.68% | 7498514 | 17509946.99
SEC |  | 21 | Running | Substation | 110KV | PE-315 | 110KV Salam Royal Palace | Ahmed Faisal | Marwan | 218577987 |  | 0 | 218577987 | 185847008 | 185847008 | 161810308.491 | 191385813.48 | 138466773.85 | 14179162.76 | 82.21% | 100% | 71.89% | -10.32% | 161810308.491 | 122491730.4422 | 7.61% | 12.44% | 16633785 | 27192173.52
SEC |  | 22 | Running | UGC | UGC | PE-246 | UM-AL-JOUD BSP | Bandar Khalid Al Qalah | Hasan | 36073440 |  | 0 | 36073440 | 27705016 | 27705016 | 26639369.6776 | 34191905.77 | 25769527.44 | 3270045.69 | 79.2% | 100% | 74.89% | -4.312% | 26639369.6776 | 23871834.9778 | 5.83% | 5.216% | 2103082 | 1881534.23
SEC | Egypt Office | 23 | Running | Substation | 380KV | PE-263 | MOWAIH PV 380/110V BSP | Ahmed Aboelseoud | Eslam Elmowafy | 217950300 |  | 34406000 | 252356300 | 226577283.52 | 226577283.52 | 201790387.0252 | 218027760.76 | 210838408.49 | 1734362.51 | 99.3% | 100% | 97.31% | -1.99% | 201790387.0252 | 201497017.1126 | 6.28% | 13.6% | 15847975.64 | 34328539.24
SEC | Egypt Office | 24 | Running | Substation | 110kv | PE-265 | 110/33 KV ALMAHANI S/S IN TAIF | Khaled Abdelaty | Mai Abdelmaksoud | 131418256 |  | 0 | 131418256 | 99148949 | 97883916 | 98213454.4101 | 131417297.98 | 117308781.6 | 8281864.99 | 97.3% | 100% | 87.78% | -9.52% | 98213454.4101 | 105855522.6348 | 4.54% | 0.000729% | 5970533 | 958.02
SEC | Egypt Office | 25 | Running | Substation | 110KV | PE-266 | EXT. OF THE EXIS. THAGEF &ADAM | Mahmoud Sobhy | Ibrahim Eldesouky | 37810500 | 0 | 0 | 37810500 | 29053444 | 29053444 | 26193144.6605 | 33735677.93 | 24677613.15 | 4033183.23 | 82.48% | 90% | 69.96% | -12.52% | 26193144.6605 | 24051289.03 | 14.41% | 10.78% | 5448232 | 4074822.07
NEOM | Egypt Office | 26 | Running | SDCC | SDCC | PE-286 | SEC Smart Distribution Control Centre | Mostafa Lashien | Kareem Sobhy | 388016486 | 0 | 0 | 388016486 | 152961744 | 152961744 | 152961744 | 355607182.98 | 183039784.93 | 107455296.96 | 79.69% | 100% | 49.9% | -29.79% | 152961744 | 153451188 | 7.41% | 8.353% | 28741962 | 32409303.02
SEC |  | 27 | Running | Substation | 380kv ex | PE-287 | Exp. of YCNT BSP for Power to Neom | Zohaib | Azeem | 351450000 |  | -12000000 | 339450000 | 269597677 | 269597677 | 227723233.2905 | 283597331.01 | 219630392.47 | 22370628.23 | 80.6% | 100% | 77.23% | -3.37% | 227723233.2905 | 199242192.7361 | 4.03% | 16.45% | 13688790 | 55852668.99
SEC |  | 28 | Running | Substation | 110kv ex | PE-294 | Airport C (KAIA) Interconnection REINF. | Khaled Abdelaty | Hasan | 40038020 |  | 0 | 40038020 | 29873177 | 29873177 | 24176246.9667 | 30116251 | 21182712.75 | 2190968.94 | 91.8% | 100% | 69.28% | -22.52% | 24176246.9667 | 14463539.67 | 7.15% | 24.78% | 2862718 | 9921769
SEC | Egypt Office | 29 | Running | UGC | UGC | PE-295 | Interconnection of AJM-1 (New Jamoom) | Abdelazeem Morsy | Badr Eldin khaled | 76529100 | 383109 | 0 | 76529100 | 67860130.488 | 67860130.488 | 46141311.4521 | 57711052.13 | 50088335.23 | 2049372.84 | 93.11% | 100% | 86.19% | -6.92% | 46141311.4521 | 45865606 | 5.66% | 24.59% | 4329636 | 18818047.87
Masar | Egypt Office | 30 | Running | Substation | 380kv ex | PE-301 | Expansion of Mowaih PV 380kV BSP | Ahmed Aboelseoud | Eslam Elmowafy | 335406292 |  | 0 | 335406292 | 265264290.89 | 265264290.89 | 177111267.0549 | 299469903.68 | 260941377 | 13826642 | 96.5% | 100% | 86.1% | -10.4% | 177111267.0549 | 242774376 | 10.71% | 10.71% | 35922013.8732 | 35936388.32
modon | Egypt Office | 31 | Running | 110KV ss | 110KV | PE-305 | KAR-2 -110KV SS & UGC | Mohammad Obeidat | Merna mohamed | 165245150 | 359454.3 | 3114375 | 168359525 | 119732538.07 | 119732538.07 | 94514300.9008 | 131524606.83 | 86199371.54 | 15867596.42 | 77.7% | 97.1% | 66.76% | -10.94% | 94514300.9008 | 45683059.3687 | 10.57% | 21.88% | 17735202 | 36834918.17
SEC | Egypt Office | 32 | Running | Substation | 132KV | PE-307 | 132/13.8KV Sub Industrial City Tabuk | Shafqat Zia | Ahmed Labib | 108569000 |  | 608288 | 109177288 | 95211669 | 95211669 | 85690502.1 | 98994799 | 94648104.48 | 728456.81 | 99% | 100% | 95.75% | -3.25% | 96547402 | 88768157 | 9.09% | 9.327% | 9870304 | 10182489
SEC | Egypt Office | 33 | Running | Substation | 110KV | PE-308 | 110KV Salam Royal | Ahmed Faisal | Eslam Elmowafy | 152000000 |  | 0 | 152000000 | 0 | 0 | 0 | 139571180.71 | 873763 | 61709311 | 0.4% | 7.3% | 0.5% | 0.1% | 0 | 3075879 | 8.257% | 8.177% | 12550458.3354 | 12428819.29
SEC |  | 34 | Running | Substation | 380kV | PE-312 | Const of Southern 380KV BSP ¦ Al Ula | Pervaiz Akbar | Syed Ibrahim Quadri | 878629474 |  | 0 | 878629474 | 648755834 | 648755834 | 465270388.943 | 757377634.45 | 632547247.41 | 62103657.9 | 87.6% | 100% | 82.85% | -4.75% | 465270388.943 | 632547247.41 | 6.54% | 13.8% | 57462368 | 121251839.55
SEC | Egypt Office | 35 | Running | Substation | 380kv ex | PE-314 | Expansion of Tabuk BSP & Duba BSP | Shafqat Zia | Ahmed Labib | 205975000 | 6494939 | 0 | 205975000 | 158955720 | 158955720 | 155636874 | 184193505.87 | 168976269 | 4980635.45 | 95.9% | 100% | 90.8% | -5.1% | 152120923.455 | 148942000 | 9.08% | 10.57% | 18708299 | 21781494.13
SEC |  | 36 | Running | HVDC | HVDC | PE-319 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 | Khaled Abdelaty Hassan Emara Shehata | Shahabas/ Azhagar | 1055702232 |  | 0 | 1055702232 |  | 0 | 249546087.8879 | 916415702.29 | 464308840.06 | 215332179.35 |  | 0% | 46.3% | 46.3% | 249546087.8879 | 464308840.06 | 9.09% | 13.19% | 95963333 | 139286529.71
SEC |  | 37 | Running | OHTL | OHTL | PE-324 | Stage-2 HVDC OHTL COA-WOA | Ahmed Radwan | Sakthi | 954530000 |  | 0 | 954530000 | 529361790 | 529361790 | 361392070.7088 | 868139130.13 | 600488974.6 | 202482994.25 | 64.81% | 70% | 53.86% | -10.95% | 361392070.7088 | 600488974.6 | 19.58% | 9.051% | 186896974 | 86390869.87
SEC |  | 38 | Running | OHTL | OHTL | PE-329 | SEC ¦ 132KV OHTL Tabuk | Mohan | Ganesh | 98175162 |  | 12443769 | 110618931 | 88690836.85 | 88690836.85 | 61788402.4803 | 76756532.8 | 56634484.76 | 8012958.66 | 68.11% | 80% | 72.57% | 4.461% | 61788402.4803 | 56634484.76 | 13.06% | 30.61% | 14450340 | 33862398.2
SEC |  | 39 | Running | OHTL | OHTL | PE-331 | UMM AL-QURA CEMENT OHTL | Sudhakar | Anwar Shiek / Bandi Mansoor | 176416000 | 4734324 | 0 | 176416000 | 102697920.6 | 102697920.6 | 103262607.5323 | 139730200.71 | 67602516.14 | 14602715.43 | 62.17% | 100% | 48.1% | -14.07% | 103262607.5323 | 67602516.14 | 13.04% | 20.8% | 23010783 | 36685799.29
SEC |  | 40 | Running | OHTL | OHTL | PE-332 | 110KV OHTL FOR MAADEN-AL MAHAD | Abdelazeem Morsy | Dhana Baskar P | 122169900 |  | 0 | 122169900 | 52976660.97 | 52976660.97 | 47873053.5816 | 106344412.52 | 33397052.55 | 25609552.77 | 29.21% | 42% | 28.03% | -1.18% | 47873053.5816 | 33397052.55 | 12.95% | 12.95% | 15825987.48 | 15825487.48
SEC |  | 41 | Running | BESS | BESS | PE-338 | Battery Energy (BESS) -Rabigh | Mohamed Elmazawy | Vivek / Senthil | 522306062 | 0 | 0 | 522306062 | 463197875.824 | 411024102.624 | 310575728.3669 | 324874550.98 | 298955885.16 | 4517261.23 | 99.25% | 100% | 91.72% | -7.533% | 361704502 | 298955885.16 | 7.41% | 37.8% | 38702879 | 197431511.02 | Project Energized. TCC Invoice submitted for SEC approval.
SEC | Egypt Office | 42 | Running | Substation | 110KV | PE-345 | Arafat SS | Mostafa Ayop | Mai Abdelmaksoud | 168310428 |  | 0 | 168310428 | 86215796.48 | 55484993 | 43488747.0335 | 146397893.76 | 32758459.02 | 52283239.95 | 23.9% | 50% | 18.65% | -5.25% | 43488747.0335 | 35445893.1404 | 13.04% | 13.02% | 21947679.8112 | 21912534.24
SEC |  | 43 | Running | BESS | BESS | PE-347 | Construction of Tabuk Substation for BESS | Amin El sayed | Vivek / Senthil | 432362000 | 3117500 | 3117500 | 435479500 | 224803897.6 | 110130259.86 | 89192525 | 394726635.87 | 124043236.07 | 145192475.67 | 40.62% | 72.38% | 26.26% | -14.36% | 89192525 | 124043236.07 | 6.54% | 9.358% | 28276475 | 40752864.13
SEC | Egypt Office | 44 | Running | Substation | 110KV | PE-328 | CONSTRUCTION OF ALWESSAM TAIF 110/13.SKV SUBSTATION IN TAIF | Moustafa Elkayyal | Karim Ahmed | 110239453 |  | 0 | 110239453 | 8447743 | 6328855 | 10803801.4 | 102076167.07 | 7108037.46 | 68900629.4 | 26.08% | 55% | 4.48% | -21.6% | 10803801.4 | 10134284 | 7.41% | 7.405% | 8168743 | 8163285.93
SEC | Egypt Office | 45 | Running | Substation | 132kv | PE-368 | CONSTRUCTION OF A NEW 132/13.8KV SUBSTATION RABIAH TABUK (RBTBK) & ITS 132KV INTERCONNECTION IN TABUK | Shafqat Zia | Badr Eldin khaled | 121779924 | 0 | 0 | 121779924 | 12015009.4334 | 12015009.4334 | 11934596.32 | 112758346.68 | 12732354.67 | 69974600.74 | 10.54% | 50% | 10.54% | 0% | 11934596.32 | 12732354.67 | 7.41% | 7.408% | 9021577 | 9021577.32
SEC | Egypt Office | 46 | Running | Substation | 110KV | PE-369 | CONSTRUCTION OF A NEW 110/13.8 kV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammed Ilyas | Menna Abdelhamid | 103814627 | 0 | 0 | 103814627 | 5386589 | 5386589 | 11694402 | 95242778.15 | 4207454 | 63822107.68 | 6.99% | 29.46% | 3.91% | -3.08% | 11694402 | 6244377 | 8.26% | 8.257% | 8571850 | 8571848.85
SEC | Egypt Office | 47 | Running | Statcom | STATCOM | PE-346 | Installation of New STATCOM ±300MV AR At 132kV Level At Northern BSP | Pervaiz Akbar | Eslam Elmowafy | 236924477 |  | 0 | 236924477 | 7451413.4 | 7451413.4 | 0 | 218363573.54 | 2617071 | 93766779 | 2.4% | 7.3% | 1.3% | -1.1% | 0 | 8102386 | 7.834% | 7.834% | 18560903.46 | 18560903.46
SEC |  | 48 | Running | OHTL | OHTL | PE-359 | CONSTRUCTION OF A NEW 110KV D/C OHTL FOR A NEW 110/13.8KV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammed Ilyas | Dhana Baskar P | 204670557 | 0 | 0 | 204670557 | 2749442 | 2749442 | 21567927 | 177975988.32 | 5061427.91 | 90972460.41 | 3.7% | 30% | 0.51% | -3.19% | 21567927.34 | 5061427.91 | 13.04% | 13.04% | 26694569 | 26694568.68
SEC | Egypt Office | 49 | Running | Substation | 380KV | PE-365 | CONSTRUCTION OF A NEW SUBSTATION KHR-1 380/110 KV BSP & EXP OF EXISTING MHR BSP UNDER RENEWABLE ENERGY | Ahmed abdelhadi | Ahmed Labib | 505052515 |  | 0 | 505052515 | 22770359 | 22770359 | 49472252 | 476464636.67 | 29661850 | 300797346 | 8.2% | 14.64% | 3.5% | -4.7% | 49472252 | 43373016 | 5.66% | 5.66% | 28587878 | 28587878.33
SEC | Egypt Office | 50 | Running | Substation | 380KV | PE-370 | CONSTRUCTION OF A NEW SUBSTATION KHR-2 380/110 KV BSP UNDER RENEWABLE ENERGY POWER PLANT (WOA) | Hossam Mahrous | Merna mohamed | 467466515 | 0 | 0 | 467466515 | 55568352.6 | 55568352.6 | 45788823.5 | 441006145.98 | 22761530.91 | 246885846.72 | 7% | 15% | 4.14% | -2.86% | 45788823.5 | 34326820.3143 | 5.66% | 5.66% | 26458605 | 26460369.02
SEC |  | 51 | Running | Substation | 110KV | PE-380 | AL JAMOOM 110/33/13.8KV SUBSTATION (Te3830) | Bandar Al Qalah | Karim Ahmed | 111410000 |  | 0 | 111410000 | 0 | 0 | 0 | 89127999.87 | 97712.79 | 31258870.64 | 5.2% | 33% | 0.04% | -5.16% | 0 | 1039569 | 20% | 20% | 22282000 | 22282000.13
|  | 52 | Running | Substation | 380KV | PE-388 | CONSTRUCTION OF HENAKIYAH-3 PV | Mohamed Omar | Azeem | 619500000 |  | 0 | 619500000 | 0 | 0 | 0 | 582079445.61 | 83230.5 | 0 |  |  | 0.01% | 0.01% | 0 | 0 | 6.1% | 6.04% | 37789500 | 37420554.39
|  | 53 | Running |  |  | PE-398 | CONSTRUCTION OF NEW 110KV D/C OHTL FOR NEW SUBSTATION BAHITAH HOUSING IN TAIF-WOA | Mohan |  | 125693278 |  | 0 | 125693278
|  | 54 | Running |  |  | PE-391 | ADDITION OF TWO (2) 80/100MVA 132/33KV TRANSFORMERS AT DUBA-2 SUBSTATION. | Shafqat Zia | Ahmed Labib | 104775000 |  | 0 | 104775000
SEC |  | 55 | Running |  |  | PE-371 | Replacement of Musayjid BSP By Expansion of PS-2 BSP in Western Operating Area. | Mahmoud sobhy |  | 391050000 |  | 0 | 391050000
[7 empty] | INFRA UNIT |  |  | 382840600 | 0 | 0 | 382840600 | 225259885.458 | 172353252.65 | 115110727.5498 | 357912833.75 | 160657875.65 | 128757189.13 | 85.6% | 95% | 38.73% | -46.87% | 115110727.5498 | 171699870.69 | 10.88% | 6.713% | 41867052 | 26006882 | -56589143.1402
SEC | Egypt Office | 56 | Running | Infra | Infra | PE-289 | SWRO Des. Plant ¦ Shoaibha PP | Fathi Mohamed moussa | Mohamed Saeed Harb | 126266000 |  | 0 | 126266000 | 88094301.22 | 72941522.17 | 55904070.9364 | 119159175.13 | 66368713.16 | 35888076.22 | 85.1% | 95% | 48.51% | -36.59% | 55904070.9364 | 62293668.4935 | 9.91% | 5.63% | 12512982 | 7108825
SEC | Egypt Office | 57 | Running | Infra | Infra | PE-293 | SWRO Des. Plant- Shuqaiq Power Plant | Fathi Mohamed moussa | Mohamed Saeed Harb | 123984000 |  | 0 | 123984000 | 59017312.8676 | 40833141.37 | 35678613.8934 | 120106372.46 | 41541167.19 | 52696086.66 | 88.5% | 95% | 30.15% | -58.35% | 35678613.8934 | 52466694.5322 | 8.87% | 3.89% | 10991649 | 4817743
SEC | Egypt Office | 58 | Running | Infra | Infra | PE-303 | Water Treatment Plant & Tank - Jeddah | Fathi Mohamed moussa | Mohamed Saeed Harb | 132590600 |  | 0 | 132590600 | 78148271.3704 | 58578589.11 | 23528042.72 | 118647286.16 | 52747995.3 | 40173026.25 | 83.2% | 95% | 37.52% | -45.68% | 23528042.72 | 56939507.6643 | 13.85% | 10.62% | 18362421 | 14080314
[9 empty] | PE-243 | 1 | 1 | 168693200 | 168693200 | 168693200 | 58578589.11
[9 empty] | PE-241 | 1 | 0.989 | 452757500 | 452757500 | 447777167.5
[9 empty] | PE-257 | 1 | 0.9989 | 125309260 | 125309260 | 125171419.814
[9 empty] | PE-258 | 1 | 0.9 | 31600000 | 31600000 | 28440000
[9 empty] | PE-270 | 1 | 0.9841 | 119195073 | 119195073 | 117299871.3393
[9 empty] | PE-290 | 1 | 0.9842 | 126251953 | 126251953 | 124257172.1426
[9 empty] | PE-254 | 1 | 1 | 579828000 | 579828000 | 579828000 |  | 246885846.72
[9 empty] | PE-260 | 1 | 0.975 | 22632720 | 22632720 | 22066902
[9 empty] | PE-262 | 1 | 0.9696 | 33637620 | 33637620 | 32615036.352
[9 empty] | PE-296 | 1 | 0.9453 | 130635969 | 130635969 | 123490181.4957
[9 empty] | PE-281 | 1 | 0.99 | 127230866 | 127230866 | 125958557.34
[9 empty] | PE-280 | 1 | 1 | 120233866 | 120233866 | 120233866
[9 empty] | PE-185 | 1 | 0.9965 | 151200000 | 151200000 | 150670800
[9 empty] | PE-267 | 1 | 0.9794 | 383000000 | 383000000 | 375110200
[9 empty] | PE-291 | 1 | 0.9998 | 121141296 | 121141296 | 121117067.7408
[9 empty] | PE-292 | 1 | 0.9925 | 119245157 | 119245157 | 118350818.3225
[9 empty] | PE-315 | 1 | 0.959 | 218577987 | 218577987 | 209616289.533
[9 empty] | PE-263 | 1 | 0.99 | 217950300 | 217950300 | 215770797
[9 empty] | PE-246 | 1 | 0.8895 | 36073440 | 36073440 | 32087324.88
[9 empty] | PE-265 | 1 | 0.923 | 131418256 | 131418256 | 121299050.288 | 7451413.4
[9 empty] | PE-266 | 1 | 0.8663 | 37810500 | 37810500 | 32755236.15
[9 empty] | PE-286 | 0.9831 | 0.9021 | 388016486 | 381459007.3866 | 350029672.0206
[9 empty] | PE-287 | 0.9338 | 0.9508 | 351450000 | 328184010 | 334158660
[9 empty] | PE-294 | 1 | 0.8399 | 40038020 | 40038020 | 33627932.998
[9 empty] | PE-295 | 1 | 0.9052 | 76529100 | 76529100 | 69274141.32
[9 empty] | PE-301 | 1 | 0.985 | 335406292 | 335406292 | 330375197.62
[9 empty] | PE-305 | 0.93 | 0.9 | 165245150 | 153677989.5 | 148720635
[9 empty] | PE-307 | 0.9806 | 0.9831 | 108569000 | 106462761.4 | 106734183.9
[9 empty] | PE-308 | 0.1002 | 0.1933 | 152000000 | 15230400 | 29381600
[9 empty] | PE-312 | 0.9864 | 0.9615 | 878629474 | 866680113.1536 | 844802239.251
[9 empty] | PE-314 | 0.9223 | 0.9198 | 205975000 | 189970742.5 | 189455805
[9 empty] | PE-319 | 0.9717 | 0.9434 | 1055702232 | 1025825858.8344 | 995949485.6688
[9 empty] | PE-324 | 0.963 | 0.82 | 954530000 | 919212390 | 782714600
[9 empty] | PE-329 | 0.995 | 0.9493 | 98175162 | 97684286.19 | 93197681.2866
[9 empty] | PE-331 | 1 | 0.7455 | 176416000 | 176416000 | 131518128
[9 empty] | PE-332 | 0.9983 | 0.6936 | 122169900 | 121962211.17 | 84737042.64
[9 empty] | PE-338 | 1 | 0.9867 | 522306062 | 522306062 | 515359391.3754
[9 empty] | PE-345 | 0.8706 | 0.7051 | 168310428 | 146531058.6168 | 118675682.7828
[9 empty] | PE-347 | 1 | 0.7542 | 432362000 | 432362000 | 326087420.4
[9 empty] | PE-328 | 0.5545 | 0.2641 | 110239453 | 61127776.6885 | 29114239.5373
[9 empty] | PE-368 | 0.3583 | 0.313 | 121779924 | 43633746.7692 | 38117116.212
[9 empty] | PE-369 | 0.3826 | 0.2291 | 103814627 | 39719476.2902 | 23783931.0457
[9 empty] | PE-346 | 0.2002 | 0.1451 | 236924477 | 47432280.2954 | 34377741.6127
[9 empty] | PE-359 | 0.6799 | 0.2405 | 204670557 | 139155511.7043 | 49223268.9585
[9 empty] | PE-365 | 0.2581 | 0.2583 | 505052515 | 130354054.1215 | 130455064.6245
[9 empty] | PE-370 | 0.2585 | 0.255 | 467466515 | 120840094.1275 | 119203961.325
[9 empty] | PE-380 | 0.02 | 0.01 | 111410000 | 2228200 | 1114100
[9 empty] | PE-388 | 0.0652 | 0.0634 | 619500000 | 40391400 | 39276300
[9 empty] | PE-398 |  |  | 125693278 | 0 | 0
[9 empty] | PE-391 |  |  | 104775000 | 0 | 0
[9 empty] | PE-371 |  |  | 391050000 | 0 | 0
[13 empty] | 82.31% | 76.78%