## Marketing-Related Sheet
S.N. | Project Code | Project Name | Project Managers Name | Region | Marketing Required (Yes/No) | Requirement Provided (Yes/No) | PO Creation (Yes/No) | Marketing Completion (Yes/No) | Required for Closing Projects (Yes/No/N/A) | Start Date | Planned % | Actual % | Var. | Client | City | EOT STATUS (Submitted/Approved/Under Approval/ N/A) | TCC |  |  | FAC |  |  | Remarks
[10 empty] | Start Date | [6 empty] | Contract Date | Revised Date | Forecast Date | Contract Date | Revised Date | Forecast Date | Remarks
CENTRAL REGION UNIT (BASIL ALHAKAMI)
1 | PE-215 | SMP - O&M 3 Yrs | Mohamed Sabri | Central | No | No | No | No |  | 2022-04-01 | 100% | 100% | 0% | SEC | Riyadh | Approved | 2024-05-30 | 2025-06-04 | 2025-06-04 | 2024-05-30 | 2025-06-04 | 2025-06-04 | All certification Received
2 | PE-226 | KHASM-AL-AAN BSP | Amin El Sayed | Central | No | No | No | No |  | 2021-06-03 | 100% | 86.3% | -13.7% | SEC | Riyadh | Approved | 2023-02-03 | 2024-12-31 | 2027-01-24 | 2023-08-03 | 2025-05-31 | 2027-06-25 | Partial TCC Received ¦ Project on Hold
3 | PM-223 | GASCO - 2 | Fathi Mohamed | Central | No | No | No | No |  | 2021-06-21 | 100% | 99.91% | -0.09% | GASCO | Riyadh | Approved | 2023-07-29 | 2025-03-31 | 2025-10-31 | 2023-07-29 | 2025-03-31 | 2025-10-31 | Initial Handing over received
4 | PE-228 | SVC QASSIM -2 | Hany Kamal | Central | No | No | No | No |  | 2021-09-05 | 100% | 99.28% | -0.72% | SEC | Riyadh | Approved | 2023-11-05 | 2025-03-17 | 2025-03-17 | 2024-03-05 | 2025-07-17 | 2026-08-30 | TCC Received.
5 | PE-233 | Tabarjal 380KV BSP Expn. | Malik Qarioutyee | Central | No | No | No | No |  | 2021-12-12 | 100% | 99% | -1% | SEC | Riyadh | Approved | 2023-12-12 | 2025-12-30 | 2026-07-30 | 2024-05-12 | 2026-05-30 | 2026-12-30 | Partial TCC received on 16-Jan-24
6 | PE-245 | Hail OHTL | Rafa Awad Al Hassan | Central | No | No | No | No |  | 2022-08-15 | 100% | 96.12% | -3.88% | SEC | Riyadh | Approved | 2024-05-15 | 2024-12-30 | 2026-06-20 | 2024-10-15 | 2025-05-27 | 2026-11-15 | One line Energizaed. Another line by 20-Jun-26. Change Order approval is critical
7 | PE-247 | RIYADH SEDRA-2 | Anas Derzy | Central | No | No | No | No |  | 2022-09-29 | 100% | 99.1% | -0.9% | Roshn | Riyadh | Under Approval | 2024-09-03 | 2024-09-03 | 2025-09-20 | 2024-11-03 | 2024-11-03 | 2026-08-30 | Partial TCC received & 90% invoice approved
8 | PE-248 | PP10 Conv. | Rabei Mohamed Mohamed Attia Daoud | Central | No | No | No | No |  | 2022-10-13 | 100% | 95.76% | -4.24% | SEC | Riyadh | Approved | 2024-08-13 | 2025-12-27 | 2026-08-29 | 2025-11-13 | 2027-03-31 | 2027-11-29 | TCC milestone achieved. Certification not receied. Punchlist Clearance is critical
9 | PE-255 | 380kv D/C OHTL LILO SAAD OHTL | Malik Al Qaryotee | Central | No | Yes |  |  |  | 2022-10-23 | 89.98% | 75.18% | -14.8% | SEC | Riyadh | Approved | 2023-12-23 | 2025-06-05 | 2026-12-30 | 2024-06-23 | 2025-12-05 | 2027-07-01 | 1. Amendment for New circuit Arrangement at Tapping Point . 2. Outage requirements 3. Hardware fittings material for re-route portion
10 | PE-256 | Sudair PV 380KV BSP | Tariq Mahmoud Ali Alsheyab | Central | No | No | No | No |  | 2022-11-02 | 100% | 78.77% | -21.23% | SEC | Riyadh | Under Approval | 2024-09-02 | 2024-09-02 | 2026-10-30 | 2025-02-02 | 2025-02-02 | 2027-04-01 | SS portion energized. Delay in Receiving Permit UGC works and inside PP9 works (MTO,LOA& ARAMCO Permits)
11 | PE-259 | WAAD AL SHAMAAL 380KV BSP | Muhannad Ibrahim Al Heh | Central | No | No | No | No |  | 2022-11-06 | 100% | 96.93% | -3.07% | SEC | Riyadh | Approved | 2024-11-15 | 2025-05-30 | 2026-11-30 | 2025-04-15 | 2025-10-30 | 2027-05-02 | Paritally Energized on 09-Feb-26 ¦ Delay in receiving outage to enrgize CKT 2 Wind to Waad Alshamaal & Wind to TABARJAL energization (expected by Oct 26)
12 | PE-264 | TABARJAL-B 13213.8 KV S/S IN JOUF | Khalid Mohamed Aql | Central | No | No | No | No |  | 2023-05-17 | 100% | 99.18% | -0.82% | SEC | Riyadh | Approved | 2025-03-16 | 2025-06-30 | 2026-06-29 | 2025-08-16 | 2025-11-30 | 2026-11-29 | 1.Total of four circuits are planned; two are scheduled for energization by June 2026. 2.SE confirmation is still pending for the remaining two circuits.
13 | PE-271 | AL-DAR AL-BAIDHA 132/13.8KV SUB | Hassan Ayloti | Central | No | No | No | No |  | 2023-07-13 | 100% | 98.5% | -1.5% | SEC | Riyadh | Approved | 2024-11-12 | 2026-02-28 | 2026-03-17 | 2025-04-12 | 2026-07-28 | 2027-01-29 | Energized on 17-Mar-26 ¦ Other Circuit depends on Outage ¦ Expected - 31-Oct-26
14 | PE-272 | AL-MUNSIYAH 132/13.8KV SUB # 8273 | Mohamed El hag | Central | No | No | No | No |  | 2023-07-13 | 100% | 96.13% | -3.87% | SEC | Riyadh | Under Approval | 2024-11-13 | 2024-11-13 | 2026-09-07 | 2025-04-13 | 2025-04-13 | 2027-02-05 | One Circuit Energized. Other Circuit depends on Outage ¦ Expected - 31-Oct-26
15 | PE-273 | ALMANFOHA 132/13.8KV SUB # 8138 | Mohamed El hag | Central | No | No | No | No |  | 2023-07-12 | 100% | 98.6% | -1.4% | SEC | Riyadh | Under Approval | 2024-11-12 | 2025-11-30 | 2025-11-30 | 2025-04-12 | 2026-04-30 | 2027-01-28 | One Circuit Energized on 21-Dec-25
16 | PE-274 | NASIRIYAH 132/13.8KV SUB # 8154 | Omar Samman | Central | No | No | No | No |  | 2023-07-12 | 100% | 92.7% | -7.3% | SEC | Riyadh | Approved | 2024-11-12 | 2026-01-12 | 2025-12-31 | 2025-04-12 | 2026-06-12 | 2026-09-30 | One Energized on 11-Feb-26. TCC received with dated 31-Dec-2025
17 | PE-275 | 380kV Diriyah Gate-2 BSP # 9080 | Amin El Sayed | Central | Yes |  |  | yes |  | 2023-11-16 | 50.84% | 45.12% | -5.72% | SEC | Riyadh | Under Approval | 2025-11-16 | 2027-04-13 | 2027-06-09 | 2026-04-16 | 2027-09-11 | 2027-11-07 | Progress based on Internal Baseline. 1-Delay in approval of water proofing VO & removal of loose material, which affects the construction works. 2- Negative Cash flow. 3-Claim Approval 201 Mn for prolongation & inflation costs. 4- Delivery for disconnector switch expected to be delayed.
18 | PE-276 | SHARAFIYAH 380 KV SS | Mohamed Sabri | Central | No | No | No | No |  | 2023-08-01 | 100% | 93.78% | -6.22% | SEC | Riyadh | Under Approval | 2025-02-01 | 2025-02-01 | 2026-06-10 | 2025-07-01 | 2025-07-01 | 2026-11-07 | Partially Energized. 1.Taihan - Oil Joints 2.Design Approval - 6 Remote end ( 132 kV) 3.Gantry Foundation for Existing Substation 4.Unclear Shutdown schedule for Power and Communication link with all remote ends 5. Delay in Micro Trenching of FOC 25km
19 | PE-279 | AL-NAZEEM 132/13.8KV SS # 8271 | Nedal Alkhatib | Central | No | No | No | No |  | 2023-07-24 | 100% | 90.85% | -9.15% | SEC | Riyadh | Approved | 2024-11-23 | 2025-06-23 | 2026-12-31 | 2025-04-23 | 2025-11-23 | 2027-06-02 | Commissioing on Hold due to non-readiness of UG Contractor
20 | PE-299 | Reinf of 132KV Network of Baqaa | Yousef AlMohtaseb | Central | No | No | No | No |  | 2023-11-08 | 99.92% | 93.58% | -6.34% | SEC | Riyadh | Approved | 2025-05-07 | 2025-11-20 | 2026-10-31 | 2025-10-07 | 2026-04-20 | 2027-03-31 | 1.OHTL S/C & D/C crossing - Delay in HOT permits 2.Cutting point outage at TEE OFF location. 3.ERS System & TEE- OFF Tower Installation 4.Design Approval of Flood Protection
21 | PE-300 | 300 MVAR STATCOM | Ibrahim Jaradat | Central | Yes | no |  |  |  | 2024-03-06 | 79.28% | 69.16% | -10.12% | SEC | Riyadh | Under Approval | 2026-03-06 | 2026-09-06 | 2026-10-20 | 2026-08-06 | 2026-02-06 | 2026-03-22 | 1.Delay in delivery of AES scope material. (delay in these materials ,impact the project completion ) 2.Delay in 380 kv insulator (Lapp) 3.New fire pump-Delivery (change order), 4.Delay in delivery of MV grounding transformer
22 | PE-306 | NEW AL-ARED 380/132KV BSP | Munther Elkhatib | Central | No | No | No | No |  | 2023-10-19 | 100% | 94.68% | -5.32% | SEC | Riyadh | Under Approval | 2025-04-19 | 2025-08-19 | 2026-06-30 | 2025-09-19 | 2026-01-19 | 2026-11-30 | 1.Slow Punch list - Transformers ,GIS, AES 2.Delay in SEC UG Cable Vendor - New Line( Circuits 3 )
23 | PE-309 | Reliablity Enh.for SS of 9011 in Sudair | Mohsin Arshad | Central | Yes | Yes |  |  |  | 2025-12-24 | 45.04% | 21.89% | -23.15% | SEC | Riyadh | N/A | 2026-11-23 | 2026-11-23 | 2027-04-21 | 2027-04-23 | 2027-04-23 | 2027-09-19 | Current issues 1.Delay in Plan & Profile - OHTL 2.Delay in Plan & Profile - UG Cable ( T- off Tower Location) 3.Delay in SE supply GIS Bays 4.Delay in Material :- Tower, Hardware, Insulator 5. Delay in providing existing Design : Remote End, U/G 8500 to 8521, Basement & Sleeves Details, Telecom Room, Control Room Layouts 6.Delay in Mobilization of Project Team OHTL Site Engr & Project Engr, QA & QC Civil & Electrical 7. Unclear Shutdown for Project
24 | PE-310 | Al Shifa Housing 132/13.8KV SS | Meshari Alqarni | Central | No | No | No | No |  | 2024-01-22 | 94.6% | 86.92% | -7.68% | SEC | Riyadh | Under Approval | 2025-11-22 | 2026-06-21 | 2026-08-17 | 2026-04-21 | 2026-11-21 | 2027-01-17 | 1.Incomplete HV underground cable works under another contractor’s scope are impacting the substation energization activities. 2.STATCOM PQS approval remains pending with SEC/vendor, affecting material delivery and subsequent installation. 3.Delay in remote end (8131) works due to pending C1 work permit
25 | PE-326 | Shaqra Wind 380/132kV SS | Ahmed Mosaad Abdel Nabi Hussein | Central | Yes | no |  |  |  | 2024-10-24 | 96.75% | 68.77% | -27.98% | SEC | Riyadh | N/A | 2026-05-23 | 2026-05-23 | 2026-12-31 | 2026-10-23 | 2026-10-23 | 2027-06-02 | 1-Delay in the delivery of 132kV and 380kV GIB and Hybrid GIS (SEC Direct purchase) beyond the scheduled dates, where the original plan was December 2025; however, only the 132kV GIB was delivered in end of May 2026, while the 380kV GIB and Hybrid GIS are still pending. 2-Delay in the supply of AC and DC panels from AES up to date. 3- Delay in obtaining ITP approvals for DSM and TFR systems AES prequalification to perform the FAT in AES factory. 4-Change order confirmation for the additional scope , which holding following activities (Civil work for Search facilities - Guard house - security building and along with all septic tank and water connections , HCIS stage 3 finalization and approval , Procurement of all electrical , mechanical , security material related to this pending . 5-Delay in the approval of firefighting system designs due to changing multiple changes in the review process from SEC and adding new comments with each revision. 6- After approval of lightening panels design (MS Hawaa ) SEC insist to change the manufactural to new alternate as (MS hawaa )is currently suspended in the system 7- Confirmation of EOT which submitted 9-Apr-26.
26 | PE-335 | Battery Energy (BESS) - Qaisumah | Tariq Mahmoud Ali Alsheyab | Central | No | No | No | No |  | 2024-12-16 | 100% | 95.63% | -4.37% | SEC | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-11 | 2026-10-16 | 2026-10-16 | 2026-10-11 | Energized.
27 | PE-336 | Battery Energy (BESS) - Dawadmi | Mohamed Ahmed Abdellatif Abdelkader | Central | No | No | No | No |  | 2024-12-16 | 100% | 97.66% | -2.34% | SEC | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | 2026-10-16 | 2026-10-16 | 2026-10-10 | Energized.
28 | PE-337 | Battery Energy (BESS) - Airport | Tarig Mohammed | Central | No | No | No | No |  | 2024-12-16 | 100% | 98.83% | -1.17% | SEC | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-06 | 2026-10-16 | 2026-10-16 | 2026-10-06 | Energized.
29 | PE-339 | Battery Energy (BESS) - Jouf | Khalid Mohamed Aql | Central | No | No | No | No |  | 2024-12-16 | 100% | 98.62% | -1.38% | SEC | Jouf | N/A | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Energized.
30 | PE-348 | Construction of Hail-2 Substation for BESS | Muhannad Ibrahim Al Heh | Central | Yes | No |  |  |  | 2025-07-03 | 88.73% | 46.61% | -42.12% | SEC | Hail | N/A | 2026-06-03 | 2026-06-03 | 2026-09-15 | 2026-11-03 | 2026-11-03 | 2027-02-15 | 1-Delay in approving critical designs such as FF designs, & Remote end AMI , with some submittals open for more than 3 months 2- Delay in design inputs has delayed grid studies submission & approval cycles 3- Delay in Alfanar equipment delivery: - Auxiliary transformer - AC & DC Panels - TFR & DSM - Remote End AMI & Metering 4- Delay in BESS Supplier fire fighting protion delivery (BESS gas pipes) 5- Delay in Firefighting pumps delivery 6- Delay in surge arrestors, and post insulators delivery 7- Delay in 33Kv SWGR termination kits delivery 8- Delay in HGIS Delivery: 1 out of 2 Bays delivered 9- Delay in UPS delivery
31 | PE-353 | Conv of Riyadh CC PP10 - Phase 2 | Muhannad Badawi | Central | Yes | Yes |  |  |  | 2025-05-08 | 40.19% | 16.42% | -23.77% | SEC | Riyadh | N/A | 2027-05-08 | 2027-05-08 | 2028-01-13 | 2028-06-08 | 2028-06-08 | 2029-02-13 | 1.Base Design Approval : Disagreement with SE on interpretation of the Contract. 2.Engineering Review Cycle Delays : Agreed timelines for review are not being adhered. 3.Delivery durations for critical (LLIs) exceed the Contractual timeline, creating a significant risk to meeting the contractual milestones. 4.Accelerated Dec 2026 completion requested by SE for GT 1st Fire. 5.Site Access Gate Permits & Work Permit issues.
32 | PE-356 | 380KV OHTL ¦ MAWQAQ BSP CONNECTION | Omar Samman | Central | Yes | no |  |  |  | 2025-08-28 | 53.31% | 16.06% | -37.25% | SEC | Riyadh | N/A | 2027-02-28 | 2027-02-28 | 2027-12-02 | 2027-07-27 | 2027-07-27 | 2028-04-30 | 1) Revised Route with additional change order.Revised Route under approval 2) Finalization of the route is pending for the portion that falls under KSRR. 3) Cost and time impact resulting from the increased transmission line route length and associated scope changes. 4) Delay in approval of plan and profile
33 | PE-360 | SMP¦OPERATION & PROF. SERVICES (HES&HHU) | Hazem Mahmoud | Central | No |  |  |  |  | 2025-07-15 | 83.33% | 83.33% | 0% | SEC | Riyadh | N/A | 2026-07-14 | 2026-10-14 | 2026-10-14 | 2026-07-14 | 2026-10-14 | 2026-10-14 | Extension of 1 quarter received
34 | PE-362 | 132KV SS ¦CONST. SPORTS BOULEVARD-RIYADH | Mirza Ikramullah | Central | Yes | No |  |  |  | 2025-08-13 | 33.24% | 21.94% | -11.3% | SEC | Riyadh | N/A | 2027-02-11 | 2027-02-11 | 2027-09-30 | 2027-07-11 | 2027-07-11 | 2028-02-27 | Delay in Site Handing Over. Not handed over yet
35 | PE-316 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 | Mohamed Sabri | Central | Yes |  | No | No |  | 2024-06-27 | 79.32% | 69.71% | -9.61% | SEC | Riyadh | N/A | 2026-12-31 | 2026-12-31 | 2027-01-31 | 2027-05-31 | 2027-05-31 | 2027-07-01 | -
36 | PE-317 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 | Mohamed Sabri | Central | No |  |  | yes |  | 2024-06-27 | 89.48% | 78.73% | -10.75% | SEC | Riyadh | N/A | 2026-12-31 | 2026-12-31 | 2027-02-28 | 2027-05-31 | 2027-05-31 | 2027-07-29 | -
37 | PE-363 | SULYBIAH SS 8823 132/33KV | Youssef Al Mohtaesab | Central | Yes |  |  |  |  | 2026-01-25 | 5.05% | 3.42% | -1.63% | SEC | Qassim | N/A | 2027-07-25 | 2027-07-25 | 2027-10-13 | 2027-12-25 | 2027-12-25 | 2028-03-14 | 1. Delay in Receiving Design for GIS Package Supplied by SEC Vendor 2. Delay in soil investigation activities due to one corner of the substation located on farmland 3. Terminal compound 1 location changed 4. Repetition of soil investigation activities due to the client's rejection of the proposed vendor
38 | PE-372 | AL-DWADMI SS 8618 132/33KV | Mohamed Azhar | Central | Yes |  |  |  |  | 2026-01-14 | 8.58% | 5.79% | -2.79% | SEC | Riyadh | N/A | 2027-07-12 | 2027-07-12 | 2027-09-30 | 2027-12-12 | 2027-12-12 | 2028-03-01 | 1. Delay in approval of GEL 2. Delay of Receiving Design for GIS Package Supplied by SEC (GIS Delivery delayed ) 3. Delay in municipality approval 4. Delay in Issuance Of P.O Transformer
39 | PE-394 | NEW AL-GHADIR SS#8237 132/33K | Rafa Awad Al Hassan | Central | Yes |  |  |  |  | 2026-01-21 | 7.39% | 5.63% | -1.76% | SEC | Riyadh | N/A | 2027-09-21 | 2027-09-21 | 2027-10-21 | 2028-02-21 | 2028-02-21 | 2028-03-22 | -
40 | PE-395 | New Al- Wadi 132/13.8Kv substation #8224 and its Connection in Riyadh City | Osama Mahood | Central | Yes |  |  |  |  | 2026-02-11 | 2.36% | 3.9% | 1.54% | SEC-COA | Riyadh | N/A | 2027-10-11 | 2027-10-11 | 2027-11-04 | 2028-03-11 | 2028-03-11 | 2028-04-04 | 1- Civil construction and related engineering/design activities suspended due to site cavities discovered after Soil investigation report. 2- Under Ground cables radar scanning & cable route layout submission.
EASTERN REGION UNIT (BASIL ALHAKAMI)
Completed Projects | PE111 | CONST. QURAYYAH IPP 380/230KV - Samsung | #N/A | Eastern | No | No | No |  |  |  | 100% | 100% | 0% | SEC | Dammam
| PE127 | KDF Substation | #N/A | Eastern | No | No | No |  |  | 2013-07-07 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-128 | WEST of 2nd DIE 115/13.8 KV S/S | #N/A | Eastern | No | No | No |  |  | 2013-07-07 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-129 | DHAHIYAH 115/13.8 KV S/S | #N/A | Eastern | No | No | No |  |  | 2013-07-07 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE130 | As-Shayyit Substation | #N/A | Eastern | No | No | No |  |  | 2013-07-07 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-140 | CONSTRUCTION OF AL-UQAIR 380/115KV BSP AND EXPANSION OF JAWATHA 230/115KV S/S AND ABQAIQ CENTRAL 230KV S/S | #N/A | Eastern | No | No | No |  |  | 2014-04-30 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-141 | Construction of Al-Khafji 380/115/13.8 KV BSP | #N/A | Eastern | No | No | No |  |  | 2014-04-30 | 100% | 100% | 0% | SEC | Khafji | Approved
| PE159 | CONSTRUCTION OF AL-MAZROEYAH 115/13.8KV SUBSTAION IN AL-HASSA | #N/A | Eastern | No | No | No |  |  | 2015-06-01 | 100% | 100% | 0% | SEC | Al Hassa | Approved
| PE160 | CONSTRUCTION OF POWER FACTOR CORRECTION (PHASE II) FOR 115/13.8KV S/S IN AL-HASSA | #N/A | Eastern | No | No | No |  |  | 2015-06-01 | 100% | 100% | 0% | SEC | Al Hassa | Approved
| PE161 | AL -MANSURAH 115/13.8kV S/S TO 115/13.8KV GIS S/S IN AL-HASSA | #N/A | Eastern | No | No | No |  |  | 2015-06-01 | 100% | 100% | 0% | SEC | Al Hassa | Approved
| PE-166 | Construction of Dammam North 380/115/33 KV BSP | #N/A | Eastern | No | No | No |  |  | 2015-06-25 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE167 | Construction of Nariyah North 380/115/33kV BSP | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 99.9% | -0.1% | SEC | Nariyah | Approved
| PE-168 | Construction of Dammam Housing-1 115/13.8kV Substation | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-169 | Construction of Dammam Housing-2 115/13.8kV Substation | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-170 | Construction of Dammam Housing-3 115/13.8kV Substation | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-171 | Construction of Dammam Housing-4 115/13.8kV Substation | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-172 | Construction of Dammam Housing-5 115/13.8kV Substation | #N/A | Eastern | No | No | No |  |  | 2015-09-16 | 100% | 100% | 0% | SEC | Dammam | Approved
| PE-175 | 115/13.8KV QARYAT AL ULYA | #N/A | Eastern | No | No | No |  |  | 2015-12-30 | 100% | 99.9% | -0.1% | SEC | Qaryat | Approved
| PE-176 | 115/13.8KV HAFAR BATIN-6 | #N/A | Eastern | No | No | No |  |  | 2015-12-30 | 100% | 100% | 0% | SEC | Haffr Albatan | Approved
| PE-177 | ADDITION OF MV SWITCH GEAR IN JUBAIL | #N/A | Eastern | No | No | No |  |  | 2015-12-30 | 100% | 100% | 0% | SEC | Jubail | Approved
| PE-181 | EPC OF PRIMARY ELECTRICAL SUSBSTATION #3 | Sami Atta | Eastern | No | No | No |  |  |  | 100% | 100% | 0% | SEC | Ras Al Khair | Approved | 2021-12-30 | 2021-12-30 | 2021-12-22 | 2021-12-30 | 2021-12-30 | 2025-12-31 | All Certificates Recieved
| PE-199 | Construction of SPARK 380/115 KV BSP | Walid Ahmed Khater | Eastern | No | No | No |  |  | 2018-12-01 | 100% | 99.9% | -0.1% | SEC | Abqaiq | Approved | 2020-09-30 | 2020-09-30 | 2021-04-30 | 2025-06-30 | 2025-06-30 | 2025-05-31 | All Certificates Recieved
| PE209 | Reinforcement of Fadhili Gas Plant (FGP) and Qaisumah 380kV BSP Interconnection | #N/A | Eastern | No | No | No |  |  | 2019-10-29 | 100% | 100% | 0% | SEC | Fadhili | Approved | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| PE-213 | Construction of Hawiyah Unayzah Gas Reservoir Storage (HUGRS) 380/230 kV BSP and Expansion of Al-Uqair 380kV BSP | Moath Ahmad Mahmoud Almousa | Eastern | No | No | No |  |  | 2020-01-23 | 100% | 99.9% | -0.1% | SEC | Huwyha | Approved | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Sep-22 UQA :30-Aug-26 | HUW :31-Dec-22 UQA : 30-Sep-23 | HUW :31-Dec-22 UQA : 30-Sep-23 | HUW :27-May-25 UQA :30-Nov-26 | P1: All Certificates Recieved P2: No Certificates Recieved
| PE220 | INSTALLATION OF REACTOR IN QAISUMAH 380/115KV BSP | #N/A | Eastern | No | No | No |  |  | 2020-11-20 | 100% | 100% | 0% | SEC | Qaisumha | Approved | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| PE-229 | Construction of Temporary Rail Line (CO project of PE-181) | Sami Atta | Eastern | No | No | No |  |  |  | 100% | 100% | 0% | SEC | Ras Al Khair | Approved | NA | NA | NA | 2024-11-09 | 2024-11-09 | 2025-12-31 | All Certificates Recieved
| PE-240 | SWCC ¦ OHTL Portion | Moath Ahmad Mahmoud Almousa | Eastern | No | No | No |  |  | 2022-05-23 | 100% | 99.9% | -0.1% | SWCC | Jubail | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-01-31 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC Pending on PE-238
41 | PE-214 | UTHMANIYAH | Munther Alkhatib | Eastern | No | No | No | No |  | 2020-02-23 | 100% | 99.98% | -0.0225% | Aramco | Dammam | Approved | 2023-07-27 | 2024-11-30 | 2024-09-15 | 2023-11-04 | 2024-11-30 | 2026-04-30 | All Certificates Recieved FAC not Not applicable/MCC
42 | PE-227 | Ibn zahr Expn. | Walid Khater | Eastern | No | No | No | No | No | 2021-06-10 | 100% | 88.29% | -11.71% | SEC | Dammam | Approved | 2022-09-10 | 2024-04-30 | 2026-11-05 | 2022-11-10 | 2024-06-30 | 2027-01-05 | -
43 | PE-238 | SWCC ¦ BSP Portion | Sami Abdou Sayed Atta | Eastern | No | No | No | No |  | 2022-05-23 | 100% | 98.17% | -1.828% | SWCC | Jubail | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-06-30 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC
44 | PE-239 | SWCC ¦ Solar Package | Walid Khater | Eastern | No | No | No | No |  | 2024-02-14 | 100% | 90.7% | -9.3% | SWCC | Jubail | Under Approval | 2025-02-14 | 2025-02-14 | 2026-06-30 | 2025-02-14 | 2025-02-14 | 2026-06-30 | -
45 | PE-277 | Thuqbah BSP 380/115KV | Mohammed Kutkut | Eastern | No | No | No | No |  | 2023-10-19 | 98.83% | 96.61% | -2.219% | SEC | Thuqbah | Approved | 2025-04-19 | 2026-05-31 | 2026-05-31 | 2025-09-19 | 2026-10-31 | 2027-01-31 | -
46 | PE-288 | Repl. of Berry Gas Plant 230/115KV SS | Moath Ahmad Mahmoud Almousa | Eastern | No | Yes | No | No | No | 2024-05-19 | 92.01% | 85.51% | -6.496% | SEC | Jubail | Under Approval | 2026-01-19 | 2026-01-19 | 2026-10-10 | 2027-05-19 | 2027-05-19 | 2027-11-10 | OHTL Portion after 11 months from SS which is shown here
47 | PE-302 | AL RAMES 380/115 KV BSP | Mohamed Ali Hafez Aman | Eastern | No | No | No | No |  | 2023-10-19 | 99.47% | 99.27% | -0.2054% | SEC | Dammam | Approved | 2025-04-19 | 2026-11-30 | 2026-05-31 | 2025-09-18 | 2027-04-30 | 2027-06-30 | Expected TCC will be on 13 Dec 26 due to delay of FOC readiness (31 Aug 2026) / Disconnector Switch
48 | PE-334 | Ghazlan-3 BSP | Mahmoud Abdelaal | Eastern | Yes |  |  |  |  | 2025-02-09 | 72.11% | 46.53% | -25.58% | SEC | Ghazlan | Under Approval | 2026-07-09 | 2026-07-09 | 2027-04-23 | 2026-12-09 | 2026-12-09 | 2027-09-30 | Planned % is based on orginal baseline however we have a submitted revised schedule showing 80% used for internal reporting
49 | PE-344 | Nariyah BSP | Mohamed Elhag | Eastern | Yes | No |  |  |  | 2025-02-27 | 95.49% | 56.83% | -38.66% | SEC | Nariyah | N/A | 2026-09-26 | 2026-09-26 | 2027-06-06 | 2027-02-26 | 2027-02-26 | 2027-11-08 | Delayed due to the delivery of GIS equipment Delayed 2times 1st delay till 25-June-26 2nd Delay till 25-Aug-26
50 | PE-355 | Construction of King Saud Air Base Facilities | Mohammed Kutkut | Eastern | Yes | Yes | No |  |  | 2025-08-10 | 17.57% | 12% | -5.57% | RSAF | Haffr Albatan | N/A | 2027-08-10 | 2027-08-10 | 2027-09-27 | 2028-12-10 | 2028-12-10 | 2028-12-10 | Only Scope Alfanar / There is no FAC only based on the 40 Months Completion
51 | PE-304 | 230/115kV SS ¦ JUBAIL SW REPLACEMENT | Munther Alkhatib | Eastern | Yes | No |  |  |  | 2025-08-31 | 19.69% | 12.6% | -7.09% | SEC | Jubail | N/A | 2027-08-31 | 2027-08-31 | 2028-04-27 | 2028-01-31 | 2028-01-31 | 2028-09-27 | Delayed due to site accessibility issues and Water leakage incident
52 | PE-302 | AL RAMES 380/115 KV BSP | Mohamed Ali Hafez Aman | Eastern | No | No |  |  |  | 2023-10-19 | 99.47% | 99.27% | -0.2054% | SEC | Dammam | N/A | 2025-04-19 | 2026-11-30 | 2026-05-31 | 2025-09-18 | 2027-04-30 | 2027-06-30 | Expected TCC will be on 13 Dec 26 due to delay of FOC readiness (31 Aug 2026) / Disconnector Switch
53 | PE-334 | Ghazlan-3 BSP | Mahmoud Abdelaal | Eastern | Yes | Yes |  |  |  | 2025-02-09 | 72.11% | 46.53% | -25.58% | SEC | Ghazlan | N/A | 2026-07-09 | 2026-07-09 | 2027-04-23 | 2026-12-09 | 2026-12-09 | 2027-09-30 | Planned % is based on orginal baseline however we have a submitted revised schedule showing 80% used for internal reporting
54 | PE-344 | Nariyah BSP | Mohamed Elhag | Eastern | Yes | no |  |  |  | 2025-02-27 | 95.49% | 56.83% | -38.66% | SEC | Nariyah | N/A | 2026-09-26 | 2026-09-26 | 2027-06-06 | 2027-02-26 | 2027-02-26 | 2027-11-08 | Delayed due to the delivery of GIS equipment Delayed 2times 1st delay till 25-June-26 2nd Delay till 25-Aug-26
55 | PE-355 | Construction of King Saud Air Base Facilities | Mohammed Kutkut | Eastern | Yes | Yes |  |  |  | 2025-08-10 | 17.57% | 12% | -5.57% | RSAF | Haffr Albatan | N/A | 2027-08-10 | 2027-08-10 | 2027-09-27 | 2028-12-10 | 2028-12-10 | 2028-12-10 | Only Scope Alfanar / There is no FAC only based on the 40 Months Completion
56 | PE-304 | 230/115kV SS ¦ JUBAIL SW REPLACEMENT | Munther Alkhatib | Eastern | Yes | No |  |  |  | 2025-08-31 | 19.69% | 12.6% | -7.09% | SEC | Jubail | N/A | 2027-08-31 | 2027-08-31 | 2028-04-27 | 2028-01-31 | 2028-01-31 | 2028-09-27 | Delayed due to site accessibility issues and Water leakage incident
57 | PE-366 | Qulayyib 380 kV BSP | Tarig Mohammed | Eastern | Yes |  |  |  |  | 2026-04-01 | 6.743% | 3.998% | -2.745% | MGC-Mutlaq Al Gowairi Company | Qulayyib Area | N/A | 2028-06-01 | 2028-06-01 | 2028-07-09 | 2029-06-01 | 2029-06-01 | 2029-07-09 | -
58 | PE-354 | Construction of NEW VSC HVDC Overhead Transmission Line for EOA-COA Link 1 | Moath Ahmad Mahmoud Almousa | Eastern | Yes |  |  |  |  | 2026-05-04 | 2.939% | 1.827% | -1.112% | SEC | Nariyah | N/A | 2028-11-04 | 2028-11-04 | 2028-11-22 | 2029-04-04 | 2029-04-04 | 2029-04-28 | -
WESTERN REGION UNIT (MOHAMMED ALBAZIE)
59 | PE-243 | Installation of Dynamic Reactive Power Compensation(DRPC) at Tabuk 380KV BSP | Shafqat Zia | Western | No |  |  |  |  | 2022-05-19 | 100% | 100% | 0% | SEC | Tabuk | N/A | 2024-07-19 | 2025-04-30 | 2025-04-30 | 2024-11-19 | 2026-01-30 | 2027-02-28 | Energization done without TSC Panel, TCC received. Partial PAC (21-Jan-2026) also received; Balance PAC & FAC upon delivery of remaining TSC Panel; Alfanar requested for FAC invoice and under discussion with SEC.
60 | PE-241 | Expansion of Existing Yanbu Central (YCNT) | Zohaib Iqbal | Western | No |  |  |  |  | 2022-02-06 | 100% | 98.9% | -1.1% | SEC | Yanbu,Umluj& Alwajh | N/A | 2024-01-06 | 2024-09-30 | 2024-09-30 | 2024-06-06 | 2025-02-28 | 2026-09-20 | PAC received, not yet energized due to SE shutdown issues for all the area
61 | PE-257 | Expansions of Existing MHD 380 KV BSP | Omar Samman | Western | No |  |  |  |  | 2022-11-03 | 100% | 99.89% | -0.11% | SEC | Madinah | N/A | 2024-05-03 | 2025-10-30 | 2025-12-30 | 2024-10-02 | 2026-03-30 | 2026-06-01 | As-built drawings under SEC review & approval. FAC certification waiting from SE; Request for issuance of FAC / Commitment for Completion of Outstanding Work was submitted on 20-Jul-26.
62 | PE-258 | Taif East Governorate Project | Mahmoud Sobhy El Sayed | Western | No | No |  |  |  | 2022-11-17 | 100% | 90% | -10% | SEC | Taif | N/A | 2024-04-17 | 2024-12-17 | 2026-09-30 | 2024-09-17 | 2025-05-16 | 2027-01-27 | 1. EOT-1 Approved upto 14-Dec-24, EOT-2 submitted on 12th Aug 25, TCC upto 17th Jun 26. (Under SEC Approval). EOT to be resubmitted. 2. SAS testing pending due to EWS V.O finalization and delivery (V.O) 3. OHTL Line readiness pending from SE, no clarity on readiness
63 | PE-270 | 110/13.8KV HARAZAT SUB JEDDAH | Muhammad Ilyas | Western | No | No | No | No |  | 2023-07-13 | 100% | 98.41% | -1.59% | SEC | Jeddah | N/A | 2024-11-13 | 2025-03-13 | 2025-07-29 | 2025-04-13 | 2025-08-13 | 2026-09-30 | Remote End Works: 1. Installation of Telecom Panels completed, testing will be done, once line readiness from client. (Dependent on Line Readiness from Client) 2. Final Settings of Line Protection Panels. (Dependent on Line Readiness from Client) Punchlist & As built works are in progress, completion date 30-Sep-26. Punchlist:Total 309 nos, 295 Completed, 5 nos ready to close. Asbuilt: 90% completed.
64 | PE-290 | Fadelah 110/13.8KV SS - JEDDAH | Khaled Abdelaty Hassan Emara Shehata | Western | No | No | No | No |  | 2023-07-24 | 100% | 98.42% | -1.58% | SEC | Jeddah | N/A | 2024-11-24 | 2025-09-24 | 2025-06-26 | 2025-04-24 | 2026-04-26 | 2026-09-30 | 1) Energization done with temporary line, (Permanent line readiness Dependent on Client). 2) AMI integration with WRCC. (Dependent on Line Readiness from Client). 3) Modon GIS extension bays (Shutdown -Relay setting ) 85% completed. Punchlist & As built works are in progress, completion date 30-Sep-26. Punch points : Out of 10, 2 completed, 3 ready to close. As built status: out of 12, 12 ready to close.
65 | PE-254 | HENAKIYAH BSP 380 KV | Mahmoud Sobhy El Sayed | Western | No | No | No | No |  | 2022-10-27 | 100% | 100% | 0% | SEC | Madinah | N/A | 2024-09-27 | 2024-12-31 | 2025-04-07 | 2025-02-27 | 2025-05-30 | 2026-05-07 | FAC received
66 | PE-260 | Sanabel con.at Jeddah | Abdelazeem Morsy | Western | No | No | No | No |  | 2022-12-29 | 100% | 97.5% | -2.5% | SEC | Jeddah | Approved | 2024-10-29 | 2025-01-30 | 2025-12-01 | 2025-03-28 | 2025-07-03 | 2026-10-03 | SAS Configuration and testing pending, due to AES team mobilization pending
67 | PE-262 | Reinf. of Thuwal Town KAUST 2 | Abdelazeem Morsy | Western | No | No | No | No |  | 2022-12-29 | 100% | 96.96% | -3.04% | SEC | Jeddah | Approved | 2024-08-29 | 2024-12-30 | 2025-12-01 | 2025-01-28 | 2025-06-03 | 2026-10-03 | SAS Configuration and testing pending
68 | PE-296 | Waly Alahad-4 110/13.8KV SS | Moustafa Elkayyal | Western | No | No | No | No |  | 2023-10-19 | 100% | 94.53% | -5.47% | SEC | Makkah | N/A | 2025-02-19 | 2025-11-19 | 2025-11-19 | 2025-07-19 | 2026-04-19 | 2026-10-26 | 1) Line readiness pending from SEC
69 | PE-281 | 110KV SS - KAEC-3 | Hossam Amin | Western | No | No | No | No |  | 2024-05-30 | 100% | 99% | -1% | SEC | Jeddah | N/A | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2026-04-29 | 2026-04-29 | 2026-06-30 | TCC, PAC Received. FAC Letter Submitted to Client
70 | PE-185 | NG Taif | Omar Samman | Western | No | No | No | No |  | 2018-02-25 | 100% | 99.65% | -0.35% | NG | Taif | Under Approval | NA | NA | NA | 2021-02-25 | 2026-07-14 | 2027-06-30 | EOT: Contract amendment approved,PCC on 14th Jul 25, EOT-2 submitted on 4th Nov 25, with 8 months (PCC: 14th Mar 26), Under SEC approval 1) All cable ceiling end joints works replacing works in progress, expected compeltion by 30th May 26. 2) Remote end-1 final setting done, Remote end 2 final setting completion by 10th May. 3) HV Test and end to end test pending expected completion by 15th Jun and 30th Jun
71 | PE-246 | UM-AL-JOUD BSP | Bander Khalid Al Qalah | Western | No | No | No | No |  | 2022-09-08 | 100% | 88.95% | -11.05% | SEC | Makkah | Under Approval | 2023-11-08 | 2025-02-07 | 2026-08-30 | 2024-04-08 | 2025-07-07 | 2027-01-30 | 1) EOT-2 submitted to client on 8th Jan 25, Revised TCC date confirmation is pending by SEC (Due to no clarity in readiness of remote end i.e. Fahya SS). EOT-2 resubmitted on 14-June-26 for Revised TCC on 31-July-27. Once approved, TCC letter will be submitted. 2) Remote end protection desing approval pending from SEC. Holding the procurement of loose material & modification work at remote end. 3) Protection scope for Fahya Substation is unknown: Due to which Design submission and approval for modification and procuring loose material is still not finalized 4) Restriction to work inside Rusifah Substation: No confirmation on Panel Installation is provided in Rusifah Substation due to limitations of space. Also, FOC cable pulling & termination inside SS is on hold. 5) Testing of Fiber & High Voltage cable is required to start. Waiting for SEC witness. 6) Shut down from SEC is required for Replacing Relay from Rushifah to Umaljoud. Still no clarity on shutdown also.
72 | PE-263 | MOWAIH PV 380/110V BSP | Mohammed Fathy | Western | No | No | No | No |  | 2023-03-29 | 100% | 99% | -1% | SEC | Taif | Under Approval | 2025-03-29 | 2025-10-31 | 2026-01-06 | 2025-08-28 | 2026-02-28 | 2026-08-30 | EOT is submitted with TCC and was approved on 21st Apr 26 Energization done, and TCC was received on 21st Apr 26
73 | PE-265 | 110/33 KV ALMAHANI S/S IN TAIF | Mudasir Sheikh | Western | No | No | No | No |  | 2023-05-14 | 100% | 92.3% | -7.7% | SEC | Taif | Under Approval | 2025-01-14 | 2025-11-30 | 2026-10-30 | 2025-06-14 | 2026-03-30 | 2027-02-28 | EOT: EOT submitted TCC upto 30-Nov-26. Under SEC approval. 1) delay in final setting approval for SWGR and Capacitor bank and line protection delaying open loop Tests 2) Delayed HV kit for GIS HV test (was scheduled by Jul-26) now rescheduled to 20-Aug-26 3) Delayed installations of the (HV Terminations, CSE, MV Terminations) pending subcontractor. (PO Under finalization with SCD) 4) Delayed open loop tests for the major equipment due to non-availability of SAS engineer. (Will be mobilized after Approval of final settings) 5) OHTL Line readinees (AL-mahani to MAHD), No clarity on the completion by other contractor.
74 | PE-266 | EXT. OF THE EXIS. THAGEF &ADAM | Sohaib Afdal | Western | No | No | No | No |  | 2023-05-14 | 100% | 86.63% | -13.37% | SEC | Taif | Under Approval | 2025-01-14 | 2025-10-14 | 2026-11-30 | 2025-06-14 | 2026-02-14 | 2027-03-30 | EOT: EOT-2 submitted with TCC date of 27-Jul-26. (Under SEC Approval) 1) AES Control panel (Mosaic and Annciator) detail design still under approval & no clarity on FAT date. (expected by Sep-26). 2) Missing BCU units for ADAM LCC (Hyundai), Provided by AES (Purchased from SIEMENS) Delayed since Feb-26, Latest provided date by AES is by Oct-26 3) Loose materials are required from AES for Protection, LCC Panels. To be compatible with existing systems and proceed commissioning activities 4) Delayed delivery of the PC Workstation (EWS) and the PO is still under Finalization with SCD 4) No Clarity of OHTL Line readiness.
75 | PE-267 | CONST KAR 380 110KV BSP | Bander Khalid Al Qalah | Western | No | No | No | No |  | 2023-06-01 | 100% | 97.94% | -2.06% | Masar | Makkah | Approved | 2025-05-31 | 2025-12-31 | 2025-12-31 | 2025-09-30 | 2026-05-01 | 2026-12-08 | 1.Close loop test completed 2. HVAC Testing: Completed 3. FF & FA Testing: All testing is completed and Remaining Final testing with ISD is in progress. 4. C04 modification work will be started after Energization of C06 Feeder as per SEC instruction. This will required 2 months to complete the task. 5. TCC received 6. New Change Order (confrimed) i.e. Duct Bank for future Area.-Completed 7.End to end test in progress, Expected engization by Aug'26 end.
76 | PE-280 | 110KV SS - KAEC-2 | Hossam Amin | Western | No | No | No | No |  | 2024-05-30 | 100% | 100% | 0% | SEC | Jeddah | Under Approval | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2026-04-29 | 2026-04-29 | 2026-04-29 | FAC received
77 | PE-286 | SEC Smart Distribution Control Centre | Hany Kamal | Western | No | No |  |  |  | 2024-07-25 | 98.31% | 90.21% | -8.1% | SEC | Jeddah | N/A | 2026-07-25 | 2026-07-25 | 2026-12-31 | 2027-09-24 | 2027-09-24 | 2028-02-18 | 1. SLD Submission for Downstream : CET/NARI Shortage on Manpower where current manpower is 28 and plan to be 39 by 31-Jul-26 , Target Completion Madinah : 05-Sep-26 , Jeddah :06-Oct-26 ,Makkah : 06-Oct-26 ,Abha :03-Sep-26 , Jizan : 16-Sep-26. 2. Abha ADMS System Crash: SLD NDesigner application crashed during implementation activities in Abha, resulting in delays to SLD preparation, submission, and validation activities. 3. Cyber Security Audit : Audit plan not yet Approved by SE and the PO (Third Party) has not been issued by NARI (affecting Cutover). The audit requires approximately 10 weeks after PO issuance. 4. NARI End-to-End Testing Team : A dedicated NARI team is required to focus exclusively on End-to-End testing activities. A total of nine engineers are expected to be mobilized by the 31 July 2026. 5. Delay in Telecom Panel Local Test for Remote End (MADINAH LDC). 6. Delay delivery of DWDM (PO issued to AES) – waiting the final confirmation for the recent traffic plan in Madina, Abha & Jizan. 7. All Submittal under review with FEC / HSSE. 8. Requirements from STC connectivity regarding IP Telephone (SIP) services. 9.1 ICT reviewer’s new comments regarding the passive scope and Beit Al Anzima rejection. 9.2 ICT rejected the material in Rev-02 although no comments were received in Rev-01. 9.3 The material has already been delivered and installed on site. 9.4 The ICT reviewer has been rejecting every submitted versions without providing any specific technical comments or justified reasons, Also rejecting both of the approved Design Consultant and the Contractor. This repeated rejection practice is causing significant delays to the project and directly impacting the implementation and activation of critical ICT services, including Internet connectivity, IP Telephony, and system integrations.
78 | PE-287 | Exp. of YCNT BSP for Power to Neom | Zohaib Iqbal | Western | No | No | No | No |  | 2023-08-01 | 93.38% | 95.08% | 1.7% | NEOM / SEC | Yanbu | N/A | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-01 | 2027-08-01 | 2027-08-01 | 1) 2 Nos GIS breakers damaged due to heavy wind (Fell down, no major damage), need to close the issues with GE Team, Breakers are sent to France Factory to get the repaired materials expected Repaired materials delivery by End of Sep-26. 2) HV Test Equipment delivery pending from GE, due to lack of equipment (Used for other site)
79 | PE-291 | HAMRA AL ASAD 110/13.8 KV SUB | Mohamed Omar | Western | No | No | No | No |  | 2023-07-26 | 100% | 99.98% | -0.02% | SEC | Madinah | Approved | 2024-11-26 | 2025-09-30 | 2026-05-21 | 2025-04-26 | 2026-02-28 | 2026-09-30 | 1) TCC received on 21-May-26. PAC received on 30-Jul-26. (Energization done through the AZIZIA remote-end and TCC was obtained. Remaining interface works at the MICY remote end are ongoing and are expected to be completed by end of Aug 2026.) 2) Target is to energize both remaining feeders with remote end by 1st week of Sep. 2026
80 | PE-292 | Shoran-2 110/13.8 KV - Madinah | Mohamed Omar | Western | No | No | No | No |  | 2023-07-24 | 100% | 99.25% | -0.75% | SEC | Madinah | Under Approval | 2024-11-24 | 2024-11-24 | 2026-08-31 | 2025-04-24 | 2025-04-24 | 2027-01-30 | 1) TCC is requested , still not issued. Readiness of UGC circuits have delayed energization of the substation and TCC issuance. 2) Expected energization by end of Aug. 2026 if the UGC Feeders passed ongoing Tests by Cable contractor.
81 | PE-294 | Airport C (KAIA) Interconnection REINF. | Mudasir Sheikh | Western | No |  |  |  |  | 2023-11-01 | 100% | 83.99% | -16.01% | SEC | Jeddah | N/A | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-06-01 | 2026-06-01 | 2027-01-05 | 1) TCC Received on 09-Aug-26 as per Contractual TCC Date i.e. 01-Feb-26. 2) Remaining work cannot be proceeded due to HV Cable issue from SE. Project currently onhold from SE so manpower to be demobilized accordingly. 3) CSD refused to start T&C Activities because of the unavailability of existing HV cable from SE. 4) Change order (Approx.. 47 million) submitted to SE for additional HV cable work. Waiting for their approval.
82 | PE-295 | Interconnection of AJM-1 (New Jamoom) | Abdelazeem Morsy | Western | No | No | No | No |  | 2024-01-08 | 100% | 90.52% | -9.48% | SEC | Makkah | N/A | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-08-08 | 2026-08-08 | 2026-11-03 | 1) T.C.C received. 2)Shutdown required for Connecting existing GIS to new GIS bay, expected in Aug-26.
83 | PE-301 | Expansion of Mowaih PV 380kV BSP | Ahmed Aboelseoud | Western | No | No | No | No |  | 2024-09-16 | 100% | 98.5% | -1.5% | SEC | Mowaih | Under Approval | 2025-10-16 | 2025-10-16 | 2026-08-30 | 2026-03-16 | 2026-03-16 | 2026-12-29 | 1) EOT-1 submitted on 16th Oct 25, with TCC Date on 27-5-26. Rejected by SEC on 21-Oct-25, Resubmitted, under approval with SE. 2) TCC delayed by SE, Due to SE-MOD time extension approval 2) 48 V DC system: FAT done delivery delayed expected delivery in Sep-26 3) Remote End Substations are not ready
84 | PE-305 | 110kV SS Kar-2 | Bander Khalid Al Qalah | Western | No | Yes | Yes |  |  | 2024-08-28 | 93% | 90% | -3% | Masar | Makkah | Under Approval | 2026-04-27 | 2026-10-28 | 2026-10-28 | 2026-08-27 | 2026-12-27 | 2026-12-27 | 1) Delay in Mechanical materials i.e. HVAC system (PACU), Expected material delivery by Mid Aug-26 due to current Geo-political instability.
85 | PE-307 | 132/13.8KV Sub Industrial City Tabuk | Shafqat Zia | Western | No | No | No | No |  | 2024-01-30 | 98.06% | 98.31% | 0.25% | MODON | Tabuk | N/A | NA | NA | NA | 2027-08-14 | 2027-08-14 | 2027-08-04 | Critical Issues: OLT & CLT Completed and final testing like trip test, end to end test ongoing. However, PAC form signed after mutual site visit from SE, MODON & Alfanar. All pending works to be completed to target energization.
86 | PE-308 | 110KV Salam Royal | Ahmed Faizal | Western | Yes |  |  |  |  | 2026-05-11 | 10.02% | 19.33% | 9.31% | SEC | Jeddah | N/A | 2027-11-10 | 2027-11-10 | 2027-11-10 | 2028-04-11 | 2028-04-11 | 2028-04-11 | 1) Baldia Permit required to avoid any delay in civil activities. Discussion under process. 2) AES to expedite submission of remaining Telecom drawings & also to close SE comments for submitted drawings to avoid any delay in material delivery. 3) AES to expedite to close SE comments for Protection Relay List to avoid any delay in material delivery. Protection Detail Design to be submitted. 4) AES to expedite submission of Switchgear Detail Design.
87 | PE-312 | Const of Southern 380KV BSP ¦ Al Ula | Pervaiz Akbar | Western | No | No | No | No |  | 2024-01-08 | 98.64% | 96.15% | -2.49% | SEC | Al Ula | Under Approval | 2026-01-08 | 2026-06-30 | 2026-06-30 | 2026-06-08 | 2026-11-30 | 2026-11-30 | 1) TCC received. 2) External road: Road marking 3) Testing 85% completed. 4)Finishing work and punch points in progress.
88 | PE-314 | Expansion of Tabuk BSP & Duba BSP | Shafqat Zia | Western | No | No | No | No |  | 2024-01-14 | 92.23% | 91.98% | -0.25% | SEC | Tabuk & Duba | Under Approval | 2026-01-14 | 2026-11-30 | 2026-11-30 | 2026-06-14 | 2027-04-30 | 2027-04-30 | EOT: EOT approved with revised TCC date of 30-Nov-26. 1) Duba BSP: C5 Dia. SEC granted outage on 30-Apr-26. Dismantling of Reactor, dismantling civil foundation removal completed & construction of new foundation under progress & to be completed before 28-Sep-26. Energization as per revised TCC 30-Nov-26. 2) Tabuk BSP C02 Dia: Outage for bus-bar coupling submitted to SE, however SE informed outage will not be received during current season due to peak load. Expected outage will be around Sep’26. Hence, TCC Request submitted to SE for C02 Dia & under review
89 | PE-315 | 110KV Salam Royal Palace | Ahmad Faisal | Western | No | No | No | No |  | 2024-04-04 | 100% | 95.9% | -4.1% | SEC | Jeddah | Under Approval | 2025-10-04 | 2025-10-04 | 2026-01-15 | 2026-03-04 | 2026-03-04 | 2026-08-30 | 1) EOT-1 Submitted on 13th Aug 25, with TCC date on 23rd Jul 26. Under SEC approval 2) Energization actual date 15th Jan 26
90 | PE-319 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 | Khaled Abdelaty Hassan Emara Shehata | Western | No |  |  | yes |  | 2024-06-27 | 97.17% | 94.34% | -2.83% | SEC | Jeddah | N/A | 2026-12-31 | 2026-12-31 | 2027-01-21 | 2027-05-31 | 2027-05-31 | 2027-06-21 | 1) Remote end works. 2) Pole 1 & Pole 2 valve hall equipment installation. 3) Pending materials delivery (CET partial materials and FF Materials).
91 | PE-324 | Stage-2 HVDC OHTL COA-WOA | Ahmed Radwan | Western | No | No |  |  |  | 2024-08-22 | 96.3% | 82% | -14.3% | SEC | Jeddah | N/A | 2026-08-22 | 2026-12-31 | 2027-02-22 | 2027-01-22 | 2027-05-28 | 2027-07-22 | 1) EOT has been submitted to SE on 07-Jul-26 with TCC date 22-Jan-27 under approval with SE. 2) Variation order for increase of Route length is in under approval stage with Rev TCC date 31-Dec-26. 3) Proposed FAT for remaining Combined Towers tentatively by 10-Aug which will affect TCC by 5 Months. 4) Delay in delivery of E & D SPL Tower material (Proposed date by supplier Nov-26). 5) The outage for the diversion scope is expected to occur in October 2026, which is expected to delay the TCC completion to Feb 2027.
92 | PE-329 | SEC ¦ 132KKV OHTL Tabuk | Mohan | Western | No | No | No | No |  | 2024-11-05 | 99.5% | 94.93% | -4.57% | SEC | Tabuk | N/A | 2026-04-05 | 2026-06-05 | 2026-08-02 | 2026-09-05 | 2026-11-05 | 2027-01-31 | 1)TCC Received on 02-Aug-26 2)Acceleration in Mechanical works inside Tunnel Buhaira BSP 3) Acceleration in Access road & Structure Pad final layer
93 | PE-331 | UMM AL-QURA CEMENT OHTL | Sudhakar | Western | No |  |  |  |  | 2024-11-05 | 100% | 74.55% | -25.45% | SEC | Makkah | N/A | 2026-03-05 | 2026-03-05 | 2026-11-26 | 2026-08-05 | 2026-08-05 | 2027-04-30 | 1)Slow Rate in Tower Erection & Stringing Works 2)Change order and EOT approvals to be expedited for new revised milestones.
94 | PE-332 | 110KV OHTL FOR MAADEN-AL MAHAD | Abdelazeem Morsy | Western | Yes |  |  |  |  | 2024-12-22 | 99.83% | 69.36% | -30.47% | SEC | Madinah | N/A | 2026-05-22 | 2026-05-22 | 2026-12-31 | 2026-10-22 | 2026-10-22 | 2027-05-31 | 1) Revised EOT Submitted to SEC on 21-Jun-26 with TCC date 10-Mar-27 under approval with SEC 2) SE notified of Required route deviation due to future plans for a factory, required reworks (Dismantling of erected towers) & additional qty. 3) Foundation concrete works delayed due to late delivery of concrete. 4) Angle Towers erection should expedite to avoid further delay in stringing works 5) Delay in Commencement of Stringing works due to Tower shortage material
95 | PE-338 | Battery Energy (BESS) -Rabigh | Mohamed Elmazawy | Western | No |  |  | yes |  | 2024-12-16 | 100% | 98.67% | -1.33% | SEC | Rabigh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | 2026-10-16 | 2026-10-16 | 2026-11-30 | Energization done
96 | PE-345 | Arafat SS | Mostafa Ayop | Western | No | Yes | Yes |  |  | 2025-03-10 | 87.06% | 70.51% | -16.55% | SEC | Makkah | N/A | 2026-09-10 | 2026-09-10 | 2026-11-10 | 2027-02-10 | 2027-02-10 | 2027-04-12 | 1. EOT submitted on 20-May-26 with TCC upto 8-Oct-26, SE comments received on 4th Jun 26 need to be resubmit the EOT. 2. Shutdown required from SE by Oct-26.
97 | PE-347 | Construction of Tabuk Substation for BESS | Amin El sayed | Western | No | No |  |  |  | 2025-07-03 | 100% | 75.42% | -24.58% | SEC | Tabuk | N/A | 2026-06-03 | 2026-06-03 | 2026-09-08 | 2026-11-03 | 2026-11-03 | 2027-02-09 | 1. Approval Detailed Design for switchgear, ACDB & PDMS 2. Delay in Delivering HGIS from Hitachi for second bay 3. Delay in Delivering for 125v DC System 4. Approval for FEED package 5. Delay in Inputs for Grid Studies from BYD 6. FAT confirmation for Auxiliary Transformer, Lighting Panels, ACDB, DSM, TFR 7. PDC Support required for approval of DSM & TFR. 8. AMI DESIGN APPROVAL 9. FIBER OPTIC ROUTE PLAN. 10. BASE DESIGN APPROVAL FOR TRANSFORMER. 11. DELIOVERY CONFRIATION OF FIRE PUMP MATERIAL
98 | PE-328 | CONSTRUCTION OF ALWESSAM TAIF 110/13.SKV SUBSTATION IN TAIF | Mostafa Elkayal | Western | Yes |  |  |  |  | 2025-07-22 | 55.45% | 26.41% | -29.04% | SEC | Taif | N/A | 2027-01-22 | 2027-01-22 | 2027-06-30 | 2027-06-22 | 2027-06-22 | 2027-10-27 | 1) Delay notification sent to SEC, Due to delay in issuance of construction permit & delay in design (08 Months) 2) Steel binding work & formwork for Main Building wall in progress 3) Structural design approval needs to be expedited
99 | PE-368 | CONSTRUCTION OF A NEW 132/13.8KV SUBSTATION RABIAH TABUK (RBTBK) & ITS 132KV INTERCONNECTION IN TABUK | Shafqat Zia | Western | Yes |  |  |  |  | 2025-09-11 | 35.83% | 31.3% | -4.53% | SEC | Tabuk | N/A | 2027-03-11 | 2027-03-11 | 2027-08-11 | 2027-08-11 | 2027-08-11 | 2028-01-11 | 1) Delay in commencement of OHTL works due to SE E&DD's new requirements and involvement of SE S&SD. 2) Power Transformer delivery requires advancement by at least two months to meet the energization target. The supplier is not agreeing to/confirming the expected FAT and delivery dates before Dec-26. Due to the current global situation, the supplier has indicated that the FAT/delivery may be delayed until Jan./Feb. 2027. 3) Delay in submission and approval of Remote End design and drawings due to delay from SE in providing the existing data. 4) OHTL Line Strings have a long delivery lead time, and SE has been requested to provide the material on a borrowing basis from the SE store, subject to availability. 5) Delay in OHTL Tower works.
100 | PE-369 | CONSTRUCTION OF A NEW 110/13.8 kV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammad Ilyas | Western | Yes |  |  |  |  | 2025-10-07 | 38.26% | 22.91% | -15.35% | SEC | Taif | N/A | 2027-04-07 | 2027-04-07 | 2027-07-05 | 2027-09-07 | 2027-09-07 | 2027-12-05 | 1) Construction Sub Structure forecast completion date: 23-Sep-26. 2) Construction Super Structure forecast completion date: 26-Nov-26.
101 | PE-346 | Installation of New STATCOM ±300MV AR At 132kV Level At Northern BSP | Pervaiz Akbar | Western | Yes | No |  |  |  | 2025-10-29 | 20.02% | 14.51% | -5.51% | SEC | Al Ula | N/A | 2028-07-29 | 2028-07-29 | 2028-05-10 | 2028-12-29 | 2028-12-29 | 2028-10-11 | 1) Vendor finalization is pending for Lightning Protection, HVAC, and Cable Trays; respective design approvals/offers are under process. DPOs for Post Insulator and Crane are with SCD. 2) STATCOM Building foundation works are delayed due to delay in finalization of the STATCOM Building Architectural & Precast drawings (inputs) by the designer (DAR).
102 | PE-359 | CONSTRUCTION OF A NEW 110KV D/C OHTL FOR A NEW 110/13.8KV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammad Ilyas | Western | Yes |  |  |  |  | 2025-10-16 | 67.99% | 24.05% | -43.94% | SEC | Taif | N/A | 2027-03-16 | 2027-03-16 | 2027-07-16 | 2027-08-16 | 2027-08-16 | 2027-10-16 | 1) Delay in GAFM for Insulator. 2) Delay in GAFM for Hardware Fittings. 3) Delay in Soil investigation and Foundation work Design.
103 | PE-365 | CONSTRUCTION OF A NEW SUBSTATION KHR-1 380/110 KV BSP & EXP OF EXISTING MHR BSP UNDER RENEWABLE ENERGY | Ahmed Abdel Hady Sayed | Western | Yes |  |  |  |  | 2025-10-29 | 25.81% | 25.83% | 0.02% | SEC | Taif | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 2027-12-29 | 2027-12-29 | 2027-12-29 | 1) P.O issued for GIS in expansion scope to Hitachi,BD modified after site visit and proposal of reactor location and GIB routing under review 2) Reactors BD with tbea, trench china Bushing under sec review waiting confirmation of delivery date 3) Substructure 110kv building-2 not yet approved. 4) NGR P.O issuance pending due toNGR study
104 | PE-370 | CONSTRUCTION OF A NEW SUBSTATION KHR-2 380/110 KV BSP UNDER RENEWABLE ENERGY POWER PLANT (WOA) | Hossam Amin | Western | Yes |  |  |  |  | 2025-10-29 | 25.85% | 25.5% | -0.35% | SEC | Taif | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 2027-12-29 | 2027-12-29 | 2027-12-29 | 1) Reactors BD with tbea, TEBA as unified desing with SEC, but now changed the BD format it will take one month to modify, it will impact GAFM issues and delivery - TBEA confirmed to deliver equipment within time limit of PO issued. 2) Control Room Building Slab completed
105 | PE-380 | AL JAMOOM 110/33/13.8KV SUBSTATION (Te3830) | Bander Khalid Al Qalah | Western | Yes |  |  |  |  | 2026-01-15 | 2% | 1% | -1% | SEC | Makkah | N/A | 2027-07-15 | 2027-07-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2028-05-16 | 1) SE delayed in site hand over and still site co-ordinate not yet confirmed by SE. It will impact the design submission and site commencing works. 2) Delay in issuing BD for main equipment 3) Delay in engineering Phase
106 | PE-388 | CONSTRUCTION OF HENAKIYAH-3 PV |  | Western | Yes |  |  |  |  | 2026-05-05 | 6.52% | 6.34% | -0.18% | SEC | Madinah | N/A | 2028-05-05 | 2028-05-05 | 2028-05-05 | 2028-10-05 | 2028-10-05 | 2028-10-05 | 1)BL submitted to SE for Approval 2) GLO Approval 3) delay in site office preparations and mobilization
SOUTHERN REGION UNIT (MOHAMMED ALBAZIE)
107 | PE-282 | 2X25 MVAR 33KV STATCOM | Ahmed Hussein | Southern | No | No | No | No |  | 2024-02-01 | 100% | 99.79% | -0.21% | SEC | Al Baha | Under Approval | 2025-10-01 | 2025-10-01 | 2026-01-29 | 2025-03-01 | 2026-03-01 | 2026-07-31 | TCC Certificate Received, working on Punch list & As-Buildt ongoing
108 | PE-283 | Al-Kara 132/33 kV SS in Baha Region | Ahmed Hussein | Southern | No | No | No | No |  | 2023-11-12 | 100% | 96.57% | -3.43% | SEC | Al Baha | Under Approval | 2025-07-12 | 2025-07-12 | 2026-08-31 | 2025-12-12 | 2026-07-27 | 2027-01-28 | Ready for Energization by End of May, awaiting OHTL work to be done by SEC
109 | PE-284 | Qilwah North 132-33kV SS in Tihama | Khawaja Fayyaz | Southern | No | No | No | No |  | 2023-11-12 | 100% | 96.28% | -3.72% | SEC | Al Baha | Under Approval | 2025-07-12 | 2026-03-12 | 2026-03-12 | 2025-12-12 | 2026-08-12 | 2026-10-29 | Delayed in Delivery of GIS,Power Transformer,SIS,SAS, SWGR. Delayed in T&C part where Remote end provision is yet to provided by Client, T&C almost done waiting for some items which require Shutdown by SE TCC received in on 14-July with certificate date 12-March-2026
110 | PE-298 | 132KV JCDPI- Jazan SS ¦ RC | Nadim Shaikh | Southern | No | No | No | No |  | 2024-05-21 | 99.72% | 97.85% | -1.87% | SEC | Jizan | Approved | 2026-02-10 | 2026-09-17 | 2026-11-19 | 2026-05-20 | 2026-12-17 | 2027-03-04 | Working now on T&C and expected to be finished by Sep-26
111 | PE-297 | Battery Energy Storage for BISHA | Ahmad Abdel Hady | Southern | No | No | No | No |  | 2024-02-05 | 100% | 99.96% | -0.04% | SEC | Al Baha | N/A | 2025-01-05 | 2025-01-05 | 2025-02-10 | 2025-06-05 | 2025-06-05 | 2026-10-15 | SEC Reject descoping spare part scope
112 | PE-311 | New Samtah-PV 380/132kV BSP & OHTL | Amr Sennara | Southern | No | No | No |  |  | 2024-10-02 | 99.83% | 88.07% | -11.76% | SEC | Jizan | N/A | 2026-05-02 | 2026-05-02 | 2026-10-28 | 2026-10-02 | 2026-10-02 | 2027-03-27 | Delay OHTL Road Crossing special towers approval ,Delay in lapp insulator FAT , Delay in SP tower procurement
113 | PE-313 | New Dhahyah 380/132/13.8KV BSP | Ahmed Sadek | Southern | No |  |  | yes |  | 2024-04-25 | 86.78% | 89.42% | 2.64% | SEC | Jizan | Under Approval | 2026-01-25 | 2026-12-24 | 2026-10-30 | 2026-06-25 | 2027-05-25 | 2027-03-30 | Delay in delivery of main materials 132KV GIS, 132 Power transformers and CTs (all delivered on May-26), working on internal crashed plan to energize by end of Oct-2026
114 | PE-320 | Aqabah (PS-AQB) 380/132/13.8KV | ON HOLD | Southern | Yes | ON HOLD |  |  |  | 2025-03-06 | On Hold | 0% | #VALUE! | SEC | Abha | N/A | Contract Not Signed (2Y From Signing Contract) | 0 | 0 | 0 | 0 | 0 | -
115 | PE-325 | Construction of New SS for Darb-PV | Musab Ismail | Southern | yes | yes | No |  |  | 2024-10-02 | 99.97% | 85.3% | -14.67% | SEC | Abha | N/A | 2026-05-02 | 2026-05-02 | 2026-12-30 | 2026-10-02 | 2026-10-02 | 2027-05-14 | Delay in OHTL change order , Delay in Civil design , Delay in AES material delivery , Delay in construction work. after new plan for OHTL Expected TCC Date is 15-Dec-26
116 | PE-327 | 132KV OHTL & UGC Najran | Ayman Elattar | Southern | No |  |  |  |  | 2024-10-24 | 99.99% | 75.07% | -24.92% | SEC | Najran | Under Approval | 2026-03-24 | 2026-03-24 | 2026-12-29 | 2026-10-02 | 2026-08-24 | 2027-05-31 | 1. Incomplete delivery of Angle towers from SE Energya will hinder the commencement stringing works in Portion -3 (<30km) 2. Transposition tower technical submittals, design engineering, needs to be expidted for submission as PO created on 17-May-2026, impacts material testing & delivery delay 3.UG Cable Construction needs to be start as it delayed. 4. Balance 20% material follow up with SE is required to prevent the project from delay.
117 | PE-343 | Const. Albaha ¦ Add. Scope UG Cable | Hany Kamal Elsherbini | Southern | No | No | No | No |  | 2024-10-17 | 100% | 96.3% | -3.7% | SEC | Al Baha | Approved | 2024-07-24 | 2026-02-17 | 2025-07-24 | 2024-11-24 | 2026-06-17 | 2026-08-24 | Delay in removal of existing utilities & blasting works for the remaining works
118 | PE-333 | NEW DHAHRAN ALJANOUB-2 SS | Mohammad Monawwar Eqbal | Southern | No |  |  |  |  | 2025-01-15 | 99.25% | 70.94% | -28.31% | SEC | Dhahran | N/A | 2026-07-15 | 2026-07-15 | 2026-12-16 | 2026-12-15 | 2026-12-15 | 2027-05-16 | OHTL portion delayed due to change order and shutdown Huge Delay in Delivery of Power Transformer, SAS & Gantry
119 | PE-341 | EXP. THE EXISTING KHM, ABHE & BISHA | Shawkat Alrjoub | Southern | Yes | No | No |  |  | 2025-01-26 | 71% | 42% | -29% | SEC | Abha | N/A | 2026-12-26 | 2026-12-26 | 2027-05-01 | 2027-05-26 | 2027-05-26 | 2027-10-01 | For Civil works : -Delay in Gatepasses issuance, working 5 days a week for risky civil activities. -Low Manpower deployment from FGC (Civil Subcontractor) side -GIS Building opennings design delay approval for bisha which delays GIS Modification works For Electrical Installation : -Delay delivery schedule from Hitachi for : (Reactors in Abha -Delayed FAT for GIS in bisha as it was planned on 4-Jun-26) -Delay fdelivery schedule from trench for (NGR - FS CT) -Delay delivery schedule from GE for HGIS (30-Sep-26) in Khamis and delay in FAT for LCC as it was planned to be on 19-May-268 (most critical)
120 | PE-340 | JIZAN OHTL ¦ 132 KV LINE | Amir Aboumansour | Southern | Yes | No |  |  |  | 2025-03-27 | 89.92% | 40.67% | -49.25% | SEC | Jizan | N/A | 2026-09-26 | 2026-09-26 | 2027-04-08 | 2027-02-26 | 2027-02-26 | 2027-09-08 | 1.Delay in FAT conduction for GIS with variance 5 months than planned FAT date. 2.Delay in submission & approval of foundation design which is affecting start of foundation works. 3.Delay in submission & approval of full plan & profile. 4.Delay in access road & structure pad progress.
121 | PE-342 | Refurbishment of 132kV Najran East Substation in SOA & Refurbishment of 132/33 kV Salwah Substation in SOA. | Akram Kamal | Southern | Yes | Yes |  |  |  | 2025-04-17 | 86.27% | 31.48% | -54.79% | SEC | Najran | N/A | 2026-10-17 | 2026-10-17 | 2027-06-21 | 2027-03-17 | 2027-03-17 | 2027-11-14 | 1- Delay of start manufacturing of Protection 2- PO of Batteries & Battery Chargers issued with long Manufacturing Duration (35 weeks) 3- Delay in shifting live MV cables to start construction activities 4- Delay in site handing over
122 | PE-330 | Construction of OTOUD (Khamis South-2) 132/13.8KV SS & Interconnections in Asir Region SOA | Ahmed Hussein | Southern | Yes |  |  |  |  | 2025-06-29 | 56.27% | 29.18% | -27.09% | SEC | KHM | N/A | 2026-12-29 | 2026-12-29 | 2027-10-16 | 2027-05-29 | 2027-05-29 | 2028-03-01 | *Long Manufacturing Duration of Power Transformers (SPTC) due to Non-Unified Design *Delay in All UGC Scope due to Municipality Permit Rejection for Single Circuit and Design Submittal for Double Circuit *Civil Readiness Delay due to Delayed Municipality Permits and Improper Store Location at Site
123 | PE-278 | Construction 132kv OHTL between baish west and ss1a at Jazan economic city in Jazan region-SOA | Adil Bashir | Southern | Yes | Yes |  |  |  | 2025-08-14 | 75.54% | 50.58% | -24.96% | SEC | Jizan | N/A | 2027-02-13 | 2027-02-13 | 2027-01-14 | 2027-07-13 | 2027-07-13 | 2027-06-13 | 1.Delay in access road & structure pads works. 2. Delay in GAFM for Gantry Structure material 3.Delay in GAFM for Protection 4. Delay in delivery of Tower structure Material 5. Dealy in PO issuance for Earthing & Bonding cables
124 | PE-222 | PE-222: Najran DRPC | Hany Kamal | Southern | No | No | No | No |  | 2021-01-04 | 100% | 100% | 0% | SEC | Najran | N/A | 2023-03-03 | 2023-03-03 | 2024-09-30 | 2023-07-03 | 2023-07-03 | 2025-01-30 | -
125 | PE-230 | PE-230: Wadi Eldawasser | Hany Kamal | Southern | No | No | No | No |  | 2021-07-15 | 100% | 100% | 0% | SEC | Wadi Eldawasser | N/A | 2023-01-15 | 2023-01-15 | 2024-06-20 | 2023-03-15 | 2023-03-15 | 2025-03-31 | -
126 | PE-237 | PE-237: Al BAHA | Hany Kamal | Southern | No | No | No | No |  | 2022-01-25 | 100% | 99.55% | -0.45% | SEC | ALBAHA | N/A | 2024-07-24 | 2024-07-24 | 2025-09-09 | 2024-11-24 | 2024-11-24 | 2026-06-17 | -
127 | PE-234 | PE-234: Najran-2 | Ahmed Abdelhady | Southern | No | No | No | No |  | 2022-01-18 | 100% | 98.36% | -1.64% | SEC | Najran | Approved | 2023-07-17 | 2026-11-17 | 2025-12-30 | 2024-01-17 | 2027-05-17 | 2026-08-30 | shutdown received and work ongoing for the works during shutdown
128 | PE-236 | PE-236: New Sharorah | Ahmed Abdelhady | Southern | No | No | No | No |  | 2022-01-18 | 100% | 99.9% | -0.1% | SEC | Sharorah | N/A | 2023-07-17 | 2023-07-17 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2025-12-30 | -
129 | PE-318 | HVDC-3 ¦ COA-SOA ¦ KUDMI | Mohamed Sabri | Southern | Yes |  |  | yes |  | 2024-06-27 | 56.24% | 56.26% | 0.02% | SEC | jazan | N/A | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-05-31 | 2027-05-31 | 2027-05-31 | -
130 | PE-321 | 380kV OHTL Between 1A BSP & Kudmi BSP (Approx. 47Km)¦ JCPDI P-4007 1A | Adil Bashir | Southern | Yes |  |  |  |  | 2025-10-27 | 69.88% | 29.35% | -40.53% | RC | Jizan | N/A | 2028-08-24 | 2028-08-24 | 2027-04-28 | 2028-10-26 | 2028-10-26 | 2028-10-26 | - Plan & Profile submission & Approval delayed. - Foundation design drawing submission delayed due to Geo-tech soil investigation on going. - Access road and structure PAD works on hold due to trees cutting/NCEC permit. - Delay in Delivery of Insulator by Mar-27
131 | PE-322 | Design and construction of a buried cable to feed the industrial area | Nadim Shaikh | Southern | Yes |  |  |  |  | 2025-11-27 | 32.06% | 18.97% | -13.09% | RC | Jizan | N/A | 2027-08-18 | 2027-08-18 | 2027-04-25 | 2027-03-15 | 2027-03-31 | 2028-08-01 | .Key Rout plan approval finilaiz & need to expdite reamining material POs & Power cable Manfufacturing
132 | PE-323 | Design & Construction of Electricity Substation 5E - Residential Area 132KV GIS + UGC | L1 | Southern | Yes |  |  |  |  | L1 | 0% | 0% | 0% | - | - | N/A | 0 | 0 | 0 | 0 | 0 | 0 | -
133 | PE-358 | Power supply to Saad water facility Project (new 132 kV substation project) | L1 | Southern | Yes |  |  |  |  | L1 | 0% | 0% | 0% | - | - | N/A | 0 | 0 | 0 | 0 | 0 | 0 | -
134 | PE-364 | PE364 - 380KV OHTL HDN-2 & BAHA BSP | Mohamed Eltohfa | Southern | Yes | yes | yes |  |  | 2025-10-15 | 62.35% | 47.59% | -14.76% | SEC | TAIF - BAHA | N/A | 2027-04-15 | 2027-04-15 | 2027-08-15 | 2027-09-15 | 2027-09-15 | 2028-01-15 | - Contract Amendment of Rerouting Received 19-Aug that will require Change Order & Impact on time and cost. - On-Hold shipping for the Insulators & Hardware due to the additional shipping cost imposed by the vendor is impacting stringing start by Oct-26. - Manpower shortage for Assembly / Erection works impacting the site productivity. - Delayed finalization of Stringing Subcontractor, impacting the readiness for stringing activities by Oct-26 - Delayed concreting readiness in the western area due to the availability of a batching plant (First, under relocation / Second, PO under finalization)
135 | PE-374 | 132KV Ad Dayir SS | Moazam Ali Sayed | Southern | Yes |  |  |  |  | 2026-01-08 | 27% | 14% | -13% | SEC | Jizan | N/A | 2027-07-08 | 2027-07-08 | 2027-09-01 | 2027-12-08 | 2027-12-08 | 2028-02-01 | -Delay in mobilization and site works as site handover given on 12-Feb-26 -Delay in RFM for protection,SST, HV Cables, and MV Cables due to delay in design submission from AES for SST & Protection -Delay in power source identification for auxiliary transformers which delay relocation of existing transformers and delays excavation works for the main building -Delay in precast supplier confirmation as for using precast slap or cast in situ, due to hard access to the site as it is on a mountainous area which will hinder supplying of precast slap. late confirmation impacts civil design and civil works. -Delay in manpower supplier prequalification approval for civil works -GIS GAFM released 1.5 months later than planned and no manufacturing schedule received yet from siemens
136 | PE-375 | 132KV Ayban SS | Khawaja Fayyaz | Southern | Yes |  |  |  |  | 2025-12-09 | 40.22% | 19.8% | -20.42% | SEC | Jizan | N/A | 2027-06-09 | 2027-06-09 | 2027-08-09 | 2027-11-09 | 2027-11-09 | 2028-01-09 | Presence of existing feeders, dead Gantry structures and cables causing delay in start of excavation
137 | PE-376 | 132KV Al-Haqu SS | L1 | Southern | Yes |  |  |  |  | L1 | 0% | 0% | 0% | - | - | N/A | 0 | 0 | 0 | 0 | 0 | 0 | -
138 | PE-382 | REFURBISHMENT OF 132 KV ASIR CPS SUBSTATION IN SOUTHERN OPERATING AREA | N/A | Southern | Yes |  |  |  |  | L1 | 0% | 0% | 0% | SEC | - | N/A | 0 | 0 | 0 | 0 | 0 | 0 | -
139 | PE-383 | CONVERT SAMAKH SUBSTATION TO A CONVENTIONAL SUBSTATION IN BISHA REGION-SOA | N/A | Southern | Yes |  |  |  |  | L1 | 0% | 0% | 0% | SEC | - | N/A | 0 | 0 | 0 | 0 | 0 | 0 | -
140 | PE-390 | CONST. NEW AD‑DARB S/S 132/33KV | N/A | Southern | Yes |  |  |  |  | 2026-04-12 | 7.73% | 7.37% | -0.36% | SEC | Jizan | N/A | 2028-04-12 | 2028-04-12 | 2028-04-12 | 2028-09-12 | 2028-09-12 | 2028-09-12 | -
141 | PE-400 | 132KV OHTL BETWEEN SAMITAH PV AND MOKTARA SUBSTATION IN JAZAN– SOA | N/A | Southern | Yes |  |  |  |  | 2026-05-13 | 11.37% | 5.18% | -6.19% | SEC | Jizan | N/A | 2027-11-13 | 2027-11-13 | 2027-11-13 | 2028-04-13 | 2028-04-13 | 2028-04-13 | -
INFRA UNIT (ALAA SAAD)
137 | PE-244 | Steel Factory - DOOSAN | Ahmed Shebl | Eastern | No | No | No | No |  | 2022-04-28 | 99.97% | 96.52% | -3.45% | Doosan | Ras Al Khair | N/A | 2025-01-16 | 2025-01-16 | 2025-04-30 | 2025-01-16 | 2025-01-16 | 2025-04-30 | -
138 | PE-249 | NEOM Village NRC-11 | Kamran Ali | Western | No | No | No | No |  | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-19 | -
139 | PE-250 | NEOM Village NRC-13 | Mohammd Elshafie | Western | No | No | No | No |  | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-19 | -
140 | PE-251 | NEOM Village NRC-17 | Abdelhadi Abdulhalim Kassem | Western | No | No | No | No |  | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-15 | -
141 | PE-252 | NEOM Village NRC-19 | Fahed Al Malki | Western | No | No | No | No |  |  | 100% | 99.99% | -0.01% | AGD | NEOM | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | 2024-07-21 | 2024-07-21 | 2024-12-15 | -
142 | PE-253 | NEOM Village NRC-26 | Mohamed Shokry | Western | No | No | No | No |  | 2022-11-20 | 100% | 99.99% | -0.01% | AGD | NEOM | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | 2024-09-04 | 2024-09-04 | 2025-01-15 | -
143 | PE-268 | SEVEN JIZAN Project | Khalid Khalil | Southern | Yes |  |  | yes |  | 2023-05-28 | 100% | 60.28% | -39.72% | SEVEN | Jizan | N/A | 2025-05-27 | 2025-05-27 | 2026-09-29 | 2025-05-27 | 2025-05-27 | 2026-09-29 | -
144 | PE-269 | NEOM Community 1 expansion | Mohammed Khurbush | Western | No | No | No | No |  | 2023-06-01 | 100% | 100% | 0% | NEOM | NEOM | N/A | 2024-04-04 | 2024-06-24 | 2025-05-15 | 2024-04-04 | 2024-06-24 | 2025-05-15 | -
145 | PE-289 | SWRO Des. Plant ¦ Shoaibha PP | Fathi Mousa | Western | No | yes | yes | yes |  | 2024-12-16 | 100% | 82.84% | -17.16% | SEC | Shoaibha | Under Approval | 2026-05-16 | 2026-08-30 | 2026-09-30 | 2027-06-16 | 2027-09-30 | 2027-10-30 | * Conditions Approval received TCC 30-Aug-26 *Neutralization Pit : SE to review and approve the required Variation Order * PO for Existing MV switchgear CT : Expedite the delivery of the CT *Outdoor Works Permit : approve 24h working outside the fence. Pipe and cable routing activities are delayed *Tank No. 3 Outage Required: Delay on tie-in works
146 | PE-349 | SABGS - Phase IV Schools-Central | Ahmed Shebl | Eastern | Yes | Yes | Yes |  |  | 2025-02-09 | 32.4% | 21.49% | -10.91% | Aramco | Dammam | Under Approval | 2027-09-27 | 2027-09-27 | 2029-02-15 | 2027-10-27 | 2027-10-27 | 2029-03-16 | -
147 | PE-350 | SABGS - Phase IV Schools-Southern | Ahmed Shebl | Eastern | Yes | Yes | Yes |  |  | 2025-02-09 | 32.04% | 19.14% | -12.9% | Aramco | Hofuf | N/A | 2027-09-27 | 2027-09-27 | 2028-01-29 | 2027-10-27 | 2027-10-27 | 2028-03-05 | -
148 | PE-293 | SWRO Des. Plant- Shuqaiq Power Plant | Fathi Mousa | Southern | Yes | No |  |  |  | 2025-04-28 | 80.45% | 60.06% | -20.39% | SEC | Shuqaiq | N/A | 2026-10-26 | 2026-10-26 | 2026-12-15 | 2026-11-26 | 2027-11-26 | 2028-01-15 | *Outdoor Works Permit : approve 24h working outside the fence *Conflict Regarding Chemical Bulk Storage Tanks: There exists a direct and material conflict between the two documents: Schedule B (Cl. 5.1.10) – Contractor to utilise existing bulk tanks; no new tanks required. Post-Bid Clarification (Point 2) – Contractor to supply new NaOH and H₂SO₄ bulk storage tanks with all associated equipment. * AES arabia Material Delivery: AES to officially confirm and expedite delivery dates no later than 20-Aug-26.
149 | PE-303 | Water Treatment Plant & Tank - Jeddah | Fathi Mousa | Western | No | Yes |  |  |  | 2025-03-19 | 100% | 70.55% | -29.45% | SEC | Jeddah | N/A | 2026-05-20 | 2026-05-20 | 2026-10-30 | 2027-06-20 | 2027-06-20 | 2027-11-30 | *Revised Schedule Submitted with TCC 30-Oct-26, Under SEC approval *Pipe and cable routing activities are currently slow due to pending outdoor work permits: SE to expedite the issuance of all required permits for outdoor works & Allow working 24h for outdoor works * NAOH Pipeline Hold: Finalize the pending technical decision to release the activity.
150 | PE-352 | Main Construction Work for Al Ahsa Entertainment Complex | Fahed Al Malki | Eastern | Yes |  |  | yes |  | 2025-05-01 | 11.44% | 11.89% | 0.45% | SEVEN | Alahsa | N/A | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | -
MEP UNIT (MAZEN MOSTAFA)
151 | EL-059 | Rehab & Development of Ohud Hospital | Ghaleb | Western | No | No | No | No |  | 2021-10-19 | 100% | 97.44% | -2.56% | MOH | Madinah | N/A | 2024-04-18 | 2025-10-18 | 2026-08-31 | 2024-04-18 | 2025-10-18 | 2026-08-31 | -
152 | EL-060 | CONST OF COLLEGE -Faculty of Science – Univ of Tabuk. | AbdelHafez Mousa | Western | No | No | No | No |  | 2022-07-18 | 100% | 94.09% | -5.91% | University of Tabuk | Tabuk - KSA. | Under Approval | 2024-01-09 | 2026-05-26 | 2026-08-15 | 2024-01-09 | 2026-05-26 | 2026-08-15 | -
153 | EL-062 | Four Season Resort, Triple Bay, Amaala | Raja Naveed | Western | No | No | No | No |  | 2023-08-31 | 100% | 98.71% | -1.29% | AMAALA | Al Wajh | Approved | 2024-12-17 | 2025-08-30 | 2026-08-30 | 2024-12-17 | 2025-08-30 | 2026-08-30 | -
154 | EL-063 | NEOM MEP ¦ NRC-11 | Hashem Mohamed | Western | No | No | No | No |  | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
155 | EL-064 | NEOM MEP ¦ NRC-13 | Hashem Mohamed | Western | No | No | No | No |  | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
156 | EL-065 | NEOM MEP ¦ NRC-17 | Hashem Mohamed | Western | No | No | No | No |  | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
157 | EL-066 | NEOM MEP ¦ NRC-19 | Hashem Mohamed | Western | No | No | No | No |  | 2022-11-20 | 100% | 99.99% | -0.01% | Alfanar EC | NEOM | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | 2024-07-21 | 2024-07-21 | 2025-12-31 | -
158 | EL-067 | NEOM MEP ¦ NRC-26 | Hashem Mohamed | Western | No | No | No | No |  | 2022-11-20 | 100% | 99.99% | -0.01% | Alfanar EC | NEOM | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | 2024-09-04 | 2024-09-04 | 2025-12-31 | -
159 | EL-068 | MEP Works for AMAALA YACHT CLUB | Hashem Mohamed | Western | No | No | No | No |  | 2024-09-14 | 100% | 99.9% | -0.1% | AMAALA | Al Wajh | N/A | 2025-02-27 | 2025-10-30 | 2026-07-31 | 2025-02-27 | 2025-10-30 | 2026-07-31 | -
160 | EL-069 | NEOM - BMS FOR 5 VILLAGES | Hashem Mohamed | Western | No | No | No | No |  | 2024-12-15 | 100% | 100% | 0% | ALFANAR - AGD | NEOM | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
161 | EL-070 | ALFANAR HEALTH CARE - BIM SERVICE | Hashem Mohamed | Western | No | No | No | No |  | 2024-12-05 | 100% | 100% | 0% | Alfanar Health Care | Amaala | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
162 | EL-071 | NEOM Expansion - (PE-269 Project) | Hashem Mohamed | Western | No | No | No | No |  | 2025-04-14 | 100% | 100% | 0% | Alfanar EC | NEOM | N/A | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | -
163 | EL-072 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 - MEP WORKS | Hashem Mohamed | Central | No |  |  |  |  | 2025-05-15 | 96.02% | 74.75% | -21.27% | Alfanar EC | Dhurma | N/A | 2026-04-23 | 2026-04-23 | 2026-09-14 | 2026-04-23 | 2026-04-23 | 2026-09-14 | -
164 | EL-073 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 - MEP WORKS | Hashem Mohamed | Central | Yes |  |  |  |  | 2025-05-15 | 95.29% | 67.57% | -27.72% | Alfanar EC | Kharj | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
165 | EL-074 | HVDC-3 ¦ COA-SOA ¦ KUDMI - MEP WORKS | Hashem Mohamed | Southern | No |  |  |  |  | 2025-05-15 | 100% | 73.83% | -26.17% | Alfanar EC | Kudmi | N/A | 2026-10-29 | 2026-10-29 | 2026-11-22 | 2026-10-29 | 2026-10-29 | 2026-11-22 | -
166 | EL-075 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 - MEP WORKS | Hashem Mohamed | Western | No |  |  |  |  | 2025-05-15 | 100% | 76.64% | -23.36% | Alfanar EC | Jeddah | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
167 | EL-076 | MEP WORKS FOR SEVEN - AL AHSA (Same as PE-352) | Hashem Mohamed | Eastern | Yes |  |  |  |  | 2025-05-01 | 32.8% | 28.7% | -4.1% | SEVEN | Alahsa | N/A | 2027-10-28 | 2027-10-28 | 2028-04-04 | 2027-10-28 | 2027-10-28 | 2028-04-04 | -
168 | EL-077 | MEP WORKS Amaala Wellness | Hashem Mohamed | Western | No | No | No | No |  | 2025-08-06 | 94% | 92% | -2% | AMAALA | Al Wajh | N/A | 2025-12-31 | 2026-02-11 | 2026-08-31 | 2025-12-31 | 2026-02-11 | 2026-08-31 | -
Formulas:
Start Date = VLOOKUP([Project Code],'Detailed Update'!B:D,3,FALSE)
TCC = VLOOKUP([Project Code],'Detailed Update'!B:T,11,FALSE)
Revised Date = VLOOKUP([Project Code],'Detailed Update'!B:T,12,FALSE)
Revised Date = VLOOKUP([Project Code],'Detailed Update'!B:S,18,FALSE)
Forecast Date = VLOOKUP([Project Code],'Detailed Update'!B:T,13,FALSE)
FAC = VLOOKUP([Project Code],'Detailed Update'!B:T,17,FALSE)

## Detailed Update
| Project Code | Project Name | Start Date | Planned % | Actual % | Client | Region | City | Latest EOT approved Date | EOT STATUS (Submitted/Approved/Under Approval/ N/A) |  | TCC |  |  | PAC |  | FAC / Overall Project |  |  | Remarks
|  |  | Start Date | [7 empty] | TCC | Revised Date | Forecast Date | Contract Date | Revised Date | Forecast Date | Contract Date | Revised Date | Forecast Date
CENTRAL REGION UNIT
1 | PE-215 | SMP - O&M 3 Yrs | 2022-04-01 | 100% | 100% | SEC | Central | Riyadh |  | Approved | 2024-05-30 | 2025-06-04 | 2025-06-04 | 2024-05-30 | 2025-06-04 | 2025-06-04 | 2024-05-30 | 2025-06-04 | 2025-06-04 | All certification Received
2 | PE-226 | KHASM-AL-AAN BSP | 2021-06-03 | 100% | 86.3% | SEC | Central | Riyadh | 2024-04-04 | Approved | 2023-02-03 | 2024-12-31 | 2027-01-24 | 2023-05-03 | 2025-02-28 | 2027-03-25 | 2023-08-03 | 2025-05-31 | 2027-06-25 | Partial TCC Received ¦ Project on Hold
3 | PM-223 | GASCO - 2 | 2021-06-21 | 100% | 99.91% | GASCO | Central | Riyadh |  | Approved | 2023-07-29 | 2025-03-31 | 2025-10-31 | 2023-07-29 | 2025-03-31 | 2025-10-31 | 2023-07-29 | 2025-03-31 | 2025-10-31 | Initial Handing over received
4 | PE-228 | SVC QASSIM -2 | 2021-09-05 | 100% | 99.28% | SEC | Central | Riyadh |  | Approved | 2023-11-05 | 2025-03-17 | 2025-03-17 | 2024-01-05 | 2025-05-17 | 2026-06-30 | 2024-03-05 | 2025-07-17 | 2026-08-30 | TCC Received.
5 | PE-233 | Tabarjal 380KV BSP Expn. | 2021-12-12 | 100% | 99% | SEC | Central | Riyadh |  | Approved | 2023-12-12 | 2025-12-30 | 2026-07-30 | 2024-02-12 | 2026-02-28 | 2026-09-30 | 2024-05-12 | 2026-05-30 | 2026-12-30 | Partial TCC received on 16-Jan-24
6 | PE-245 | Hail OHTL | 2022-08-15 | 100% | 96.12% | SEC | Central | Riyadh | 2024-07-03 | Approved | 2024-05-15 | 2024-12-30 | 2026-06-20 | 2024-07-15 | 2025-02-28 | 2026-08-19 | 2024-10-15 | 2025-05-27 | 2026-11-15 | One line Energizaed. Another line by 20-Jun-26. Change Order approval is critical
7 | PE-247 | RIYADH SEDRA-2 | 2022-09-29 | 100% | 99.1% | Roshn | Central | Riyadh |  | Under Approval | 2024-09-03 | 2024-09-03 | 2025-09-20 | 2024-10-03 | 2024-10-03 | 2026-07-30 | 2024-11-03 | 2024-11-03 | 2026-08-30 | Partial TCC received & 90% invoice approved
8 | PE-248 | PP10 Conv. | 2022-10-13 | 100% | 95.76% | SEC | Central | Riyadh | 2024-09-18 | Approved | 2024-08-13 | 2025-12-27 | 2026-08-29 | 2024-11-13 | 2026-03-31 | 2026-11-29 | 2025-11-13 | 2027-03-31 | 2027-11-29 | TCC milestone achieved. Certification not receied. Punchlist Clearance is critical
9 | PE-255 | 380kv D/C OHTL LILO SAAD OHTL | 2022-10-23 | 89.98% | 75.18% | SEC | Central | Riyadh | 2024-06-06 | Approved | 2023-12-23 | 2025-06-05 | 2026-12-30 | 2024-03-23 | 2025-09-05 | 2027-04-01 | 2024-06-23 | 2025-12-05 | 2027-07-01 | 1. Amendment for New circuit Arrangement at Tapping Point . 2. Outage requirements 3. Hardware fittings material for re-route portion
10 | PE-256 | Sudair PV 380KV BSP | 2022-11-02 | 100% | 78.77% | SEC | Central | Riyadh |  | Under Approval | 2024-09-02 | 2024-09-02 | 2026-10-30 | 2024-11-02 | 2024-11-02 | 2026-12-30 | 2025-02-02 | 2025-02-02 | 2027-04-01 | SS portion energized. Delay in Receiving Permit UGC works and inside PP9 works (MTO,LOA& ARAMCO Permits)
11 | PE-259 | WAAD AL SHAMAAL 380KV BSP | 2022-11-06 | 100% | 96.93% | SEC | Central | Riyadh |  | Approved | 2024-11-15 | 2025-05-30 | 2026-11-30 | 2025-01-15 | 2025-07-30 | 2027-01-30 | 2025-04-15 | 2025-10-30 | 2027-05-02 | Paritally Energized on 09-Feb-26 ¦ Delay in receiving outage to enrgize CKT 2 Wind to Waad Alshamaal & Wind to TABARJAL energization (expected by Oct 26)
12 | PE-264 | TABARJAL-B 13213.8 KV S/S IN JOUF | 2023-05-17 | 100% | 99.18% | SEC | Central | Riyadh |  | Approved | 2025-03-16 | 2025-06-30 | 2026-06-29 | 2025-05-16 | 2025-08-30 | 2026-08-29 | 2025-08-16 | 2025-11-30 | 2026-11-29 | 1.Total of four circuits are planned; two are scheduled for energization by June 2026. 2.SE confirmation is still pending for the remaining two circuits.
13 | PE-271 | AL-DAR AL-BAIDHA 132/13.8KV SUB | 2023-07-13 | 100% | 98.5% | SEC | Central | Riyadh | 2026-01-17 | Approved | 2024-11-12 | 2026-02-28 | 2026-03-17 | 2025-01-12 | 2026-04-28 | 2026-10-30 | 2025-04-12 | 2026-07-28 | 2027-01-29 | Energized on 17-Mar-26 ¦ Other Circuit depends on Outage ¦ Expected - 31-Oct-26
14 | PE-272 | AL-MUNSIYAH 132/13.8KV SUB # 8273 | 2023-07-13 | 100% | 96.13% | SEC | Central | Riyadh |  | Under Approval | 2024-11-13 | 2024-11-13 | 2026-09-07 | 2025-01-13 | 2025-01-13 | 2026-11-07 | 2025-04-13 | 2025-04-13 | 2027-02-05 | One Circuit Energized. Other Circuit depends on Outage ¦ Expected - 31-Oct-26
15 | PE-273 | ALMANFOHA 132/13.8KV SUB # 8138 | 2023-07-12 | 100% | 98.6% | SEC | Central | Riyadh |  | Approved | 2024-11-12 | 2025-11-30 | 2025-11-30 | 2025-01-12 | 2026-01-30 | 2026-10-30 | 2025-04-12 | 2026-04-30 | 2027-01-28 | One Circuit Energized on 21-Dec-25
16 | PE-274 | NASIRIYAH 132/13.8KV SUB # 8154 | 2023-07-12 | 100% | 92.7% | SEC | Central | Riyadh |  | Approved | 2024-11-12 | 2026-01-12 | 2025-12-31 | 2025-01-12 | 2026-03-12 | 2026-06-30 | 2025-04-12 | 2026-06-12 | 2026-09-30 | One Energized on 11-Feb-26. TCC received with dated 31-Dec-2025
17 | PE-275 | 380kV Diriyah Gate-2 BSP # 9080 | 2023-11-16 | 50.84% | 45.12% | SEC | Central | Riyadh |  | Under Approval | 2025-11-16 | 2027-04-13 | 2027-06-09 | 2026-01-16 | 2027-06-12 | 2027-08-08 | 2026-04-16 | 2027-09-11 | 2027-11-07 | Progress based on Internal Baseline. 1-Delay in approval of water proofing VO & removal of loose material, which affects the construction works. 2- Negative Cash flow. 3-Claim Approval 201 Mn for prolongation & inflation costs. 4- Delivery for disconnector switch expected to be delayed.
18 | PE-276 | SHARAFIYAH 380 KV SS | 2023-08-01 | 100% | 93.78% | SEC | Central | Riyadh |  | Under Approval | 2025-02-01 | 2025-02-01 | 2026-06-10 | 2025-04-01 | 2025-04-01 | 2026-08-08 | 2025-07-01 | 2025-07-01 | 2026-11-07 | Partially Energized. 1.Taihan - Oil Joints 2.Design Approval - 6 Remote end ( 132 kV) 3.Gantry Foundation for Existing Substation 4.Unclear Shutdown schedule for Power and Communication link with all remote ends 5. Delay in Micro Trenching of FOC 25km
19 | PE-279 | AL-NAZEEM 132/13.8KV SS # 8271 | 2023-07-24 | 100% | 90.85% | SEC | Central | Riyadh |  | Approved | 2024-11-23 | 2025-06-23 | 2026-12-31 | 2025-01-23 | 2025-08-23 | 2027-03-02 | 2025-04-23 | 2025-11-23 | 2027-06-02 | Commissioing on Hold due to non-readiness of UG Contractor
20 | PE-299 | Reinf of 132KV Network of Baqaa | 2023-11-08 | 99.92% | 93.58% | SEC | Central | Riyadh | 2025-10-01 | Approved | 2025-05-07 | 2025-11-20 | 2026-10-31 | 2025-08-07 | 2026-02-20 | 2027-01-31 | 2025-10-07 | 2026-04-20 | 2027-03-31 | 1.OHTL S/C & D/C crossing - Delay in HOT permits 2.Cutting point outage at TEE OFF location. 3.ERS System & TEE- OFF Tower Installation 4.Design Approval of Flood Protection
21 | PE-300 | 300 MVAR STATCOM | 2024-03-06 | 79.28% | 69.16% | SEC | Central | Riyadh | 2026-04-15 | Under Approval | 2026-03-06 | 2026-09-06 | 2026-10-20 | 2026-05-06 | 2026-11-06 | 2026-12-20 | 2026-08-06 | 2026-02-06 | 2026-03-22 | 1.Delay in delivery of AES scope material. (delay in these materials ,impact the project completion ) 2.Delay in 380 kv insulator (Lapp) 3.New fire pump-Delivery (change order), 4.Delay in delivery of MV grounding transformer
22 | PE-306 | NEW AL-ARED 380/132KV BSP | 2023-10-19 | 100% | 94.68% | SEC | Central | Riyadh | 2025-11-02 | Under Approval | 2025-04-19 | 2025-08-19 | 2026-06-30 | 2025-06-21 | 2025-10-19 | 2026-08-30 | 2025-09-19 | 2026-01-19 | 2026-11-30 | 1.Slow Punch list - Transformers ,GIS, AES 2.Delay in SEC UG Cable Vendor - New Line( Circuits 3 )
23 | PE-309 | Reliablity Enh.for SS of 9011 in Sudair | 2025-12-24 | 45.04% | 21.89% | SEC | Central | Riyadh |  | N/A | 2026-11-23 | 2026-11-23 | 2027-04-21 | 2027-01-23 | 2027-01-23 | 2027-06-21 | 2027-04-23 | 2027-04-23 | 2027-09-19 | Current issues 1.Delay in Plan & Profile - OHTL 2.Delay in Plan & Profile - UG Cable ( T- off Tower Location) 3.Delay in SE supply GIS Bays 4.Delay in Material :- Tower, Hardware, Insulator 5. Delay in providing existing Design : Remote End, U/G 8500 to 8521, Basement & Sleeves Details, Telecom Room, Control Room Layouts 6.Delay in Mobilization of Project Team OHTL Site Engr & Project Engr, QA & QC Civil & Electrical 7. Unclear Shutdown for Project
24 | PE-310 | Al Shifa Housing 132/13.8KV SS | 2024-01-22 | 94.6% | 86.92% | SEC | Central | Riyadh | 2026-01-27 | Approved | 2025-11-22 | 2026-06-21 | 2026-08-17 | 2026-01-21 | 2026-08-21 | 2026-10-17 | 2026-04-21 | 2026-11-21 | 2027-01-17 | 1.Incomplete HV underground cable works under another contractor’s scope are impacting the substation energization activities. 2.STATCOM PQS approval remains pending with SEC/vendor, affecting material delivery and subsequent installation. 3.Delay in remote end (8131) works due to pending C1 work permit
25 | PE-326 | Shaqra Wind 380/132kV SS | 2024-10-24 | 96.75% | 68.77% | SEC | Central | Riyadh |  | Under Approval | 2026-05-23 | 2026-05-23 | 2026-12-31 | 2026-07-23 | 2026-07-23 | 2027-03-02 | 2026-10-23 | 2026-10-23 | 2027-06-02 | 1-Delay in the delivery of 132kV and 380kV GIB and Hybrid GIS (SEC Direct purchase) beyond the scheduled dates, where the original plan was December 2025; however, only the 132kV GIB was delivered in end of May 2026, while the 380kV GIB and Hybrid GIS are still pending. 2-Delay in the supply of AC and DC panels from AES up to date. 3- Delay in obtaining ITP approvals for DSM and TFR systems AES prequalification to perform the FAT in AES factory. 4-Change order confirmation for the additional scope , which holding following activities (Civil work for Search facilities - Guard house - security building and along with all septic tank and water connections , HCIS stage 3 finalization and approval , Procurement of all electrical , mechanical , security material related to this pending . 5-Delay in the approval of firefighting system designs due to changing multiple changes in the review process from SEC and adding new comments with each revision. 6- After approval of lightening panels design (MS Hawaa ) SEC insist to change the manufactural to new alternate as (MS hawaa )is currently suspended in the system 7- Confirmation of EOT which submitted 9-Apr-26.
26 | PE-335 | Battery Energy (BESS) - Qaisumah | 2024-12-16 | 100% | 95.63% | SEC | Central | Riyadh |  | N/A | 2026-05-16 | 2026-05-16 | 2026-05-11 | 2026-07-16 | 2026-07-16 | 2026-07-11 | 2026-10-16 | 2026-10-16 | 2026-10-11 | Energized.
27 | PE-336 | Battery Energy (BESS) - Dawadmi | 2024-12-16 | 100% | 97.66% | SEC | Central | Riyadh |  | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | 2026-07-16 | 2026-07-16 | 2026-07-10 | 2026-10-16 | 2026-10-16 | 2026-10-10 | Energized.
28 | PE-337 | Battery Energy (BESS) - Airport | 2024-12-16 | 100% | 98.83% | SEC | Central | Riyadh |  | N/A | 2026-05-16 | 2026-05-16 | 2026-05-06 | 2026-07-16 | 2026-07-16 | 2026-07-06 | 2026-10-16 | 2026-10-16 | 2026-10-06 | Energized.
29 | PE-339 | Battery Energy (BESS) - Jouf | 2024-12-16 | 100% | 98.62% | SEC | Central | Jouf |  | N/A | 2026-05-16 | 2026-05-16 | 2026-05-16 | 2026-07-16 | 2026-07-16 | 2026-07-16 | 2026-10-16 | 2026-10-16 | 2026-10-16 | Energized.
30 | PE-348 | Construction of Hail-2 Substation for BESS | 2025-07-03 | 88.73% | 46.61% | SEC | Central | Hail |  | N/A | 2026-06-03 | 2026-06-03 | 2026-09-15 | 2026-08-03 | 2026-08-03 | 2026-11-15 | 2026-11-03 | 2026-11-03 | 2027-02-15 | 1-Delay in approving critical designs such as FF designs, & Remote end AMI , with some submittals open for more than 3 months 2- Delay in design inputs has delayed grid studies submission & approval cycles 3- Delay in Alfanar equipment delivery: - Auxiliary transformer - AC & DC Panels - TFR & DSM - Remote End AMI & Metering 4- Delay in BESS Supplier fire fighting protion delivery (BESS gas pipes) 5- Delay in Firefighting pumps delivery 6- Delay in surge arrestors, and post insulators delivery 7- Delay in 33Kv SWGR termination kits delivery 8- Delay in HGIS Delivery: 1 out of 2 Bays delivered 9- Delay in UPS delivery
31 | PE-353 | Conv of Riyadh CC PP10 - Phase 2 | 2025-05-08 | 40.19% | 16.42% | SEC | Central | Riyadh |  | N/A | 2027-05-08 | 2027-05-08 | 2028-01-13 | 2027-06-08 | 2027-06-08 | 2028-02-13 | 2028-06-08 | 2028-06-08 | 2029-02-13 | 1.Base Design Approval : Disagreement with SE on interpretation of the Contract. 2.Engineering Review Cycle Delays : Agreed timelines for review are not being adhered. 3.Delivery durations for critical (LLIs) exceed the Contractual timeline, creating a significant risk to meeting the contractual milestones. 4.Accelerated Dec 2026 completion requested by SE for GT 1st Fire. 5.Site Access Gate Permits & Work Permit issues.
32 | PE-356 | 380KV OHTL ¦ MAWQAQ BSP CONNECTION | 2025-08-28 | 53.31% | 16.06% | SEC | Central | Riyadh |  | Under Approval | 2027-02-28 | 2027-02-28 | 2027-12-02 | 2027-04-27 | 2027-04-27 | 2028-01-31 | 2027-07-27 | 2027-07-27 | 2028-04-30 | 1) Revised Route with additional change order.Revised Route under approval 2) Finalization of the route is pending for the portion that falls under KSRR. 3) Cost and time impact resulting from the increased transmission line route length and associated scope changes. 4) Delay in approval of plan and profile
33 | PE-360 | SMP¦OPERATION & PROF. SERVICES (HES&HHU) | 2025-07-15 | 83.33% | 83.33% | SEC | Central | Riyadh |  | N/A | 2026-07-14 | 2026-10-14 | 2026-10-14 | 2026-07-14 | 2026-10-14 | 2026-10-14 | 2026-07-14 | 2026-10-14 | 2026-10-14 | Extension of 1 quarter received
34 | PE-362 | 132KV SS ¦CONST. SPORTS BOULEVARD-RIYADH | 2025-08-13 | 33.24% | 21.94% | SEC | Central | Riyadh |  | N/A | 2027-02-11 | 2027-02-11 | 2027-09-30 | 2027-04-11 | 2027-04-11 | 2027-11-28 | 2027-07-11 | 2027-07-11 | 2028-02-27 | Delay in Site Handing Over. Not handed over yet
35 | PE-316 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 | 2024-06-27 | 79.32% | 69.71% | SEC | Central | Riyadh |  | N/A | 2026-12-31 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-02-28 | 2027-03-31 | 2027-05-31 | 2027-05-31 | 2027-07-01 | -
36 | PE-317 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 | 2024-06-27 | 89.48% | 78.73% | SEC | Central | Riyadh |  | N/A | 2026-12-31 | 2026-12-31 | 2027-02-28 | 2027-02-28 | 2027-02-28 | 2027-04-28 | 2027-05-31 | 2027-05-31 | 2027-07-29 | -
37 | PE-363 | SULYBIAH SS 8823 132/33KV | 2026-01-25 | 5.05% | 3.42% | SEC | Central | Qassim |  | N/A | 2027-07-25 | 2027-07-25 | 2027-10-13 | 2027-09-25 | 2027-09-25 | 2027-12-14 | 2027-12-25 | 2027-12-25 | 2028-03-14 | 1. Delay in Receiving Design for GIS Package Supplied by SEC Vendor 2. Delay in soil investigation activities due to one corner of the substation located on farmland 3. Terminal compound 1 location changed 4. Repetition of soil investigation activities due to the client's rejection of the proposed vendor
38 | PE-372 | AL-DWADMI SS 8618 132/33KV | 2026-01-14 | 8.58% | 5.79% | SEC | Central | Riyadh |  | N/A | 2027-07-12 | 2027-07-12 | 2027-09-30 | 2027-09-12 | 2027-09-12 | 2027-12-01 | 2027-12-12 | 2027-12-12 | 2028-03-01 | 1. Delay in approval of GEL 2. Delay of Receiving Design for GIS Package Supplied by SEC (GIS Delivery delayed ) 3. Delay in municipality approval 4. Delay in Issuance Of P.O Transformer
39 | PE-394 | NEW AL-GHADIR SS#8237 132/33K | 2026-01-21 | 7.39% | 5.63% | SEC | Central | Riyadh |  | N/A | 2027-09-21 | 2027-09-21 | 2027-10-21 | 2027-11-21 | 2027-11-21 | 2027-12-21 | 2028-02-21 | 2028-02-21 | 2028-03-22 | -
40 | PE-395 | New Al- Wadi 132/13.8Kv substation #8224 and its Connection in Riyadh City | 2026-02-11 | 2.36% | 3.9% | SEC-COA | Central | Riyadh |  | N/A | 2027-10-11 | 2027-10-11 | 2027-11-04 | 2027-12-11 | 2027-12-11 | 2028-01-04 | 2028-03-11 | 2028-03-11 | 2028-04-04 | 1- Civil construction and related engineering/design activities suspended due to site cavities discovered after Soil investigation report. 2- Under Ground cables radar scanning & cable route layout submission.
| PE-389 | CONSTRUCTION OF AL-MAJMAA HOUSING 132/13.8KV SUBSTATION# 8534 | 2026-04-30 | 3.35% | 1.45% | SE | Central | Riyadh |  | N/A | 2027-12-30 | 2027-12-30 | 2028-02-19 | 2027-02-28 | 2028-02-29 | 2028-04-20 | 2028-05-30 | 2028-05-30 | 2028-07-20 | 1-Soil investigation not started due to the final approval of Borehole location submittal 2- GIS design not finilzed yet with the designer
| PE-381 | CONSTRUCTION OF 132/13.8KV ALARIDH-3 SUBSTATION # 8363 IN RIYADH CITY
| PE-373 | Replacement of the existing 132/33/13.8kV Al-Githamiyah S/S # 8903 by Constructing of new 132/33/13.8kV Al-Githamiyah S/S # 8933-Hail Area | 2026-03-16 | 12.81% | 5.17% | SE | Central | Hail |  | N/A | 2027-07-16 | 2027-07-16 | 2027-10-09 | 2027-09-16 | 2027-09-16 | 2027-12-11 | 2027-12-12 | 2027-12-12 | 2028-03-11 | 1-MISSING C1 & C2 CERTIFIED EMPLOYEE, WHICH AFFECTS SOIL INVESTIGATION WORKS. 2-DELAY IN REMOVAL OBSTACLES(LIVE TRANSFORMER & UNDER GROUND CABLES PASSING BY THE MAIN BUILDING) BY SE.
| PE-393 | CONSTRUCTION OF NEW 132/13.8KV SUBSTATION # 8721 IN NORTH OF AL KHARJ
| PE-361 | Construction of New Al Sahafa 132/13.8KV S/S # 8316 and its connection in Riyadh city | 2026-06-18 | 2.19% | 1.42% | SE | Central | Riyadh |  | N/A | 2028-02-18 | 2028-02-18 | 2028-02-18 | 2028-04-18 | 2028-04-18 | 2028-04-18 | 2028-07-18 | 2028-07-18 | 2028-07-18 | 1- Baseline not approve yet ,try to fix comment and send it 2-Soil investigation not started due to the final approval of Borehole location submittal
|  | EASTERN REGION UNIT | [17 empty] | - | Planned % | Performed % | TCC | PAC | FAC
41 | PE-181 | EPC OF PRIMARY ELECTRICAL SUSBSTATION #3 | 2020-02-23 | 100% | 100% | RC | Eastern | Ras Al Khair |  | Approved | 2021-12-30 | 2021-12-30 | 2021-12-22 | NA | NA | 2024-10-24 | 2021-12-30 | 2021-12-30 | 2025-12-31 | All Certificates Recieved | 100% | 100% | 2021-12-30 | 2024-10-24 | 2025-12-31
42 | PE-199 | SPARK 380/115/13.8KV BSP | 2018-12-01 | 100% | 100% | SEC | Eastern | Abqaiq |  | Approved | 2020-09-30 | 2020-09-30 | 2021-04-30 | 2020-11-30 | 2020-11-30 | 2021-06-30 | 2025-06-30 | 2025-06-30 | 2025-05-31 | All Certificates Recieved | 100% | 100% | 2021-04-30 | 2021-06-30 | 2025-05-31
43 | PE-213 | Construction Of Hawayah 380 KV S/S | 2020-01-23 | 100% | 100% | SEC | Eastern | Huwyha |  | N/A | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Sep-22 UQA :30-Aug-26 | HUW : 30-Sep-22 UQA : 30-Jun-23 | HUW : 30-Sep-22 UQA : 30-Jun-23 | HUW : 30-Sep-22 UQA :30-Sep-26 | HUW :31-Dec-22 UQA : 30-Sep-23 | HUW :31-Dec-22 UQA : 30-Sep-23 | HUW :27-May-25 UQA :30-Nov-26 | P1: All Certificates Recieved P2: No Certificates Recieved | 100% | 100% | 2024-09-30 | 2024-11-30 | 2025-02-28
44 | PE-229 | Construction of Temporary Rail Line (CO project of PE-181) |  | 100% | 100% | RC | Eastern | Ras Al Khair |  | Approved | NA | NA | NA | NA | NA | NA | 2024-11-09 | 2024-11-09 | 2025-12-31 | All Certificates Recieved | 100% | 100% | 2025-12-31 | 2025-12-31 | 2025-12-31
45 | PE-240 | JSWCC¦OHTL Package | 2022-05-23 | 100% | 100% | SWCC | Eastern | Jubail |  | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-01-31 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC Pending on PE-238 | 100% | 100% | 2026-01-31 | 2026-01-31 | 2026-01-31
46 | PE-214 | UTHMANIYAH | 2020-02-23 | 100% | 99.98% | Aramco | Eastern | Dammam |  | Approved | 2023-07-27 | 2024-11-30 | 2024-09-15 | 2023-11-04 | 2024-11-30 | 2024-10-24 | 2023-11-04 | 2024-11-30 | 2026-04-30 | All Certificates Recieved FAC not Not applicable/MCC | 100% | 99.98% | 2024-09-15 | 2024-10-24 | 2026-04-30
47 | PE-227 | Ibn zahr Expn. | 2021-06-10 | 100% | 88.29% | SEC | Eastern | Dammam |  | Approved | 2022-09-10 | 2024-04-30 | 2026-11-05 | 2022-10-10 | 2024-05-30 | 2026-12-05 | 2022-11-10 | 2024-06-30 | 2027-01-05 | - | 100% | 88.29% | 2026-11-05 | 2026-12-05 | 2027-01-05
48 | PE-238 | SWCC ¦ BSP Portion | 2022-05-23 | 100% | 98.17% | SWCC | Eastern | Jubail |  | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-01-31 | 2024-02-23 | 2024-02-23 | 2026-06-30 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC | 100% | 98.17% | 2026-01-31 | 2026-01-31 | 2026-06-30
49 | PE-239 | SWCC ¦ Solar Package | 2024-02-14 | 100% | 90.7% | SWCC | Eastern | Jubail |  | Under Approval | 2025-02-14 | 2025-02-14 | 2026-06-30 | 2025-02-14 | 2025-02-14 | 2026-06-30 | 2025-02-14 | 2025-02-14 | 2026-06-30 | - | 100% | 90.7% | 2026-07-31 | 2026-07-31 | 2026-07-31
50 | PE-277 | Thuqbah BSP 380/115KV | 2023-10-19 | 98.83% | 96.61% | SEC | Eastern | Thuqbah |  | Approved | 2025-04-19 | 2026-05-31 | 2026-05-31 | 2025-06-19 | 2026-07-31 | 2026-10-11 | 2025-09-19 | 2026-10-31 | 2027-01-31 | - | 98.83% | 96.61% | 2026-05-31 | 2026-10-11 | 2027-01-31
51 | PE-288 | Repl. of Berry Gas Plant 230/115KV SS | 2024-05-19 | 92.01% | 85.51% | SEC | Eastern | Jubail | Not Yet | Under Approval | 2026-01-19 | 2026-01-19 | 2026-10-10 | 2027-02-19 | 2027-02-19 | 2027-10-10 | 2027-05-19 | 2027-05-19 | 2027-11-10 | OHTL Portion after 11 months from SS which is shown here | 92.01% | 85.51% | 2026-10-10 | 2027-10-10 | 2027-11-10
52 | PE-302 | AL RAMES 380/115 KV BSP | 2023-10-19 | 99.47% | 99.27% | SEC | Eastern | Dammam |  | Approved | 2025-04-19 | 2026-11-30 | 2026-05-31 | 2025-06-19 | 2027-01-30 | 2027-03-11 | 2025-09-18 | 2027-04-30 | 2027-06-30 | Expected TCC will be on 13 Dec 26 due to delay of FOC readiness (31 Aug 2026) / Disconnector Switch | 99.47% | 99.27% | 2026-05-31 | 2027-03-11 | 2027-06-30
53 | PE-334 | Ghazlan-3 BSP | 2025-02-09 | 72.11% | 46.53% | SEC | Eastern | Ghazlan | Not Yet | Under Approval | 2026-07-09 | 2026-07-09 | 2027-04-23 | 2026-09-09 | 2026-09-09 | 2027-06-30 | 2026-12-09 | 2026-12-09 | 2027-09-30 | Planned % is based on orginal baseline however we have a submitted revised schedule showing 80% used for internal reporting | 72.11% | 46.53% | 2027-04-23 | 2027-06-30 | 2027-09-30
54 | PE-344 | Nariyah BSP | 2025-02-27 | 95.49% | 56.83% | SEC | Eastern | Nariyah |  | N/A | 2026-09-26 | 2026-09-26 | 2027-06-06 | 2026-11-26 | 2026-11-26 | 2027-08-08 | 2027-02-26 | 2027-02-26 | 2027-11-08 | Delayed due to the delivery of GIS equipment Delayed 2times 1st delay till 25-June-26 2nd Delay till 25-Aug-26 | 95.49% | 56.83% | 2027-06-06 | 2027-08-08 | 2027-11-08
55 | PE-355 | Construction of King Saud Air Base Facilities | 2025-08-10 | 17.57% | 12% | RSAF | Eastern | Haffr Albatan |  | N/A | 2027-08-10 | 2027-08-10 | 2027-09-27 | 2027-10-10 | 2027-10-10 | 2027-11-30 | 2028-12-10 | 2028-12-10 | 2028-12-10 | Only Scope Alfanar / There is no FAC only based on the 40 Months Completion | #N/A | #N/A | #N/A | #N/A | #N/A
56 | PE-304 | 230/115kV SS ¦ JUBAIL SW REPLACEMENT | 2025-08-31 | 19.69% | 12.6% | SEC | Eastern | Jubail |  | N/A | 2027-08-31 | 2027-08-31 | 2028-04-27 | 2027-10-31 | 2027-10-31 | 2028-06-26 | 2028-01-31 | 2028-01-31 | 2028-09-27 | Delayed due to site accessibility issues and Water leakage incident | 19.69% | 12.6% | 2028-04-27 | 2028-06-26 | 2028-09-27
57 | PE-366 | Qulayyib 380 kV BSP | 2026-04-01 | 6.743% | 3.998% | MGC-Mutlaq Al Gowairi Company | Eastern | Qulayyib Area |  | N/A | 2028-06-01 | 2028-06-01 | 2028-07-09 | 2028-06-01 | 2028-06-01 | 2028-07-09 | 2029-06-01 | 2029-06-01 | 2029-07-09 | - | 6.743% | 3.998% | 2028-07-09 | 2028-07-09 | 2029-07-09
58 | PE-354 | Construction of NEW VSC HVDC Overhead Transmission Line for EOA-COA Link 1 | 2026-05-04 | 2.939% | 1.827% | SEC | Eastern | Nariyah |  | N/A | 2028-11-04 | 2028-11-04 | 2028-11-22 | 2029-01-04 | 2029-01-04 | 2029-01-23 | 2029-04-04 | 2029-04-04 | 2029-04-28 |  | 2.939% | 1.827% | 2028-11-22 | 2029-01-23 | 2029-04-28
|  | WESTERN REGION UNIT | [17 empty] | -
59 | PE-243 | Installation of Dynamic Reactive Power Compensation(DRPC) at Tabuk 380KV BSP | 2022-05-19 | 100% | 100% | SEC | Western | Tabuk | 2025-09-02 | Approved | 2024-07-19 | 2025-04-30 | 2025-04-30 | 2024-09-19 | 2025-11-30 | 2026-12-30 | 2024-11-19 | 2026-01-30 | 2027-02-28 | Energization done without TSC Panel, TCC received. Partial PAC (21-Jan-2026) also received; Balance PAC & FAC upon delivery of remaining TSC Panel; Alfanar requested for FAC invoice and under discussion with SEC.
60 | PE-241 | Expansion of Existing Yanbu Central (YCNT) | 2022-02-06 | 100% | 98.9% | SEC | Western | Yanbu,Umluj& Alwajh |  | N/A | 2024-01-06 | 2024-09-30 | 2024-09-30 | 2024-03-06 | 2024-11-30 | 2026-04-20 | 2024-06-06 | 2025-02-28 | 2026-09-20 | PAC received, not yet energized due to SE shutdown issues for all the area
61 | PE-257 | Expansions of Existing MHD 380 KV BSP | 2022-11-03 | 100% | 99.89% | SEC | Western | Madinah |  | N/A | 2024-05-03 | 2025-10-30 | 2025-12-30 | 2024-07-03 | 2025-12-30 | 2026-03-01 | 2024-10-02 | 2026-03-30 | 2026-06-01 | As-built drawings under SEC review & approval. FAC certification waiting from SE; Request for issuance of FAC / Commitment for Completion of Outstanding Work was submitted on 20-Jul-26.
62 | PE-258 | Taif East Governorate Project | 2022-11-17 | 100% | 90% | SEC | Western | Taif |  | N/A | 2024-04-17 | 2024-12-17 | 2026-09-30 | 2024-06-17 | 2025-02-15 | 2026-10-29 | 2024-09-17 | 2025-05-16 | 2027-01-27 | 1. EOT-1 Approved upto 14-Dec-24, EOT-2 submitted on 12th Aug 25, TCC upto 17th Jun 26. (Under SEC Approval). EOT to be resubmitted. 2. SAS testing pending due to EWS V.O finalization and delivery (V.O) 3. OHTL Line readiness pending from SE, no clarity on readiness
63 | PE-270 | 110/13.8KV HARAZAT SUB JEDDAH | 2023-07-13 | 100% | 98.41% | SEC | Western | Jeddah |  | N/A | 2024-11-13 | 2025-03-13 | 2025-07-29 | 2025-01-13 | 2025-05-13 | 2025-11-11 | 2025-04-13 | 2025-08-13 | 2026-09-30 | Remote End Works: 1. Installation of Telecom Panels completed, testing will be done, once line readiness from client. (Dependent on Line Readiness from Client) 2. Final Settings of Line Protection Panels. (Dependent on Line Readiness from Client) Punchlist & As built works are in progress, completion date 30-Sep-26. Punchlist:Total 309 nos, 295 Completed, 5 nos ready to close. Asbuilt: 90% completed.
64 | PE-290 | Fadelah 110/13.8KV SS - JEDDAH | 2023-07-24 | 100% | 98.42% | SEC | Western | Jeddah |  | N/A | 2024-11-24 | 2025-09-24 | 2025-06-26 | 2025-01-24 | 2025-01-24 | 2025-11-18 | 2025-04-24 | 2026-04-26 | 2026-09-30 | 1) Energization done with temporary line, (Permanent line readiness Dependent on Client). 2) AMI integration with WRCC. (Dependent on Line Readiness from Client). 3) Modon GIS extension bays (Shutdown -Relay setting ) 85% completed. Punchlist & As built works are in progress, completion date 30-Sep-26. Punch points : Out of 10, 2 completed, 3 ready to close. As built status: out of 12, 12 ready to close.
65 | PE-254 | HENAKIYAH BSP 380 KV | 2022-10-27 | 100% | 100% | SEC | Western | Madinah |  | N/A | 2024-09-27 | 2024-12-31 | 2025-04-07 | 2024-11-27 | 2025-02-28 | 2026-03-08 | 2025-02-27 | 2025-05-30 | 2026-05-07 | FAC received
66 | PE-260 | Sanabel con.at Jeddah | 2022-12-29 | 100% | 97.5% | SEC | Western | Jeddah |  | N/A | 2024-10-29 | 2025-01-30 | 2025-12-01 | 2024-12-29 | 2025-04-01 | 2026-08-15 | 2025-03-28 | 2025-07-03 | 2026-10-03 | SAS Configuration and testing pending, due to AES team mobilization pending
67 | PE-262 | Reinf. of Thuwal Town KAUST 2 | 2022-12-29 | 100% | 96.96% | SEC | Western | Jeddah |  | N/A | 2024-08-29 | 2024-12-30 | 2025-12-01 | 2024-10-29 | 2025-03-01 | 2026-08-15 | 2025-01-28 | 2025-06-03 | 2026-10-03 | SAS Configuration and testing pending
68 | PE-296 | Waly Alahad-4 110/13.8KV SS | 2023-10-19 | 100% | 94.53% | SEC | Western | Makkah |  | N/A | 2025-02-19 | 2025-11-19 | 2025-11-19 | 2025-04-19 | 2026-01-19 | 1900-01-07 | 2025-07-19 | 2026-04-19 | 2026-10-26 | 1) Line readiness pending from SEC
69 | PE-281 | 110KV SS - KAEC-3 | 2024-05-30 | 100% | 99% | SEC | Western | Jeddah |  | N/A | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2026-01-30 | 2026-01-30 | 2026-03-12 | 2026-04-29 | 2026-04-29 | 2026-06-30 | TCC, PAC Received. FAC Letter Submitted to Client
70 | PE-280 | 110KV SS - KAEC-2 | 2024-05-30 | 100% | 100% | SEC | Western | Jeddah |  | N/A | 2025-11-30 | 2025-11-30 | 2025-11-30 | 2026-01-30 | 2026-01-30 | 2026-03-12 | 2026-04-29 | 2026-04-29 | 2026-04-29 | FAC received
71 | PE-185 | NG Taif | 2018-02-25 | 100% | 99.65% | NG | Western | Taif |  | N/A | NA | NA | NA | 2020-02-25 | 2025-07-14 | 2026-08-15 | 2021-02-25 | 2026-07-14 | 2027-06-30 | EOT: Contract amendment approved,PCC on 14th Jul 25, EOT-2 submitted on 4th Nov 25, with 8 months (PCC: 14th Mar 26), Under SEC approval 1) All cable ceiling end joints works replacing works in progress, expected compeltion by 30th May 26. 2) Remote end-1 final setting done, Remote end 2 final setting completion by 10th May. 3) HV Test and end to end test pending expected completion by 15th Jun and 30th Jun
72 | PE-267 | CONST KAR 380 110KV BSP | 2023-06-01 | 100% | 97.94% | Masar | Western | Makkah | 2025-09-01 | Approved | 2025-05-31 | 2025-12-31 | 2025-12-31 | 2025-07-30 | 2026-03-01 | 2026-10-08 | 2025-09-30 | 2026-05-01 | 2026-12-08 | 1.Close loop test completed 2. HVAC Testing: Completed 3. FF & FA Testing: All testing is completed and Remaining Final testing with ISD is in progress. 4. C04 modification work will be started after Energization of C06 Feeder as per SEC instruction. This will required 2 months to complete the task. 5. TCC received 6. New Change Order (confrimed) i.e. Duct Bank for future Area.-Completed 7.End to end test in progress, Expected engization by Aug'26 end.
73 | PE-291 | HAMRA AL ASAD 110/13.8 KV SUB | 2023-07-26 | 100% | 99.98% | SEC | Western | Madinah |  | Approved | 2024-11-26 | 2025-09-30 | 2026-05-21 | 2025-01-26 | 2025-11-30 | 2026-07-30 | 2025-04-26 | 2026-02-28 | 2026-09-30 | 1) TCC received on 21-May-26. PAC received on 30-Jul-26. (Energization done through the AZIZIA remote-end and TCC was obtained. Remaining interface works at the MICY remote end are ongoing and are expected to be completed by end of Aug 2026.) 2) Target is to energize both remaining feeders with remote end by 1st week of Sep. 2026
74 | PE-292 | Shoran-2 110/13.8 KV - Madinah | 2023-07-24 | 100% | 99.25% | SEC | Western | Madinah |  | Under Approval | 2024-11-24 | 2024-11-24 | 2026-08-31 | 2025-01-25 | 2025-01-25 | 2026-10-31 | 2025-04-24 | 2025-04-24 | 2027-01-30 | 1) TCC is requested , still not issued. Readiness of UGC circuits have delayed energization of the substation and TCC issuance. 2) Expected energization by end of Aug. 2026 if the UGC Feeders passed ongoing Tests by Cable contractor.
75 | PE-315 | 110KV Salam Royal Palace | 2024-04-04 | 100% | 95.9% | SEC | Western | Jeddah |  | N/A | 2025-10-04 | 2025-10-04 | 2026-01-15 | 2025-12-04 | 2025-12-04 | 2026-03-12 | 2026-03-04 | 2026-03-04 | 2026-08-30 | 1) EOT-1 Submitted on 13th Aug 25, with TCC date on 23rd Jul 26. Under SEC approval 2) Energization actual date 15th Jan 26
76 | PE-263 | MOWAIH PV 380/110V BSP | 2023-03-29 | 100% | 99% | SEC | Western | Taif |  | N/A | 2025-03-29 | 2025-10-31 | 2026-01-06 | 2025-05-29 | 2025-12-30 | 2026-05-08 | 2025-08-28 | 2026-02-28 | 2026-08-30 | EOT is submitted with TCC and was approved on 21st Apr 26 Energization done, and TCC was received on 21st Apr 26
77 | PE-246 | UM-AL-JOUD BSP | 2022-09-08 | 100% | 88.95% | SEC | Western | Makkah |  | Under Approval | 2023-11-08 | 2025-02-07 | 2026-08-30 | 2024-01-08 | 2025-04-07 | 2026-10-30 | 2024-04-08 | 2025-07-07 | 2027-01-30 | 1) EOT-2 submitted to client on 8th Jan 25, Revised TCC date confirmation is pending by SEC (Due to no clarity in readiness of remote end i.e. Fahya SS). EOT-2 resubmitted on 14-June-26 for Revised TCC on 31-July-27. Once approved, TCC letter will be submitted. 2) Remote end protection desing approval pending from SEC. Holding the procurement of loose material & modification work at remote end. 3) Protection scope for Fahya Substation is unknown: Due to which Design submission and approval for modification and procuring loose material is still not finalized 4) Restriction to work inside Rusifah Substation: No confirmation on Panel Installation is provided in Rusifah Substation due to limitations of space. Also, FOC cable pulling & termination inside SS is on hold. 5) Testing of Fiber & High Voltage cable is required to start. Waiting for SEC witness. 6) Shut down from SEC is required for Replacing Relay from Rushifah to Umaljoud. Still no clarity on shutdown also.
78 | PE-265 | 110/33 KV ALMAHANI S/S IN TAIF | 2023-05-14 | 100% | 92.3% | SEC | Western | Taif | 2025-02-02 | Under Approval | 2025-01-14 | 2025-11-30 | 2026-10-30 | 2025-03-14 | 2026-01-30 | 2026-12-30 | 2025-06-14 | 2026-03-30 | 2027-02-28 | EOT: EOT submitted TCC upto 30-Nov-26. Under SEC approval. 1) delay in final setting approval for SWGR and Capacitor bank and line protection delaying open loop Tests 2) Delayed HV kit for GIS HV test (was scheduled by Jul-26) now rescheduled to 20-Aug-26 3) Delayed installations of the (HV Terminations, CSE, MV Terminations) pending subcontractor. (PO Under finalization with SCD) 4) Delayed open loop tests for the major equipment due to non-availability of SAS engineer. (Will be mobilized after Approval of final settings) 5) OHTL Line readinees (AL-mahani to MAHD), No clarity on the completion by other contractor.
79 | PE-266 | EXT. OF THE EXIS. THAGEF &ADAM | 2023-05-14 | 100% | 86.63% | SEC | Western | Taif | 2025-10-14 | Under Approval | 2025-01-14 | 2025-10-14 | 2026-11-30 | 2025-03-15 | 2025-12-14 | 2027-01-30 | 2025-06-14 | 2026-02-14 | 2027-03-30 | EOT: EOT-2 submitted with TCC date of 27-Jul-26. (Under SEC Approval) 1) AES Control panel (Mosaic and Annciator) detail design still under approval & no clarity on FAT date. (expected by Sep-26). 2) Missing BCU units for ADAM LCC (Hyundai), Provided by AES (Purchased from SIEMENS) Delayed since Feb-26, Latest provided date by AES is by Oct-26 3) Loose materials are required from AES for Protection, LCC Panels. To be compatible with existing systems and proceed commissioning activities 4) Delayed delivery of the PC Workstation (EWS) and the PO is still under Finalization with SCD 4) No Clarity of OHTL Line readiness.
80 | PE-286 | SEC Smart Distribution Control Centre | 2024-07-25 | 98.31% | 90.21% | SEC | Western | Jeddah |  | N/A | 2026-07-25 | 2026-07-25 | 2026-12-31 | 2026-09-25 | 2026-09-25 | 2027-02-19 | 2027-09-24 | 2027-09-24 | 2028-02-18 | 1. SLD Submission for Downstream : CET/NARI Shortage on Manpower where current manpower is 28 and plan to be 39 by 31-Jul-26 , Target Completion Madinah : 05-Sep-26 , Jeddah :06-Oct-26 ,Makkah : 06-Oct-26 ,Abha :03-Sep-26 , Jizan : 16-Sep-26. 2. Abha ADMS System Crash: SLD NDesigner application crashed during implementation activities in Abha, resulting in delays to SLD preparation, submission, and validation activities. 3. Cyber Security Audit : Audit plan not yet Approved by SE and the PO (Third Party) has not been issued by NARI (affecting Cutover). The audit requires approximately 10 weeks after PO issuance. 4. NARI End-to-End Testing Team : A dedicated NARI team is required to focus exclusively on End-to-End testing activities. A total of nine engineers are expected to be mobilized by the 31 July 2026. 5. Delay in Telecom Panel Local Test for Remote End (MADINAH LDC). 6. Delay delivery of DWDM (PO issued to AES) – waiting the final confirmation for the recent traffic plan in Madina, Abha & Jizan. 7. All Submittal under review with FEC / HSSE. 8. Requirements from STC connectivity regarding IP Telephone (SIP) services. 9.1 ICT reviewer’s new comments regarding the passive scope and Beit Al Anzima rejection. 9.2 ICT rejected the material in Rev-02 although no comments were received in Rev-01. 9.3 The material has already been delivered and installed on site. 9.4 The ICT reviewer has been rejecting every submitted versions without providing any specific technical comments or justified reasons, Also rejecting both of the approved Design Consultant and the Contractor. This repeated rejection practice is causing significant delays to the project and directly impacting the implementation and activation of critical ICT services, including Internet connectivity, IP Telephony, and system integrations.
81 | PE-287 | Exp. of YCNT BSP for Power to Neom | 2023-08-01 | 93.38% | 95.08% | NEOM / SEC | Western | Yanbu |  | N/A | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-06-01 | 2027-06-01 | 2027-06-01 | 2027-08-01 | 2027-08-01 | 2027-08-01 | 1) 2 Nos GIS breakers damaged due to heavy wind (Fell down, no major damage), need to close the issues with GE Team, Breakers are sent to France Factory to get the repaired materials expected Repaired materials delivery by End of Sep-26. 2) HV Test Equipment delivery pending from GE, due to lack of equipment (Used for other site)
82 | PE-294 | Airport C (KAIA) Interconnection REINF. | 2023-11-01 | 100% | 83.99% | SEC | Western | Jeddah |  | N/A | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-04-01 | 2026-04-01 | 2026-11-09 | 2026-06-01 | 2026-06-01 | 2027-01-05 | 1) TCC Received on 09-Aug-26 as per Contractual TCC Date i.e. 01-Feb-26. 2) Remaining work cannot be proceeded due to HV Cable issue from SE. Project currently onhold from SE so manpower to be demobilized accordingly. 3) CSD refused to start T&C Activities because of the unavailability of existing HV cable from SE. 4) Change order (Approx.. 47 million) submitted to SE for additional HV cable work. Waiting for their approval.
83 | PE-295 | Interconnection of AJM-1 (New Jamoom) | 2024-01-08 | 100% | 90.52% | SEC | Western | Makkah |  | N/A | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-06-08 | 2026-06-08 | 2026-09-02 | 2026-08-08 | 2026-08-08 | 2026-11-03 | 1) T.C.C received. 2)Shutdown required for Connecting existing GIS to new GIS bay, expected in Aug-26.
84 | PE-301 | Expansion of Mowaih PV 380kV BSP | 2024-09-16 | 100% | 98.5% | SEC | Western | Mowaih |  | Under Approval | 2025-10-16 | 2025-10-16 | 2026-08-30 | 2025-12-16 | 2025-12-16 | 2026-09-30 | 2026-03-16 | 2026-03-16 | 2026-12-29 | 1) EOT-1 submitted on 16th Oct 25, with TCC Date on 27-5-26. Rejected by SEC on 21-Oct-25, Resubmitted, under approval with SE. 2) TCC delayed by SE, Due to SE-MOD time extension approval 2) 48 V DC system: FAT done delivery delayed expected delivery in Sep-26 3) Remote End Substations are not ready
85 | PE-305 | 110kV SS Kar-2 | 2024-08-28 | 93% | 90% | Masar | Western | Makkah | 2026-01-14 | Approved | 2026-04-27 | 2026-10-28 | 2026-10-28 | 2026-06-27 | 2026-11-27 | 2026-11-27 | 2026-08-27 | 2026-12-27 | 2026-12-27 | 1) Delay in Mechanical materials i.e. HVAC system (PACU), Expected material delivery by Mid Aug-26 due to current Geo-political instability.
86 | PE-307 | 132/13.8KV Sub Industrial City Tabuk | 2024-01-30 | 98.06% | 98.31% | MODON | Western | Tabuk |  | N/A | NA | NA | NA | 2026-08-14 | 2026-08-14 | 2026-08-04 | 2027-08-14 | 2027-08-14 | 2027-08-04 | Critical Issues: OLT & CLT Completed and final testing like trip test, end to end test ongoing. However, PAC form signed after mutual site visit from SE, MODON & Alfanar. All pending works to be completed to target energization.
87 | PE-308 | 110KV Salam Royal | 2026-05-11 | 10.02% | 19.33% | SEC | Western | Jeddah |  | N/A | 2027-11-10 | 2027-11-10 | 2027-11-10 | 2028-01-11 | 2028-01-11 | 2028-01-11 | 2028-04-11 | 2028-04-11 | 2028-04-11 | 1) Baldia Permit required to avoid any delay in civil activities. Discussion under process. 2) AES to expedite submission of remaining Telecom drawings & also to close SE comments for submitted drawings to avoid any delay in material delivery. 3) AES to expedite to close SE comments for Protection Relay List to avoid any delay in material delivery. Protection Detail Design to be submitted. 4) AES to expedite submission of Switchgear Detail Design.
88 | PE-312 | Const of Southern 380KV BSP ¦ Al Ula | 2024-01-08 | 98.64% | 96.15% | SEC | Western | Al Ula | 2026-03-15 | Approved | 2026-01-08 | 2026-06-30 | 2026-06-30 | 2026-03-08 | 2026-08-30 | 2026-08-30 | 2026-06-08 | 2026-11-30 | 2026-11-30 | 1) TCC received. 2) External road: Road marking 3) Testing 85% completed. 4)Finishing work and punch points in progress.
89 | PE-314 | Expansion of Tabuk BSP & Duba BSP | 2024-01-14 | 92.23% | 91.98% | SEC | Western | Tabuk & Duba | 2026-04-15 | Approved | 2026-01-14 | 2026-11-30 | 2026-11-30 | 2026-03-14 | 2027-01-30 | 2027-01-30 | 2026-06-14 | 2027-04-30 | 2027-04-30 | EOT: EOT approved with revised TCC date of 30-Nov-26. 1) Duba BSP: C5 Dia. SEC granted outage on 30-Apr-26. Dismantling of Reactor, dismantling civil foundation removal completed & construction of new foundation under progress & to be completed before 28-Sep-26. Energization as per revised TCC 30-Nov-26. 2) Tabuk BSP C02 Dia: Outage for bus-bar coupling submitted to SE, however SE informed outage will not be received during current season due to peak load. Expected outage will be around Sep’26. Hence, TCC Request submitted to SE for C02 Dia & under review
90 | PE-319 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 | 2024-06-27 | 97.17% | 94.34% | SEC | Western | Jeddah |  | N/A | 2026-12-31 | 2026-12-31 | 2027-01-21 | 2027-02-28 | 2027-02-28 | 2027-03-22 | 2027-05-31 | 2027-05-31 | 2027-06-21 | 1) Remote end works. 2) Pole 1 & Pole 2 valve hall equipment installation. 3) Pending materials delivery (CET partial materials and FF Materials).
91 | PE-324 | Stage-2 HVDC OHTL COA-WOA | 2024-08-22 | 96.3% | 82% | SEC | Western | Jeddah |  | Approved | 2026-08-22 | 2026-12-31 | 2027-02-22 | 2026-10-22 | 2027-02-28 | 2027-04-22 | 2027-01-22 | 2027-05-28 | 2027-07-22 | 1) EOT has been submitted to SE on 07-Jul-26 with TCC date 22-Jan-27 under approval with SE. 2) Variation order for increase of Route length is in under approval stage with Rev TCC date 31-Dec-26. 3) Proposed FAT for remaining Combined Towers tentatively by 10-Aug which will affect TCC by 5 Months. 4) Delay in delivery of E & D SPL Tower material (Proposed date by supplier Nov-26). 5) The outage for the diversion scope is expected to occur in October 2026, which is expected to delay the TCC completion to Feb 2027.
92 | PE-329 | SEC ¦ 132KKV OHTL Tabuk | 2024-11-05 | 99.5% | 94.93% | SEC | Western | Tabuk |  | N/A | 2026-04-05 | 2026-06-05 | 2026-08-02 | 2026-06-05 | 2026-08-05 | 2026-10-31 | 2026-09-05 | 2026-11-05 | 2027-01-31 | 1)TCC Received on 02-Aug-26 2)Acceleration in Mechanical works inside Tunnel Buhaira BSP 3) Acceleration in Access road & Structure Pad final layer
93 | PE-331 | UMM AL-QURA CEMENT OHTL | 2024-11-05 | 100% | 74.55% | SEC | Western | Makkah |  | Under Approval | 2026-03-05 | 2026-03-05 | 2026-11-26 | 2026-05-05 | 2026-05-05 | 2027-01-26 | 2026-08-05 | 2026-08-05 | 2027-04-30 | 1)Slow Rate in Tower Erection & Stringing Works 2)Change order and EOT approvals to be expedited for new revised milestones.
94 | PE-332 | 110KV OHTL FOR MAADEN-AL MAHAD | 2024-12-22 | 99.83% | 69.36% | SEC | Western | Madinah |  | Under Approval | 2026-05-22 | 2026-05-22 | 2026-12-31 | 2026-07-22 | 2026-07-22 | 2027-02-28 | 2026-10-22 | 2026-10-22 | 2027-05-31 | 1) Revised EOT Submitted to SEC on 21-Jun-26 with TCC date 10-Mar-27 under approval with SEC 2) SE notified of Required route deviation due to future plans for a factory, required reworks (Dismantling of erected towers) & additional qty. 3) Foundation concrete works delayed due to late delivery of concrete. 4) Angle Towers erection should expedite to avoid further delay in stringing works 5) Delay in Commencement of Stringing works due to Tower shortage material
95 | PE-338 | Battery Energy (BESS) -Rabigh | 2024-12-16 | 100% | 98.67% | SEC | Western | Rabigh |  | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | 2026-07-16 | 2026-07-16 | 2026-08-31 | 2026-10-16 | 2026-10-16 | 2026-11-30 | Energization done
96 | PE-345 | Arafat SS | 2025-03-10 | 87.06% | 70.51% | SEC | Western | Makkah |  | Under Approval | 2026-09-10 | 2026-09-10 | 2026-11-10 | 2026-11-10 | 2026-11-10 | 2027-01-10 | 2027-02-10 | 2027-02-10 | 2027-04-12 | 1. EOT submitted on 20-May-26 with TCC upto 8-Oct-26, SE comments received on 4th Jun 26 need to be resubmit the EOT. 2. Shutdown required from SE by Oct-26.
97 | PE-347 | Construction of Tabuk Substation for BESS | 2025-07-03 | 100% | 75.42% | SEC | Western | Tabuk |  | N/A | 2026-06-03 | 2026-06-03 | 2026-09-08 | 2026-08-03 | 2026-08-03 | 2026-11-08 | 2026-11-03 | 2026-11-03 | 2027-02-09 | 1. Approval Detailed Design for switchgear, ACDB & PDMS 2. Delay in Delivering HGIS from Hitachi for second bay 3. Delay in Delivering for 125v DC System 4. Approval for FEED package 5. Delay in Inputs for Grid Studies from BYD 6. FAT confirmation for Auxiliary Transformer, Lighting Panels, ACDB, DSM, TFR 7. PDC Support required for approval of DSM & TFR. 8. AMI DESIGN APPROVAL 9. FIBER OPTIC ROUTE PLAN. 10. BASE DESIGN APPROVAL FOR TRANSFORMER. 11. DELIOVERY CONFRIATION OF FIRE PUMP MATERIAL
98 | PE-328 | CONSTRUCTION OF ALWESSAM TAIF 110/13.SKV SUBSTATION IN TAIF | 2025-07-22 | 55.45% | 26.41% | SEC | Western | Taif |  | N/A | 2027-01-22 | 2027-01-22 | 2027-06-30 | 2027-04-22 | 2027-04-22 | 2027-08-30 | 2027-06-22 | 2027-06-22 | 2027-10-27 | 1) Delay notification sent to SEC, Due to delay in issuance of construction permit & delay in design (08 Months) 2) Steel binding work & formwork for Main Building wall in progress 3) Structural design approval needs to be expedited
99 | PE-368 | CONSTRUCTION OF A NEW 132/13.8KV SUBSTATION RABIAH TABUK (RBTBK) & ITS 132KV INTERCONNECTION IN TABUK | 2025-09-11 | 35.83% | 31.3% | SEC | Western | Tabuk |  | N/A | 2027-03-11 | 2027-03-11 | 2027-08-11 | 2027-06-11 | 2027-06-11 | 2027-11-11 | 2027-08-11 | 2027-08-11 | 2028-01-11 | 1) Delay in commencement of OHTL works due to SE E&DD's new requirements and involvement of SE S&SD. 2) Power Transformer delivery requires advancement by at least two months to meet the energization target. The supplier is not agreeing to/confirming the expected FAT and delivery dates before Dec-26. Due to the current global situation, the supplier has indicated that the FAT/delivery may be delayed until Jan./Feb. 2027. 3) Delay in submission and approval of Remote End design and drawings due to delay from SE in providing the existing data. 4) OHTL Line Strings have a long delivery lead time, and SE has been requested to provide the material on a borrowing basis from the SE store, subject to availability. 5) Delay in OHTL Tower works.
100 | PE-369 | CONSTRUCTION OF A NEW 110/13.8 kV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | 2025-10-07 | 38.26% | 22.91% | SEC | Western | Taif |  | N/A | 2027-04-07 | 2027-04-07 | 2027-07-05 | 2027-06-07 | 2027-06-07 | 2027-09-05 | 2027-09-07 | 2027-09-07 | 2027-12-05 | 1) Construction Sub Structure forecast completion date: 23-Sep-26. 2) Construction Super Structure forecast completion date: 26-Nov-26.
101 | PE-346 | Installation of New STATCOM ±300MV AR At 132kV Level At Northern BSP | 2025-10-29 | 20.02% | 14.51% | SEC | Western | Al Ula |  | N/A | 2028-07-29 | 2028-07-29 | 2028-05-10 | 2028-09-29 | 2028-09-29 | 2028-07-12 | 2028-12-29 | 2028-12-29 | 2028-10-11 | 1) Vendor finalization is pending for Lightning Protection, HVAC, and Cable Trays; respective design approvals/offers are under process. DPOs for Post Insulator and Crane are with SCD. 2) STATCOM Building foundation works are delayed due to delay in finalization of the STATCOM Building Architectural & Precast drawings (inputs) by the designer (DAR).
102 | PE-359 | CONSTRUCTION OF A NEW 110KV D/C OHTL FOR A NEW 110/13.8KV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | 2025-10-16 | 67.99% | 24.05% | SEC | Western | Taif |  | N/A | 2027-03-16 | 2027-03-16 | 2027-07-16 | 2027-05-16 | 2027-05-16 | 2027-09-16 | 2027-08-16 | 2027-08-16 | 2027-10-16 | 1) Delay in GAFM for Insulator. 2) Delay in GAFM for Hardware Fittings. 3) Delay in Soil investigation and Foundation work Design.
103 | PE-365 | CONSTRUCTION OF A NEW SUBSTATION KHR-1 380/110 KV BSP & EXP OF EXISTING MHR BSP UNDER RENEWABLE ENERGY | 2025-10-29 | 25.81% | 25.83% | SEC | Western | Taif |  | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2027-12-29 | 2027-12-29 | 2027-12-29 | 1) P.O issued for GIS in expansion scope to Hitachi,BD modified after site visit and proposal of reactor location and GIB routing under review 2) Reactors BD with tbea, trench china Bushing under sec review waiting confirmation of delivery date 3) Substructure 110kv building-2 not yet approved. 4) NGR P.O issuance pending due toNGR study
104 | PE-370 | CONSTRUCTION OF A NEW SUBSTATION KHR-2 380/110 KV BSP UNDER RENEWABLE ENERGY POWER PLANT (WOA) | 2025-10-29 | 25.85% | 25.5% | SEC | Western | Taif |  | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2027-12-29 | 2027-12-29 | 2027-12-29 | 1) Reactors BD with tbea, TEBA as unified desing with SEC, but now changed the BD format it will take one month to modify, it will impact GAFM issues and delivery - TBEA confirmed to deliver equipment within time limit of PO issued. 2) Control Room Building Slab completed
105 | PE-380 | AL JAMOOM 110/33/13.8KV SUBSTATION (Te3830) | 2026-01-15 | 2% | 1% | SEC | Western | Makkah |  | N/A | 2027-07-15 | 2027-07-15 | 2027-12-15 | 2027-09-15 | 2027-09-15 | 2028-02-15 | 2027-12-15 | 2027-12-15 | 2028-05-16 | 1) SE delayed in site hand over and still site co-ordinate not yet confirmed by SE. It will impact the design submission and site commencing works. 2) Delay in issuing BD for main equipment 3) Delay in engineering Phase
106 | PE-388 | CONSTRUCTION OF HENAKIYAH-3 PV | 2026-05-05 | 6.52% | 6.34% | SEC | Western | Madinah |  | N/A | 2028-05-05 | 2028-05-05 | 2028-05-05 | 2028-07-05 | 2028-07-05 | 2028-07-05 | 2028-10-05 | 2028-10-05 | 2028-10-05 | 1)BL submitted to SE for Approval 2) GLO Approval 3) delay in site office preparations and mobilization
107 | PE-398 | CONSTRUCTION OF NEW 110KV D/C OHTL FOR NEW SUBSTATION BAHITAH HOUSING IN TAIF-WOA | 2026-07-20 | [6 empty] | N/A | 2028-01-19 | 2028-01-19 | 2028-01-19 | 2028-03-19 | 2028-03-19 | 2028-03-19 | 2028-06-19 | 2028-06-19 | 2028-06-19
108 | PE-391 | ADDITION OF TWO (2) 80/100MVA 132/33KV TRANSFORMERS AT DUBA-2 SUBSTATION. | 2026-08-02 |  |  | SEC | Western | Tabuk |  | N/A | 2028-08-02 | 2028-08-02 | 2028-08-02 | 2028-10-02 | 2028-10-02 | 2028-10-02 | 2029-01-02 | 2029-01-02 | 2029-01-02 | Contract Signed, Baseline Schedule under Preparation
109 | PE-371 | Replacement of Musayjid BSP By Expansion of PS-2 BSP in Western Operating Area. | [7 empty] | N/A | [9 empty] | LOA received, Contract not yet signed
|  | SOUTHERN REGION UNIT | [17 empty] | -
107 | PE-282 | 2X25 MVAR 33KV STATCOM | 2024-02-01 | 100% | 99.79% | SEC | Southern | Al Baha |  | Under Approval | 2025-10-01 | 2025-10-01 | 2026-01-29 | 2025-12-01 | 2025-12-01 | 2026-06-30 | 2025-03-01 | 2026-03-01 | 2026-07-31 | TCC Certificate Received, working on Punch list & As-Buildt ongoing
108 | PE-283 | Al-Kara 132/33 kV SS in Baha Region | 2023-11-12 | 100% | 96.57% | SEC | Southern | Al Baha |  | Under Approval | 2025-07-12 | 2025-07-12 | 2026-08-31 | 2025-09-12 | 2026-04-27 | 2026-10-30 | 2025-12-12 | 2026-07-27 | 2027-01-28 | Delayed in Delivery of GIS,Power Transformer,SIS,SAS, SWGR. Delayed in T&C part where Remote end provision is yet to provided by Client, T&C almost done waiting for some items which require Shutdown by SE
109 | PE-284 | Qilwah North 132-33kV SS in Tihama | 2023-11-12 | 100% | 96.28% | SEC | Southern | Al Baha |  | Under Approval | 2025-07-12 | 2026-03-12 | 2026-03-12 | 2025-09-12 | 2026-05-12 | 2026-07-31 | 2025-12-12 | 2026-08-12 | 2026-10-29 | Delayed in Delivery of GIS,Power Transformer,SIS,SAS, SWGR. Delayed in T&C part where Remote end provision is yet to provided by Client, T&C almost done waiting for some items which require Shutdown by SE TCC received in on 14-July with certificate date 12-March-2026
110 | PE-298 | 132KV JCDPI- Jazan SS ¦ RC | 2024-05-21 | 99.72% | 97.85% | SEC | Southern | Jizan |  | Approved | 2026-02-10 | 2026-09-17 | 2026-11-19 | 2026-03-12 | 2026-10-17 | 2026-12-26 | 2026-05-20 | 2026-12-17 | 2027-03-04 | Working now on T&C and expected to be finished by Sep-26
111 | PE-297 | Battery Energy Storage for BISHA | 2024-02-05 | 100% | 99.96% | SEC | Southern | Al Baha |  | N/A | 2025-01-05 | 2025-01-05 | 2025-02-10 | 2025-03-05 | 2025-03-05 | 2026-07-15 | 2025-06-05 | 2025-06-05 | 2026-10-15 | SEC Reject descoping spare part scope
112 | PE-311 | New Samtah-PV 380/132kV BSP & OHTL | 2024-10-02 | 99.83% | 88.07% | SEC | Southern | Jizan |  | Under Approval | 2026-05-02 | 2026-05-02 | 2026-10-28 | 2026-07-02 | 2026-07-02 | 2026-12-27 | 2026-10-02 | 2026-10-02 | 2027-03-27 | Delay OHTL Road Crossing special towers approval ,Delay in lapp insulator FAT , Delay in SP tower procurement
113 | PE-313 | New Dhahyah 380/132/13.8KV BSP | 2024-04-25 | 86.78% | 89.42% | SEC | Southern | Jizan |  | Approved | 2026-01-25 | 2026-12-24 | 2026-10-30 | 2026-03-25 | 2027-02-25 | 2026-12-30 | 2026-06-25 | 2027-05-25 | 2027-03-30 | Delay in delivery of main materials 132KV GIS, 132 Power transformers and CTs (all delivered on May-26), working on internal crashed plan to energize by end of Oct-2026
114 | PE-320 | Aqabah (PS-AQB) 380/132/13.8KV | 2025-03-06 | On Hold |  | SEC | Southern | Abha |  | N/A | 2026-09-10: Contract Not Signed (2Y From Signing Contract) | -
115 | PE-325 | Construction of New SS for Darb-PV | 2024-10-02 | 99.97% | 85.3% | SEC | Southern | Abha |  | N/A | 2026-05-02 | 2026-05-02 | 2026-12-30 | 2026-07-02 | 2026-07-02 | 2027-02-13 | 2026-10-02 | 2026-10-02 | 2027-05-14 | Delay in OHTL change order , Delay in Civil design , Delay in AES material delivery , Delay in construction work. after new plan for OHTL Expected TCC Date is 15-Dec-26
116 | PE-327 | 132KV OHTL & UGC Najran | 2024-10-24 | 99.99% | 75.07% | SEC | Southern | Najran |  | Under Approval | 2026-03-24 | 2026-03-24 | 2026-12-29 | 2026-07-02 | 2026-05-24 | 2027-02-28 | 2026-10-02 | 2026-08-24 | 2027-05-31 | 1. Incomplete delivery of Angle towers from SE Energya will hinder the commencement stringing works in Portion -3 (<30km) 2. Transposition tower technical submittals, design engineering, needs to be expidted for submission as PO created on 17-May-2026, impacts material testing & delivery delay 3.UG Cable Construction needs to be start as it delayed. 4. Balance 20% material follow up with SE is required to prevent the project from delay.
117 | PE-343 | Const. Albaha ¦ Add. Scope UG Cable | 2024-10-17 | 100% | 96.3% | SEC | Southern | Al Baha |  | Approved | 2024-07-24 | 2026-02-17 | 2025-07-24 | 2024-09-24 | 2026-04-16 | 2025-11-03 | 2024-11-24 | 2026-06-17 | 2026-08-24 | Delay in removal of existing utilities & blasting works for the remaining works
118 | PE-333 | NEW DHAHRAN ALJANOUB-2 SS | 2025-01-15 | 99.25% | 70.94% | SEC | Southern | Dhahran |  | Under Approval | 2026-07-15 | 2026-07-15 | 2026-12-16 | 2026-09-15 | 2026-09-15 | 2027-02-15 | 2026-12-15 | 2026-12-15 | 2027-05-16 | OHTL portion delayed due to change order and shutdown Huge Delay in Delivery of Power Transformer, SAS & Gantry
119 | PE-341 | EXP. THE EXISTING KHM, ABHE & BISHA | 2025-01-26 | 71% | 42% | SEC | Southern | Abha |  | Under Approval | 2026-12-26 | 2026-12-26 | 2027-05-01 | 2027-02-26 | 2027-02-26 | 2027-07-01 | 2027-05-26 | 2027-05-26 | 2027-10-01 | For Civil works : -Delay in Gatepasses issuance, working 5 days a week for risky civil activities. -Low Manpower deployment from FGC (Civil Subcontractor) side -GIS Building opennings design delay approval for bisha which delays GIS Modification works For Electrical Installation : -Delay delivery schedule from Hitachi for : (Reactors in Abha -Delayed FAT for GIS in bisha as it was planned on 4-Jun-26) -Delay fdelivery schedule from trench for (NGR - FS CT) -Delay delivery schedule from GE for HGIS (30-Sep-26) in Khamis and delay in FAT for LCC as it was planned to be on 19-May-268 (most critical)
120 | PE-340 | JIZAN OHTL ¦ 132 KV LINE | 2025-03-27 | 89.92% | 40.67% | SEC | Southern | Jizan |  | Under Approval | 2026-09-26 | 2026-09-26 | 2027-04-08 | 2026-12-26 | 2026-12-26 | 2027-07-08 | 2027-02-26 | 2027-02-26 | 2027-09-08 | 1.Delay in FAT conduction for GIS with variance 5 months than planned FAT date. 2.Delay in submission & approval of foundation design which is affecting start of foundation works. 3.Delay in submission & approval of full plan & profile. 4.Delay in access road & structure pad progress.
121 | PE-342 | Refurbishment of 132kV Najran East Substation in SOA & Refurbishment of 132/33 kV Salwah Substation in SOA. | 2025-04-17 | 86.27% | 31.48% | SEC | Southern | Najran |  | N/A | 2026-10-17 | 2026-10-17 | 2027-06-21 | 2026-12-17 | 2026-12-17 | 2027-08-15 | 2027-03-17 | 2027-03-17 | 2027-11-14 | 1- Delay of start manufacturing of Protection 2- PO of Batteries & Battery Chargers issued with long Manufacturing Duration (35 weeks) 3- Delay in shifting live MV cables to start construction activities 4- Delay in site handing over
122 | PE-330 | Construction of OTOUD (Khamis South-2) 132/13.8KV SS & Interconnections in Asir Region SOA | 2025-06-29 | 56.27% | 29.18% | SEC | Southern | KHM |  | N/A | 2026-12-29 | 2026-12-29 | 2027-10-16 | 2027-02-28 | 2027-02-28 | 2027-12-09 | 2027-05-29 | 2027-05-29 | 2028-03-01 | *Long Manufacturing Duration of Power Transformers (SPTC) due to Non-Unified Design *Delay in All UGC Scope due to Municipality Permit Rejection for Single Circuit and Design Submittal for Double Circuit *Civil Readiness Delay due to Delayed Municipality Permits and Improper Store Location at Site
123 | PE-278 | Construction 132kv OHTL between baish west and ss1a at Jazan economic city in Jazan region-SOA | 2025-08-14 | 75.54% | 50.58% | SEC | Southern | Jizan |  | N/A | 2027-02-13 | 2027-02-13 | 2027-01-14 | 2027-05-13 | 2027-05-13 | 2027-04-14 | 2027-07-13 | 2027-07-13 | 2027-06-13 | 1.Delay in access road & structure pads works. 2. Delay in GAFM for Gantry Structure material 3.Delay in GAFM for Protection 4. Delay in delivery of Tower structure Material 5. Dealy in PO issuance for Earthing & Bonding cables
124 | PE-222 | PE-222: Najran DRPC | 2021-01-04 | 100% | 100% | SEC | Southern | Najran |  | N/A | 2023-03-03 | 2023-03-03 | 2024-09-30 | 2023-05-03 | 2023-05-03 | 2024-11-30 | 2023-07-03 | 2023-07-03 | 2025-01-30 | -
125 | PE-230 | PE-230: Wadi Eldawasser | 2021-07-15 | 100% | 100% | SEC | Southern | Wadi Eldawasser |  | N/A | 2023-01-15 | 2023-01-15 | 2024-06-20 | 2023-02-15 | 2023-02-15 | 2024-10-31 | 2023-03-15 | 2023-03-15 | 2025-03-31 | -
126 | PE-237 | PE-237: Al BAHA | 2022-01-25 | 100% | 99.55% | SEC | Southern | ALBAHA |  | N/A | 2024-07-24 | 2024-07-24 | 2025-09-09 | 2024-09-24 | 2024-09-24 | 2025-12-31 | 2024-11-24 | 2024-11-24 | 2026-06-17 | -
127 | PE-234 | PE-234: Najran-2 | 2022-01-18 | 100% | 98.36% | SEC | Southern | Najran |  | Approved | 2023-07-17 | 2026-11-17 | 2025-12-30 | 2023-10-17 | 2027-02-17 | 2026-06-15 | 2024-01-17 | 2027-05-17 | 2026-08-30 | shutdown received and work ongoing for the works during shutdown
128 | PE-236 | PE-236: New Sharorah | 2022-01-18 | 100% | 99.9% | SEC | Southern | Sharorah |  | N/A | 2023-07-17 | 2023-07-17 | 2024-01-17 | 2023-10-17 | 2023-10-17 | 2025-12-15 | 2024-01-17 | 2024-01-17 | 2025-12-30 | -
129 | PE-318 | HVDC-3 ¦ COA-SOA ¦ KUDMI | 2024-06-27 | 56.24% | 56.26% | SEC | Southern | jazan |  | N/A | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-02-28 | 2027-02-28 | 2027-02-28 | 2027-05-31 | 2027-05-31 | 2027-05-31 | -
130 | PE-321 | 380kV OHTL Between 1A BSP & Kudmi BSP (Approx. 47Km)¦ JCPDI P-4007 1A | 2025-10-27 | 69.88% | 29.35% | RC | Southern | Jizan |  | N/A | 2028-08-24 | 2028-08-24 | 2027-04-28 | 2028-09-23 | 2028-09-23 | 2028-09-23 | 2028-10-26 | 2028-10-26 | 2028-10-26 | - Plan & Profile submission & Approval delayed. - Foundation design drawing submission delayed due to Geo-tech soil investigation on going. - Access road and structure PAD works on hold due to trees cutting/NCEC permit. - Delay in Delivery of Insulator by Mar-27
131 | PE-322 | Design and construction of a buried cable to feed the industrial area | 2025-11-27 | 32.06% | 18.97% | RC | Southern | Jizan |  | N/A | 2027-08-18 | 2027-08-18 | 2027-04-25 | 2027-01-21 | 2027-01-11 | 2027-05-06 | 2027-03-15 | 2027-03-31 | 2028-08-01 | .Key Rout plan approval finilaiz & need to expdite reamining material POs & Power cable Manfufacturing
132 | PE-323 | Design & Construction of Electricity Substation 5E - Residential Area 132KV GIS + UGC | L1 |  |  | - | Southern | - |  | N/A | [9 empty] | -
133 | PE-358 | Power supply to Saad water facility Project (new 132 kV substation project) | L1 |  |  | - | Southern | - |  | N/A | [9 empty] | -
134 | PE-364 | PE364 - 380KV OHTL HDN-2 & BAHA BSP | 2025-10-15 | 62.35% | 47.59% | SEC | Southern | TAIF - BAHA |  | N/A | 2027-04-15 | 2027-04-15 | 2027-08-15 | 2027-06-15 | 2027-06-15 | 2027-10-15 | 2027-09-15 | 2027-09-15 | 2028-01-15 | - Contract Amendment of Rerouting Received 19-Aug that will require Change Order & Impact on time and cost. - On-Hold shipping for the Insulators & Hardware due to the additional shipping cost imposed by the vendor is impacting stringing start by Oct-26. - Manpower shortage for Assembly / Erection works impacting the site productivity. - Delayed finalization of Stringing Subcontractor, impacting the readiness for stringing activities by Oct-26 - Delayed concreting readiness in the western area due to the availability of a batching plant (First, under relocation / Second, PO under finalization)
135 | PE-374 | 132KV Ad Dayir SS | 2026-01-08 | 27% | 14% | SEC | Southern | Jizan |  | N/A | 2027-07-08 | 2027-07-08 | 2027-09-01 | 2027-09-08 | 2027-09-08 | 2027-11-01 | 2027-12-08 | 2027-12-08 | 2028-02-01 | -Delay in mobilization and site works as site handover given on 12-Feb-26 -Delay in RFM for protection,SST, HV Cables, and MV Cables due to delay in design submission from AES for SST & Protection -Delay in power source identification for auxiliary transformers which delay relocation of existing transformers and delays excavation works for the main building -Delay in precast supplier confirmation as for using precast slap or cast in situ, due to hard access to the site as it is on a mountainous area which will hinder supplying of precast slap. late confirmation impacts civil design and civil works. -Delay in manpower supplier prequalification approval for civil works -GIS GAFM released 1.5 months later than planned and no manufacturing schedule received yet from siemens
136 | PE-375 | 132KV Ayban SS | 2025-12-09 | 40.22% | 19.8% | SEC | Southern | Jizan |  | N/A | 2027-06-09 | 2027-06-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-10-09 | 2027-11-09 | 2027-11-09 | 2028-01-09 | Presence of existing feeders, dead Gantry structures and cables causing delay in start of excavation
137 | PE-376 | 132KV Al-Haqu SS | L1 |  |  | - | Southern | - |  | N/A | [9 empty] | -
138 | PE-382 | REFURBISHMENT OF 132 KV ASIR CPS SUBSTATION IN SOUTHERN OPERATING AREA | L1 |  |  | SEC | Southern | - |  | N/A | [9 empty] | -
139 | PE-383 | CONVERT SAMAKH SUBSTATION TO A CONVENTIONAL SUBSTATION IN BISHA REGION-SOA | L1 |  |  | SEC | Southern | - |  | N/A | [9 empty] | -
140 | PE-390 | CONST. NEW AD‑DARB S/S 132/33KV | 2026-04-12 | 7.73% | 7.37% | SEC | Southern | Jizan |  | N/A | 2028-04-12 | 2028-04-12 | 2028-04-12 | 2028-06-12 | 2028-06-12 | 2028-06-12 | 2028-09-12 | 2028-09-12 | 2028-09-12 | -
141 | PE-392 | New 380KV Shunt Reactors at JRP 380KV SS & Abha 380KV BSP in SOA | L1 |  |  | SEC | Southern | Jizan |  | N/A
142 | PE-400 | 132KV OHTL BETWEEN SAMITAH PV AND MOKTARA SUBSTATION IN JAZAN– SOA | 2026-05-13 | 11.37% | 5.18% | SEC | Southern | Jizan |  | N/A | 2027-11-13 | 2027-11-13 | 2027-11-13 | 2028-01-13 | 2028-01-13 | 2028-01-13 | 2028-04-13 | 2028-04-13 | 2028-04-13 | -
|  | INFRA UNIT | [17 empty] | -
143 | PE-244 | Steel Factory - DOOSAN | 2022-04-28 | 99.97% | 96.52% | Doosan | Eastern | Ras Al Khair |  | N/A | 2025-01-16 | 2025-01-16 | 2025-04-30 | 2025-01-16 | 2025-01-16 | 2025-04-30 | 2025-01-16 | 2025-01-16 | 2025-04-30 | -
144 | PE-249 | NEOM Village NRC-11 | 2022-04-28 | 100% | 99.99% | AGD | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-19 | 2024-06-06 | 2024-06-06 | 2024-12-19 | -
145 | PE-250 | NEOM Village NRC-13 | 2022-04-28 | 100% | 99.99% | AGD | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-19 | 2024-06-06 | 2024-06-06 | 2024-12-19 | -
146 | PE-251 | NEOM Village NRC-17 | 2022-04-28 | 100% | 99.99% | AGD | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2024-12-15 | 2024-06-06 | 2024-06-06 | 2024-12-15 | -
147 | PE-252 | NEOM Village NRC-19 |  | 100% | 99.99% | AGD | Western | NEOM |  | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | 2024-07-21 | 2024-07-21 | 2024-12-15 | 2024-07-21 | 2024-07-21 | 2024-12-15 | -
148 | PE-253 | NEOM Village NRC-26 | 2022-11-20 | 100% | 99.99% | AGD | Western | NEOM |  | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | 2024-09-04 | 2024-09-04 | 2025-01-15 | 2024-09-04 | 2024-09-04 | 2025-01-15 | -
149 | PE-268 | SEVEN JIZAN Project | 2023-05-28 | 100% | 60.28% | SEVEN | Southern | Jizan |  | N/A | 2025-05-27 | 2025-05-27 | 2026-09-29 | 2025-05-27 | 2025-05-27 | 2026-09-29 | 2025-05-27 | 2025-05-27 | 2026-09-29 | -
150 | PE-269 | NEOM Community 1 expansion | 2023-06-01 | 100% | 100% | NEOM | Western | NEOM |  | N/A | 2024-04-04 | 2024-06-24 | 2025-05-15 | 2024-04-04 | 2024-06-24 | 2025-05-15 | 2024-04-04 | 2024-06-24 | 2025-05-15 | -
151 | PE-349 | SABGS - Phase IV Schools-Central | 2025-02-09 | 32.4% | 21.49% | Aramco | Eastern | Dammam |  | Under Approval | 2027-09-27 | 2027-09-27 | 2029-02-15 | 2027-10-17 | 2027-10-17 | 2029-03-06 | 2027-10-27 | 2027-10-27 | 2029-03-16 | -
152 | PE-350 | SABGS - Phase IV Schools-Southern | 2025-02-09 | 32.04% | 19.14% | Aramco | Eastern | Hofuf |  | N/A | 2027-09-27 | 2027-09-27 | 2028-01-29 | 2027-10-17 | 2027-10-17 | 2028-02-17 | 2027-10-27 | 2027-10-27 | 2028-03-05 | -
153 | PE-289 | SWRO Des. Plant ¦ Shoaibha PP | 2024-12-16 | 100% | 82.84% | SEC | Western | Shoaibha |  | Under Approval | 2026-05-16 | 2026-08-30 | 2026-09-30 | 2026-06-16 | 2026-09-30 | 2026-10-30 | 2027-06-16 | 2027-09-30 | 2027-10-30 | * Conditions Approval received TCC 30-Aug-26 *Neutralization Pit : SE to review and approve the required Variation Order * PO for Existing MV switchgear CT : Expedite the delivery of the CT *Outdoor Works Permit : approve 24h working outside the fence. Pipe and cable routing activities are delayed *Tank No. 3 Outage Required: Delay on tie-in works
154 | PE-293 | SWRO Des. Plant- Shuqaiq Power Plant | 2025-04-28 | 80.45% | 60.06% | SEC | Southern | Shuqaiq |  | N/A | 2026-10-26 | 2026-10-26 | 2026-12-15 | 2026-11-26 | 2026-11-26 | 2027-01-15 | 2026-11-26 | 2027-11-26 | 2028-01-15 | *Outdoor Works Permit : approve 24h working outside the fence *Conflict Regarding Chemical Bulk Storage Tanks: There exists a direct and material conflict between the two documents: Schedule B (Cl. 5.1.10) – Contractor to utilise existing bulk tanks; no new tanks required. Post-Bid Clarification (Point 2) – Contractor to supply new NaOH and H₂SO₄ bulk storage tanks with all associated equipment. * AES arabia Material Delivery: AES to officially confirm and expedite delivery dates no later than 20-Aug-26.
155 | PE-303 | Water Treatment Plant & Tank - Jeddah | 2025-03-19 | 100% | 70.55% | SEC | Western | Jeddah |  | Under Approval | 2026-05-20 | 2026-05-20 | 2026-10-30 | 2026-06-20 | 2026-06-20 | 2026-11-30 | 2027-06-20 | 2027-06-20 | 2027-11-30 | *Revised Schedule Submitted with TCC 30-Oct-26, Under SEC approval *Pipe and cable routing activities are currently slow due to pending outdoor work permits: SE to expedite the issuance of all required permits for outdoor works & Allow working 24h for outdoor works * NAOH Pipeline Hold: Finalize the pending technical decision to release the activity.
156 | PE-352 | Main Construction Work for Al Ahsa Entertainment Complex | 2025-05-01 | 11.44% | 11.89% | SEVEN | Eastern | Alahsa |  | N/A | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | 2027-10-28 | -
|  | MEP UNIT | [17 empty] | -
157 | EL-059 | Rehab & Development of Ohud Hospital | 2021-10-19 | 100% | 97.44% | MOH | Western | Madinah |  | Under Approval | 2024-04-18 | 2025-10-18 | 2026-08-31 | 2024-04-18 | 2025-10-18 | 2026-08-31 | 2024-04-18 | 2025-10-18 | 2026-08-31 | -
158 | EL-060 | CONST OF COLLEGE -Faculty of Science – Univ of Tabuk. | 2022-07-18 | 100% | 94.09% | University of Tabuk | Western | Tabuk - KSA. |  | Under Approval | 2024-01-09 | 2026-05-26 | 2026-08-15 | 2024-01-09 | 2026-05-26 | 2026-08-15 | 2024-01-09 | 2026-05-26 | 2026-08-15 | -
159 | EL-062 | Four Season Resort, Triple Bay, Amaala | 2023-08-31 | 100% | 98.71% | AMAALA | Western | Al Wajh |  | Under Approval | 2024-12-17 | 2025-08-30 | 2026-08-30 | 2024-12-17 | 2025-08-30 | 2026-08-30 | 2024-12-17 | 2025-08-30 | 2026-08-30 | -
160 | EL-063 | NEOM MEP ¦ NRC-11 | 2022-10-06 | 100% | 99.99% | Alfanar EC | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
161 | EL-064 | NEOM MEP ¦ NRC-13 | 2022-10-06 | 100% | 99.99% | Alfanar EC | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
162 | EL-065 | NEOM MEP ¦ NRC-17 | 2022-10-06 | 100% | 99.99% | Alfanar EC | Western | NEOM |  | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
163 | EL-066 | NEOM MEP ¦ NRC-19 | 2022-11-20 | 100% | 99.99% | Alfanar EC | Western | NEOM |  | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | 2024-07-21 | 2024-07-21 | 2025-12-31 | 2024-07-21 | 2024-07-21 | 2025-12-31 | -
164 | EL-067 | NEOM MEP ¦ NRC-26 | 2022-11-20 | 100% | 99.99% | Alfanar EC | Western | NEOM |  | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | 2024-09-04 | 2024-09-04 | 2025-12-31 | 2024-09-04 | 2024-09-04 | 2025-12-31 | -
165 | EL-068 | MEP Works for AMAALA YACHT CLUB | 2024-09-14 | 100% | 99.9% | AMAALA | Western | Al Wajh |  | N/A | 2025-02-27 | 2025-10-30 | 2026-07-31 | 2025-02-27 | 2025-10-30 | 2026-07-31 | 2025-02-27 | 2025-10-30 | 2026-07-31 | -
166 | EL-069 | NEOM - BMS FOR 5 VILLAGES | 2024-12-15 | 100% | 100% | ALFANAR - AGD | Western | NEOM |  | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
167 | EL-070 | ALFANAR HEALTH CARE - BIM SERVICE | 2024-12-05 | 100% | 100% | Alfanar Health Care | Western | Amaala |  | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
168 | EL-071 | NEOM Expansion - (PE-269 Project) | 2025-04-14 | 100% | 100% | Alfanar EC | Western | NEOM |  | N/A | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | 2025-05-31 | -
169 | EL-072 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 - MEP WORKS | 2025-05-15 | 96.02% | 74.75% | Alfanar EC | Central | Dhurma |  | N/A | 2026-04-23 | 2026-04-23 | 2026-09-14 | 2026-04-23 | 2026-04-23 | 2026-09-14 | 2026-04-23 | 2026-04-23 | 2026-09-14 | -
170 | EL-073 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 - MEP WORKS | 2025-05-15 | 95.29% | 67.57% | Alfanar EC | Central | Kharj |  | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
171 | EL-074 | HVDC-3 ¦ COA-SOA ¦ KUDMI - MEP WORKS | 2025-05-15 | 100% | 73.83% | Alfanar EC | Southern | Kudmi |  | N/A | 2026-10-29 | 2026-10-29 | 2026-11-22 | 2026-10-29 | 2026-10-29 | 2026-11-22 | 2026-10-29 | 2026-10-29 | 2026-11-22 | -
172 | EL-075 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 - MEP WORKS | 2025-05-15 | 100% | 76.64% | Alfanar EC | Western | Jeddah |  | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
173 | EL-076 | MEP WORKS FOR SEVEN - AL AHSA (Same as PE-352) | 2025-05-01 | 32.8% | 28.7% | SEVEN | Eastern | Alahsa |  | N/A | 2027-10-28 | 2027-10-28 | 2028-04-04 | 2027-10-28 | 2027-10-28 | 2028-04-04 | 2027-10-28 | 2027-10-28 | 2028-04-04 | -
174 | EL-077 | MEP WORKS Amaala Wellness | 2025-08-06 | 94% | 92% | AMAALA | Western | Al Wajh |  | N/A | 2025-12-31 | 2026-02-11 | 2026-08-31 | 2025-12-31 | 2026-02-11 | 2026-08-31 | 2025-12-31 | 2026-02-11 | 2026-08-31 | -
Formulas:
Forecast Date = [Forecast Date]+60
Forecast Date = [Forecast Date]+([Revised Date]-[PAC])
TCC = XLOOKUP([Project Code],'[1]03-Project Information'!$E:$E,'[1]03-Project Information'!AE:AE)
TCC = [TCC]
PAC = XLOOKUP([Project Code],'[1]03-Project Information'!$E:$E,'[1]03-Project Information'!AF:AF)
PAC = EDATE([TCC],2)
FAC = XLOOKUP([Project Code],'[1]03-Project Information'!$E:$E,'[1]03-Project Information'!AG:AG)
Revised Date = EDATE([PAC],3)
Revised Date = +EDATE([PAC],3)

## Updated Progress % + TCC
S.N. | Project Code | Project Name | Project Managers Name | Start Date | Planned % | Actual % | Var. | Client | Region | City | EOT STATUS (Submitted/Approved/Under Approval/ N/A) | TCC |  |  | Remarks
|  |  |  | Start Date | [7 empty] | Contract Date | Revised Date | Forecast Date | Remarks
CENTRAL REGION UNIT (BASIL ALHAKAMI)
1 | PE-215 | SMP - O&M 3 Yrs | Mohamed Sabri | 2022-04-01 | 100% | 100% | 0% | SEC | Central | Riyadh | Approved | 2024-05-30 | 2025-06-04 | 2025-06-04 | All certification Received
2 | PE-226 | KHASM-AL-AAN BSP | Amin El Sayed | 2021-06-03 | 100% | 86.3% | -13.7% | SEC | Central | Riyadh | Approved | 2023-02-03 | 2024-12-31 | 2027-01-24 | Partial TCC Received ¦ Project on Hold
3 | PM-223 | GASCO - 2 | Fathi Mohamed | 2021-06-21 | 100% | 99.91% | -0.09% | GASCO | Central | Riyadh | Approved | 2023-07-29 | 2025-03-31 | 2025-10-31 | Initial Handing over received
4 | PE-228 | SVC QASSIM -2 | Hany Kamal | 2021-09-05 | 100% | 99.28% | -0.72% | SEC | Central | Riyadh | Approved | 2023-11-05 | 2025-03-17 | 2025-03-17 | TCC Received.
5 | PE-233 | Tabarjal 380KV BSP Expn. | Malik Qarioutyee | 2021-12-12 | 100% | 99% | -1% | SEC | Central | Riyadh | Approved | 2023-12-12 | 2025-12-30 | 2026-07-30 | Partial TCC received on 16-Jan-24
6 | PE-245 | Hail OHTL | Rafa Awad Al Hassan | 2022-08-15 | 100% | 96.12% | -3.88% | SEC | Central | Riyadh | Approved | 2024-05-15 | 2024-12-30 | 2026-06-20 | One line Energizaed. Another line by 20-Jun-26. Change Order approval is critical
7 | PE-247 | RIYADH SEDRA-2 | Anas Derzy | 2022-09-29 | 100% | 99.1% | -0.9% | Roshn | Central | Riyadh | Under Approval | 2024-09-03 | 2024-09-03 | 2025-09-20 | Partial TCC received & 90% invoice approved
8 | PE-248 | PP10 Conv. | Rabei Mohamed Mohamed Attia Daoud | 2022-10-13 | 100% | 95.98% | -4.02% | SEC | Central | Riyadh | Approved | 2024-08-13 | 2025-12-27 | 2026-08-29 | TCC milestone achieved. Certification not receied. Punchlist Clearance is critical
9 | PE-255 | 380kv D/C OHTL LILO SAAD OHTL | Malik Al Qaryotee | 2022-10-23 | 91.21% | 75.62% | -15.59% | SEC | Central | Riyadh | Approved | 2023-12-23 | 2025-06-05 | 2026-12-30 | 1. Amendment for New circuit Arrangement at Tapping Point . 2. Outage requirements 3. Hardware fittings material for re-route portion
10 | PE-256 | Sudair PV 380KV BSP | Tariq Mahmoud Ali Alsheyab | 2022-11-02 | 100% | 79.02% | -20.98% | SEC | Central | Riyadh | Under Approval | 2024-09-02 | 2024-09-02 | 2026-10-30 | SS portion energized. Delay in Receiving Permit UGC works and inside PP9 works (MTO,LOA& ARAMCO Permits)
11 | PE-259 | WAAD AL SHAMAAL 380KV BSP | Muhannad Ibrahim Al Heh | 2022-11-06 | 100% | 96.98% | -3.02% | SEC | Central | Riyadh | Approved | 2024-11-15 | 2025-05-30 | 2026-11-30 | Paritally Energized on 09-Feb-26 ¦ Delay in receiving outage to enrgize CKT 2 Wind to Waad Alshamaal & Wind to TABARJAL energization (expected by Oct 26)
12 | PE-264 | TABARJAL-B 13213.8 KV S/S IN JOUF | Khalid Mohamed Aql | 2023-05-17 | 100% | 99.25% | -0.75% | SEC | Central | Riyadh | Approved | 2025-03-16 | 2025-06-30 | 2026-06-29 | 1.Total of four circuits are planned; two are scheduled for energization by June 2026. 2.SE confirmation is still pending for the remaining two circuits.
13 | PE-271 | AL-DAR AL-BAIDHA 132/13.8KV SUB | Hassan Ayloti | 2023-07-13 | 100% | 98.5% | -1.5% | SEC | Central | Riyadh | Approved | 2024-11-12 | 2026-02-28 | 2026-03-17 | Energized on 17-Mar-26 ¦ Other Circuit depends on Outage ¦ Expected - 31-Oct-26
14 | PE-272 | AL-MUNSIYAH 132/13.8KV SUB # 8273 | Mohamed El hag | 2023-07-13 | 100% | 96.46% | -3.54% | SEC | Central | Riyadh | Under Approval | 2024-11-13 | 2024-11-13 | 2026-09-07 | One Circuit Energized. Other Circuit depends on Outage ¦ Expected - 31-Oct-26
15 | PE-273 | ALMANFOHA 132/13.8KV SUB # 8138 | Mohamed El hag | 2023-07-12 | 100% | 98.6% | -1.4% | SEC | Central | Riyadh | Under Approval | 2024-11-12 | 2025-11-30 | 2025-11-30 | One Circuit Energized on 21-Dec-25
16 | PE-274 | NASIRIYAH 132/13.8KV SUB # 8154 | Omar Samman | 2023-07-12 | 100% | 92.7% | -7.3% | SEC | Central | Riyadh | Approved | 2024-11-12 | 2026-01-12 | 2025-12-31 | One Energized on 11-Feb-26. TCC received with dated 31-Dec-2025
17 | PE-275 | 380kV Diriyah Gate-2 BSP # 9080 | Amin El Sayed | 2023-11-16 | 52.38% | 46.27% | -6.11% | SEC | Central | Riyadh | Under Approval | 2025-11-16 | 2027-04-13 | 2027-06-09 | Progress based on Internal Baseline. 1-Delay in approval of water proofing VO & removal of loose material, which affects the construction works. 2- Negative Cash flow. 3-Claim Approval 201 Mn for prolongation & inflation costs. 4- Delivery for disconnector switch expected to be delayed.
18 | PE-276 | SHARAFIYAH 380 KV SS | Mohamed Sabri | 2023-08-01 | 100% | 94.51% | -5.49% | SEC | Central | Riyadh | Under Approval | 2025-02-01 | 2025-02-01 | 2026-06-10 | Partially Energized. 1.Taihan - Oil Joints 2.Design Approval - 6 Remote end ( 132 kV) 3.Gantry Foundation for Existing Substation 4.Unclear Shutdown schedule for Power and Communication link with all remote ends 5. Delay in Micro Trenching of FOC 25km
19 | PE-279 | AL-NAZEEM 132/13.8KV SS # 8271 | Nedal Alkhatib | 2023-07-24 | 100% | 93.04% | -6.96% | SEC | Central | Riyadh | Approved | 2024-11-23 | 2025-06-23 | 2026-12-31 | Commissioing on Hold due to non-readiness of UG Contractor
20 | PE-299 | Reinf of 132KV Network of Baqaa | Yousef AlMohtaseb | 2023-11-08 | 100% | 93.92% | -6.08% | SEC | Central | Riyadh | Approved | 2025-05-07 | 2025-11-20 | 2026-10-31 | 1.OHTL S/C & D/C crossing - Delay in HOT permits 2.Cutting point outage at TEE OFF location. 3.ERS System & TEE- OFF Tower Installation 4.Design Approval of Flood Protection
21 | PE-300 | 300 MVAR STATCOM | Ibrahim Jaradat | 2024-03-06 | 86.73% | 71.51% | -15.22% | SEC | Central | Riyadh | Under Approval | 2026-03-06 | 2026-09-06 | 2026-10-20 | 1.Delay in delivery of AES scope material. (delay in these materials ,impact the project completion ) 2.Delay in 380 kv insulator (Lapp) 3.New fire pump-Delivery (change order), 4.Delay in delivery of MV grounding transformer
22 | PE-306 | NEW AL-ARED 380/132KV BSP | Munther Elkhatib | 2023-10-19 | 100% | 95.38% | -4.62% | SEC | Central | Riyadh | Under Approval | 2025-04-19 | 2025-08-19 | 2026-06-30 | 1.Slow Punch list - Transformers ,GIS, AES 2.Delay in SEC UG Cable Vendor - New Line( Circuits 3 )
23 | PE-309 | Reliablity Enh.for SS of 9011 in Sudair | Mohsin Arshad | 2025-12-24 | 57.25% | 24.53% | -32.72% | SEC | Central | Riyadh | N/A | 2026-11-23 | 2026-11-23 | 2027-04-21 | Current issues 1.Delay in Plan & Profile - OHTL 2.Delay in Plan & Profile - UG Cable ( T- off Tower Location) 3.Delay in SE supply GIS Bays 4.Delay in Material :- Tower, Hardware, Insulator 5. Delay in providing existing Design : Remote End, U/G 8500 to 8521, Basement & Sleeves Details, Telecom Room, Control Room Layouts 6.Delay in Mobilization of Project Team OHTL Site Engr & Project Engr, QA & QC Civil & Electrical 7. Unclear Shutdown for Project
24 | PE-310 | Al Shifa Housing 132/13.8KV SS | Meshari Alqarni | 2024-01-22 | 95.37% | 87.66% | -7.71% | SEC | Central | Riyadh | Under Approval | 2025-11-22 | 2026-06-21 | 2026-08-17 | 1.Incomplete HV underground cable works under another contractor’s scope are impacting the substation energization activities. 2.STATCOM PQS approval remains pending with SEC/vendor, affecting material delivery and subsequent installation. 3.Delay in remote end (8131) works due to pending C1 work permit
25 | PE-326 | Shaqra Wind 380/132kV SS | Ahmed Mosaad Abdel Nabi Hussein | 2024-10-24 | 100% | 72.04% | -27.96% | SEC | Central | Riyadh | N/A | 2026-05-23 | 2026-05-23 | 2026-12-31 | 1-Delay in the delivery of 132kV and 380kV GIB and Hybrid GIS (SEC Direct purchase) beyond the scheduled dates, where the original plan was December 2025; however, only the 132kV GIB was delivered in end of May 2026, while the 380kV GIB and Hybrid GIS are still pending. 2-Delay in the supply of AC and DC panels from AES up to date. 3- Delay in obtaining ITP approvals for DSM and TFR systems AES prequalification to perform the FAT in AES factory. 4-Change order confirmation for the additional scope , which holding following activities (Civil work for Search facilities - Guard house - security building and along with all septic tank and water connections , HCIS stage 3 finalization and approval , Procurement of all electrical , mechanical , security material related to this pending . 5-Delay in the approval of firefighting system designs due to changing multiple changes in the review process from SEC and adding new comments with each revision. 6- After approval of lightening panels design (MS Hawaa ) SEC insist to change the manufactural to new alternate as (MS hawaa )is currently suspended in the system 7- Confirmation of EOT which submitted 9-Apr-26.
26 | PE-335 | Battery Energy (BESS) - Qaisumah | Tariq Mahmoud Ali Alsheyab | 2024-12-16 | 100% | 98.26% | -1.74% | SEC | Central | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-11 | Energized.
27 | PE-336 | Battery Energy (BESS) - Dawadmi | Mohamed Ahmed Abdellatif Abdelkader | 2024-12-16 | 100% | 98% | -2% | SEC | Central | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | Energized.
28 | PE-337 | Battery Energy (BESS) - Airport | Tarig Mohammed | 2024-12-16 | 100% | 98.7% | -1.3% | SEC | Central | Riyadh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-06 | Energized.
29 | PE-339 | Battery Energy (BESS) - Jouf | Khalid Mohamed Aql | 2024-12-16 | 100% | 100% | 0% | SEC | Central | Jouf | N/A | 2026-05-16 | 2026-05-16 | 2026-05-16 | Energized.
30 | PE-348 | Construction of Hail-2 Substation for BESS | Muhannad Ibrahim Al Heh | 2025-07-03 | 98.68% | 70.74% | -27.94% | SEC | Central | Hail | N/A | 2026-06-03 | 2026-06-03 | 2026-09-15 | 1-Delay in approving critical designs such as FF designs, & Remote end AMI , with some submittals open for more than 3 months 2- Delay in design inputs has delayed grid studies submission & approval cycles 3- Delay in Alfanar equipment delivery: - Auxiliary transformer - AC & DC Panels - TFR & DSM - Remote End AMI & Metering 4- Delay in BESS Supplier fire fighting protion delivery (BESS gas pipes) 5- Delay in Firefighting pumps delivery 6- Delay in surge arrestors, and post insulators delivery 7- Delay in 33Kv SWGR termination kits delivery 8- Delay in HGIS Delivery: 1 out of 2 Bays delivered 9- Delay in UPS delivery
31 | PE-353 | Conv of Riyadh CC PP10 - Phase 2 | Muhannad Badawi | 2025-05-08 | 50.02% | 18.68% | -31.34% | SEC | Central | Riyadh | N/A | 2027-05-08 | 2027-05-08 | 2028-01-13 | 1.Base Design Approval : Disagreement with SE on interpretation of the Contract. 2.Engineering Review Cycle Delays : Agreed timelines for review are not being adhered. 3.Delivery durations for critical (LLIs) exceed the Contractual timeline, creating a significant risk to meeting the contractual milestones. 4.Accelerated Dec 2026 completion requested by SE for GT 1st Fire. 5.Site Access Gate Permits & Work Permit issues.
32 | PE-356 | 380KV OHTL ¦ MAWQAQ BSP CONNECTION | Omar Samman | 2025-08-28 | 36.12% | 13.33% | -22.79% | SEC | Central | Riyadh | N/A | 2027-02-28 | 2027-02-28 | 2027-12-02 | 1) Revised Route with additional change order.Revised Route under approval 2) Finalization of the route is pending for the portion that falls under KSRR. 3) Cost and time impact resulting from the increased transmission line route length and associated scope changes. 4) Delay in approval of plan and profile
33 | PE-360 | SMP¦OPERATION & PROF. SERVICES (HES&HHU) | Hazem Mahmoud | 2025-07-15 | 91% | 91% | 0% | SEC | Central | Riyadh | N/A | 2026-07-14 | 2026-10-14 | 2026-10-14 | Extension of 1 quarter received
34 | PE-362 | 132KV SS ¦CONST. SPORTS BOULEVARD-RIYADH | Mirza Ikramullah | 2025-08-13 | 38.27% | 27.04% | -11.23% | SEC | Central | Riyadh | N/A | 2027-02-11 | 2027-02-11 | 2027-09-30 | Delay in Site Handing Over. Not handed over yet
35 | PE-316 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 | Mohamed Sabri | 2024-06-27 | 93.76% | 87.11% | -6.65% | SEC | Central | Riyadh | N/A | 2026-12-31 | 2026-12-31 | 2027-01-31 | -
36 | PE-317 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 | Mohamed Sabri | 2024-06-27 | 91.76% | 83.49% | -8.27% | SEC | Central | Riyadh | N/A | 2026-12-31 | 2026-12-31 | 2027-02-28 | -
37 | PE-363 | SULYBIAH SS 8823 132/33KV | Youssef Al Mohtaesab | 2026-01-25 | 7.18% | 4.97% | -2.21% | SEC | Central | Qassim | N/A | 2027-07-25 | 2027-07-25 | 2027-10-13 | 1. Delay in Receiving Design for GIS Package Supplied by SEC Vendor 2. Delay in soil investigation activities due to one corner of the substation located on farmland 3. Terminal compound 1 location changed 4. Repetition of soil investigation activities due to the client's rejection of the proposed vendor
38 | PE-372 | AL-DWADMI SS 8618 132/33KV | Mohamed Azhar | 2026-01-14 | 11.74% | 9.18% | -2.56% | SEC | Central | Riyadh | N/A | 2027-07-12 | 2027-07-12 | 2027-09-30 | 1. Delay in approval of GEL 2. Delay of Receiving Design for GIS Package Supplied by SEC (GIS Delivery delayed ) 3. Delay in municipality approval 4. Delay in Issuance Of P.O Transformer
39 | PE-394 | NEW AL-GHADIR SS#8237 132/33K | Rafa Awad Al Hassan | 2026-01-21 | 10.68% | 6.89% | -3.79% | SEC | Central | Riyadh | N/A | 2027-09-21 | 2027-09-21 | 2027-10-21 | -
40 | PE-395 | New Al- Wadi 132/13.8Kv substation #8224 and its Connection in Riyadh City | Osama Mahood | 2026-02-11 | 5.17% | 5.71% | 0.54% | SEC-COA | Central | Riyadh | N/A | 2027-10-11 | 2027-10-11 | 2027-11-04 | 1- Civil construction and related engineering/design activities suspended due to site cavities discovered after Soil investigation report. 2- Under Ground cables radar scanning & cable route layout submission.
EASTERN REGION UNIT (BASIL ALHAKAMI)
41 | PE-214 | UTHMANIYAH | Munther Alkhatib | 2020-02-23 | 100% | 99.98% | -0.0225% | Aramco | Eastern | Dammam | Approved | 2023-07-27 | 2024-11-30 | 2024-09-15 | All Certificates Recieved FAC not Not applicable/MCC
42 | PE-227 | Ibn zahr Expn. | Walid Khater | 2021-06-10 | 100% | 88.29% | -11.71% | SEC | Eastern | Dammam | Approved | 2022-09-10 | 2024-04-30 | 2026-11-05 | -
43 | PE-238 | SWCC ¦ BSP Portion | Sami Abdou Sayed Atta | 2022-05-23 | 100% | 98.17% | -1.828% | SWCC | Eastern | Jubail | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC
44 | PE-239 | SWCC ¦ Solar Package | Walid Khater | 2024-02-14 | 100% | 90.7% | -9.3% | SWCC | Eastern | Jubail | Under Approval | 2025-02-14 | 2025-02-14 | 2026-06-30 | -
45 | PE-277 | Thuqbah BSP 380/115KV | Mohammed Kutkut | 2023-10-19 | 98.83% | 96.61% | -2.219% | SEC | Eastern | Thuqbah | Approved | 2025-04-19 | 2026-05-31 | 2026-05-31 | -
46 | PE-288 | Repl. of Berry Gas Plant 230/115KV SS | Moath Ahmad Mahmoud Almousa | 2024-05-19 | 92.01% | 85.51% | -6.496% | SEC | Eastern | Jubail | Under Approval | 2026-01-19 | 2026-01-19 | 2026-10-10 | OHTL Portion after 11 months from SS which is shown here
47 | PE-302 | AL RAMES 380/115 KV BSP | Mohamed Ali Hafez Aman | 2023-10-19 | 99.47% | 99.27% | -0.2054% | SEC | Eastern | Dammam | Approved | 2025-04-19 | 2026-11-30 | 2026-05-31 | Expected TCC will be on 13 Dec 26 due to delay of FOC readiness (31 Aug 2026) / Disconnector Switch
48 | PE-334 | Ghazlan-3 BSP | Mahmoud Abdelaal | 2025-02-09 | 94.15% | 34.88% | -59.27% | SEC | Eastern | Ghazlan | Under Approval | 2026-07-09 | 2026-07-09 | 2027-04-23 | Planned % is based on orginal baseline however we have a submitted revised schedule showing 80% used for internal reporting
49 | PE-344 | Nariyah BSP | Mohamed Elhag | 2025-02-27 | 95.49% | 56.83% | -38.66% | SEC | Eastern | Nariyah | N/A | 2026-09-26 | 2026-09-26 | 2027-06-06 | Delayed due to the delivery of GIS equipment Delayed 2times 1st delay till 25-June-26 2nd Delay till 25-Aug-26
50 | PE-355 | Construction of King Saud Air Base Facilities | Mohammed Kutkut | 2025-08-10 | 17.57% | 12% | -5.57% | RSAF | Eastern | Haffr Albatan | N/A | 2027-08-10 | 2027-08-10 | 2027-09-27 | Only Scope Alfanar / There is no FAC only based on the 40 Months Completion
51 | PE-304 | 230/115kV SS ¦ JUBAIL SW REPLACEMENT | Munther Alkhatib | 2025-08-31 | 19.69% | 12.6% | -7.09% | SEC | Eastern | Jubail | N/A | 2027-08-31 | 2027-08-31 | 2028-04-27 | Delayed due to site accessibility issues and Water leakage incident
52 | PE-181 | EPC OF PRIMARY ELECTRICAL SUSBSTATION #3 | Sami Atta | 2020-02-23 | 100% | 100% | 0% | RC | Eastern | Ras Al Khair | Approved | 2021-12-30 | 2021-12-30 | 2021-12-22 | All Certificates Recieved
53 | PE-199 | SPARK 380/115/13.8KV BSP | Walid Ahmed Khater | 2018-12-01 | 100% | 100% | 0% | SEC | Eastern | Abqaiq | Approved | 2020-09-30 | 2020-09-30 | 2021-04-30 | All Certificates Recieved
54 | PE-213 | Construction Of Hawayah 380 KV S/S | Moath Ahmad Mahmoud Almousa | 2020-01-23 | 100% | 100% | 0% | SEC | Eastern | Huwyha | N/A | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Jul-22 UQA : 30-Apr-23 | HUW : 30-Sep-22 UQA :30-Aug-26 | P1: All Certificates Recieved P2: No Certificates Recieved
55 | PE-229 | Construction of Temporary Rail Line (CO project of PE-181) | Sami Atta | 0 | 100% | 100% | 0% | RC | Eastern | Ras Al Khair | Approved | NA | NA | NA | All Certificates Recieved
56 | PE-240 | JSWCC¦OHTL Package | Moath Ahmad Mahmoud Almousa | 2022-05-23 | 100% | 100% | 0% | SWCC | Eastern | Jubail | Under Approval | 2024-02-23 | 2024-02-23 | 2026-01-31 | PAC Partially Recieved Waiting for final approval of Time Extension on Etimad For FAC Pending on PE-238
57 | PE-366 | Qulayyib 380 kV BSP | Tarig Mohammed | 2026-04-01 | 6.743% | 3.998% | -2.745% | MGC-Mutlaq Al Gowairi Company | Eastern | Qulayyib Area | N/A | 2028-06-01 | 2028-06-01 | 2028-07-09 | -
58 | PE-354 | Construction of NEW VSC HVDC Overhead Transmission Line for EOA-COA Link 1 | Moath Ahmad Mahmoud Almousa | 2026-05-04 | 2.939% | 1.827% | -1.112% | SEC | Eastern | Nariyah | N/A | 2028-11-04 | 2028-11-04 | 2028-11-22 | -
WESTERN REGION UNIT (MOHAMMED ALBAZIE)
59 | PE-243 | Installation of Dynamic Reactive Power Compensation(DRPC) at Tabuk 380KV BSP | Shafqat Zia | 2022-05-19 | 100% | 100% | 0% | SEC | Western | Tabuk | N/A | 2024-07-19 | 2025-04-30 | 2025-04-30 | Energization done without TSC Panel, TCC received. Partial PAC (21-Jan-2026) also received; Balance PAC & FAC upon delivery of remaining TSC Panel; Alfanar requested for FAC invoice and under discussion with SEC.
60 | PE-241 | Expansion of Existing Yanbu Central (YCNT) | Zohaib Iqbal | 2022-02-06 | 100% | 98.9% | -1.1% | SEC | Western | Yanbu,Umluj& Alwajh | N/A | 2024-01-06 | 2024-09-30 | 2024-09-30 | PAC received, not yet energized due to SE shutdown issues for all the area
61 | PE-257 | Expansions of Existing MHD 380 KV BSP | Omar Samman | 2022-11-03 | 100% | 99.89% | -0.11% | SEC | Western | Madinah | N/A | 2024-05-03 | 2025-10-30 | 2025-12-30 | As-built drawings under SEC review & approval. FAC certification waiting from SE; Request for issuance of FAC / Commitment for Completion of Outstanding Work was submitted on 20-Jul-26.
62 | PE-258 | Taif East Governorate Project | Mahmoud Sobhy El Sayed | 2022-11-17 | 100% | 90% | -10% | SEC | Western | Taif | N/A | 2024-04-17 | 2024-12-17 | 2026-09-30 | 1. EOT-1 Approved upto 14-Dec-24, EOT-2 submitted on 12th Aug 25, TCC upto 17th Jun 26. (Under SEC Approval). EOT to be resubmitted. 2. SAS testing pending due to EWS V.O finalization and delivery (V.O) 3. OHTL Line readiness pending from SE, no clarity on readiness
63 | PE-270 | 110/13.8KV HARAZAT SUB JEDDAH | Muhammad Ilyas | 2023-07-13 | 100% | 98.41% | -1.59% | SEC | Western | Jeddah | N/A | 2024-11-13 | 2025-03-13 | 2025-07-29 | Remote End Works: 1. Installation of Telecom Panels completed, testing will be done, once line readiness from client. (Dependent on Line Readiness from Client) 2. Final Settings of Line Protection Panels. (Dependent on Line Readiness from Client) Punchlist & As built works are in progress, completion date 30-Sep-26. Punchlist:Total 309 nos, 295 Completed, 5 nos ready to close. Asbuilt: 90% completed.
64 | PE-290 | Fadelah 110/13.8KV SS - JEDDAH | Khaled Abdelaty Hassan Emara Shehata | 2023-07-24 | 100% | 98.42% | -1.58% | SEC | Western | Jeddah | N/A | 2024-11-24 | 2025-09-24 | 2025-06-26 | 1) Energization done with temporary line, (Permanent line readiness Dependent on Client). 2) AMI integration with WRCC. (Dependent on Line Readiness from Client). 3) Modon GIS extension bays (Shutdown -Relay setting ) 85% completed. Punchlist & As built works are in progress, completion date 30-Sep-26. Punch points : Out of 10, 2 completed, 3 ready to close. As built status: out of 12, 12 ready to close.
65 | PE-254 | HENAKIYAH BSP 380 KV | Mahmoud Sobhy El Sayed | 2022-10-27 | 100% | 100% | 0% | SEC | Western | Madinah | N/A | 2024-09-27 | 2024-12-31 | 2025-04-07 | FAC received
66 | PE-260 | Sanabel con.at Jeddah | Abdelazeem Morsy | 2022-12-29 | 100% | 97.5% | -2.5% | SEC | Western | Jeddah | Approved | 2024-10-29 | 2025-01-30 | 2025-12-01 | SAS Configuration and testing pending, due to AES team mobilization pending
67 | PE-262 | Reinf. of Thuwal Town KAUST 2 | Abdelazeem Morsy | 2022-12-29 | 100% | 96.96% | -3.04% | SEC | Western | Jeddah | Approved | 2024-08-29 | 2024-12-30 | 2025-12-01 | SAS Configuration and testing pending
68 | PE-296 | Waly Alahad-4 110/13.8KV SS | Moustafa Elkayyal | 2023-10-19 | 100% | 94.53% | -5.47% | SEC | Western | Makkah | N/A | 2025-02-19 | 2025-11-19 | 2025-11-19 | 1) Line readiness pending from SEC
69 | PE-281 | 110KV SS - KAEC-3 | Hossam Amin | 2024-05-30 | 100% | 99% | -1% | SEC | Western | Jeddah | N/A | 2025-11-30 | 2025-11-30 | 2025-11-30 | TCC, PAC Received. FAC Letter Submitted to Client
70 | PE-280 | 110KV SS - KAEC-2 | Hossam Amin | 2024-05-30 | 100% | 100% | 0% | SEC | Western | Jeddah | N/A | 2025-11-30 | 2025-11-30 | 2025-11-30 | FAC received
71 | PE-185 | NG Taif | Omar Samman | 2018-02-25 | 100% | 99.65% | -0.35% | NG | Western | Taif | Under Approval | NA | NA | NA | EOT: Contract amendment approved,PCC on 14th Jul 25, EOT-2 submitted on 4th Nov 25, with 8 months (PCC: 14th Mar 26), Under SEC approval 1) All cable ceiling end joints works replacing works in progress, expected compeltion by 30th May 26. 2) Remote end-1 final setting done, Remote end 2 final setting completion by 10th May. 3) HV Test and end to end test pending expected completion by 15th Jun and 30th Jun
72 | PE-267 | CONST KAR 380 110KV BSP | Bander Khalid Al Qalah | 2023-06-01 | 100% | 97.94% | -2.06% | Masar | Western | Makkah | Approved | 2025-05-31 | 2025-12-31 | 2025-12-31 | 1.Close loop test completed 2. HVAC Testing: Completed 3. FF & FA Testing: All testing is completed and Remaining Final testing with ISD is in progress. 4. C04 modification work will be started after Energization of C06 Feeder as per SEC instruction. This will required 2 months to complete the task. 5. TCC received 6. New Change Order (confrimed) i.e. Duct Bank for future Area.-Completed 7.End to end test in progress, Expected engization by Aug'26 end.
73 | PE-291 | HAMRA AL ASAD 110/13.8 KV SUB | Mohamed Omar | 2023-07-26 | 100% | 99.98% | -0.02% | SEC | Western | Madinah | Approved | 2024-11-26 | 2025-09-30 | 2026-05-21 | 1) TCC received on 21-May-26. PAC received on 30-Jul-26. (Energization done through the AZIZIA remote-end and TCC was obtained. Remaining interface works at the MICY remote end are ongoing and are expected to be completed by end of Aug 2026.) 2) Target is to energize both remaining feeders with remote end by 1st week of Sep. 2026
74 | PE-292 | Shoran-2 110/13.8 KV - Madinah | Mohamed Omar | 2023-07-24 | 100% | 99.25% | -0.75% | SEC | Western | Madinah | Under Approval | 2024-11-24 | 2024-11-24 | 2026-08-31 | 1) TCC is requested , still not issued. Readiness of UGC circuits have delayed energization of the substation and TCC issuance. 2) Expected energization by end of Aug. 2026 if the UGC Feeders passed ongoing Tests by Cable contractor.
75 | PE-315 | 110KV Salam Royal Palace | Ahmad Faisal | 2024-04-04 | 100% | 95.9% | -4.1% | SEC | Western | Jeddah | N/A | 2025-10-04 | 2025-10-04 | 2026-01-15 | 1) EOT-1 Submitted on 13th Aug 25, with TCC date on 23rd Jul 26. Under SEC approval 2) Energization actual date 15th Jan 26
76 | PE-246 | UM-AL-JOUD BSP | Bander Khalid Al Qalah | 2022-09-08 | 100% | 88.95% | -11.05% | SEC | Western | Makkah | Under Approval | 2023-11-08 | 2025-02-07 | 2026-08-30 | 1) EOT-2 submitted to client on 8th Jan 25, Revised TCC date confirmation is pending by SEC (Due to no clarity in readiness of remote end i.e. Fahya SS). EOT-2 resubmitted on 14-June-26 for Revised TCC on 31-July-27. Once approved, TCC letter will be submitted. 2) Remote end protection desing approval pending from SEC. Holding the procurement of loose material & modification work at remote end. 3) Protection scope for Fahya Substation is unknown: Due to which Design submission and approval for modification and procuring loose material is still not finalized 4) Restriction to work inside Rusifah Substation: No confirmation on Panel Installation is provided in Rusifah Substation due to limitations of space. Also, FOC cable pulling & termination inside SS is on hold. 5) Testing of Fiber & High Voltage cable is required to start. Waiting for SEC witness. 6) Shut down from SEC is required for Replacing Relay from Rushifah to Umaljoud. Still no clarity on shutdown also.
77 | PE-263 | MOWAIH PV 380/110V BSP | Mohammed Fathy | 2023-03-29 | 100% | 99% | -1% | SEC | Western | Taif | Under Approval | 2025-03-29 | 2025-10-31 | 2026-01-06 | EOT is submitted with TCC and was approved on 21st Apr 26 Energization done, and TCC was received on 21st Apr 26
78 | PE-265 | 110/33 KV ALMAHANI S/S IN TAIF | Mudasir Sheikh | 2023-05-14 | 100% | 92.3% | -7.7% | SEC | Western | Taif | Under Approval | 2025-01-14 | 2025-11-30 | 2026-10-30 | EOT: EOT submitted TCC upto 30-Nov-26. Under SEC approval. 1) delay in final setting approval for SWGR and Capacitor bank and line protection delaying open loop Tests 2) Delayed HV kit for GIS HV test (was scheduled by Jul-26) now rescheduled to 20-Aug-26 3) Delayed installations of the (HV Terminations, CSE, MV Terminations) pending subcontractor. (PO Under finalization with SCD) 4) Delayed open loop tests for the major equipment due to non-availability of SAS engineer. (Will be mobilized after Approval of final settings) 5) OHTL Line readinees (AL-mahani to MAHD), No clarity on the completion by other contractor.
79 | PE-266 | EXT. OF THE EXIS. THAGEF &ADAM | Sohaib Afdal | 2023-05-14 | 100% | 86.63% | -13.37% | SEC | Western | Taif | Under Approval | 2025-01-14 | 2025-10-14 | 2026-11-30 | EOT: EOT-2 submitted with TCC date of 27-Jul-26. (Under SEC Approval) 1) AES Control panel (Mosaic and Annciator) detail design still under approval & no clarity on FAT date. (expected by Sep-26). 2) Missing BCU units for ADAM LCC (Hyundai), Provided by AES (Purchased from SIEMENS) Delayed since Feb-26, Latest provided date by AES is by Oct-26 3) Loose materials are required from AES for Protection, LCC Panels. To be compatible with existing systems and proceed commissioning activities 4) Delayed delivery of the PC Workstation (EWS) and the PO is still under Finalization with SCD 4) No Clarity of OHTL Line readiness.
80 | PE-286 | SEC Smart Distribution Control Centre | Hany Kamal | 2024-07-25 | 98.31% | 90.21% | -8.1% | SEC | Western | Jeddah | N/A | 2026-07-25 | 2026-07-25 | 2026-12-31 | 1. SLD Submission for Downstream : CET/NARI Shortage on Manpower where current manpower is 28 and plan to be 39 by 31-Jul-26 , Target Completion Madinah : 05-Sep-26 , Jeddah :06-Oct-26 ,Makkah : 06-Oct-26 ,Abha :03-Sep-26 , Jizan : 16-Sep-26. 2. Abha ADMS System Crash: SLD NDesigner application crashed during implementation activities in Abha, resulting in delays to SLD preparation, submission, and validation activities. 3. Cyber Security Audit : Audit plan not yet Approved by SE and the PO (Third Party) has not been issued by NARI (affecting Cutover). The audit requires approximately 10 weeks after PO issuance. 4. NARI End-to-End Testing Team : A dedicated NARI team is required to focus exclusively on End-to-End testing activities. A total of nine engineers are expected to be mobilized by the 31 July 2026. 5. Delay in Telecom Panel Local Test for Remote End (MADINAH LDC). 6. Delay delivery of DWDM (PO issued to AES) – waiting the final confirmation for the recent traffic plan in Madina, Abha & Jizan. 7. All Submittal under review with FEC / HSSE. 8. Requirements from STC connectivity regarding IP Telephone (SIP) services. 9.1 ICT reviewer’s new comments regarding the passive scope and Beit Al Anzima rejection. 9.2 ICT rejected the material in Rev-02 although no comments were received in Rev-01. 9.3 The material has already been delivered and installed on site. 9.4 The ICT reviewer has been rejecting every submitted versions without providing any specific technical comments or justified reasons, Also rejecting both of the approved Design Consultant and the Contractor. This repeated rejection practice is causing significant delays to the project and directly impacting the implementation and activation of critical ICT services, including Internet connectivity, IP Telephony, and system integrations.
81 | PE-287 | Exp. of YCNT BSP for Power to Neom | Zohaib Iqbal | 2023-08-01 | 93.38% | 95.08% | 1.7% | NEOM / SEC | Western | Yanbu | N/A | 2026-12-01 | 2026-12-01 | 2026-12-01 | 1) 2 Nos GIS breakers damaged due to heavy wind (Fell down, no major damage), need to close the issues with GE Team, Breakers are sent to France Factory to get the repaired materials expected Repaired materials delivery by End of Sep-26. 2) HV Test Equipment delivery pending from GE, due to lack of equipment (Used for other site)
82 | PE-294 | Airport C (KAIA) Interconnection REINF. | Mudasir Sheikh | 2023-11-01 | 100% | 83.99% | -16.01% | SEC | Western | Jeddah | N/A | 2026-02-01 | 2026-02-01 | 2026-02-01 | 1) TCC Received on 09-Aug-26 as per Contractual TCC Date i.e. 01-Feb-26. 2) Remaining work cannot be proceeded due to HV Cable issue from SE. Project currently onhold from SE so manpower to be demobilized accordingly. 3) CSD refused to start T&C Activities because of the unavailability of existing HV cable from SE. 4) Change order (Approx.. 47 million) submitted to SE for additional HV cable work. Waiting for their approval.
83 | PE-295 | Interconnection of AJM-1 (New Jamoom) | Abdelazeem Morsy | 2024-01-08 | 100% | 90.52% | -9.48% | SEC | Western | Makkah | N/A | 2026-04-08 | 2026-04-08 | 2026-04-08 | 1) T.C.C received. 2)Shutdown required for Connecting existing GIS to new GIS bay, expected in Aug-26.
84 | PE-301 | Expansion of Mowaih PV 380kV BSP | Ahmed Aboelseoud | 2024-09-16 | 100% | 89% | -11% | SEC | Western | Mowaih | Under Approval | 2025-10-16 | 2025-10-16 | 2026-08-30 | 1) EOT-1 submitted on 16th Oct 25, with TCC Date on 27-5-26. Rejected by SEC on 21-Oct-25, Resubmitted, under approval with SE. 2) TCC delayed by SE, Due to SE-MOD time extension approval 2) 48 V DC system: FAT done delivery delayed expected delivery in Sep-26 3) Remote End Substations are not ready
85 | PE-305 | 110kV SS Kar-2 | Bander Khalid Al Qalah | 2024-08-28 | 93% | 90% | -3% | Masar | Western | Makkah | Under Approval | 2026-04-27 | 2026-10-28 | 2026-10-28 | 1) Delay in Mechanical materials i.e. HVAC system (PACU), Expected material delivery by Mid Aug-26 due to current Geo-political instability.
86 | PE-307 | 132/13.8KV Sub Industrial City Tabuk | Shafqat Zia | 2024-01-30 | 98.06% | 98.31% | 0.25% | MODON | Western | Tabuk | N/A | NA | NA | NA | Critical Issues: OLT & CLT Completed and final testing like trip test, end to end test ongoing. However, PAC form signed after mutual site visit from SE, MODON & Alfanar. All pending works to be completed to target energization.
87 | PE-308 | 110KV Salam Royal | Ahmed Faizal | 2026-05-11 | 10.02% | 19.33% | 9.31% | SEC | Western | Jeddah | N/A | 2027-11-10 | 2027-11-10 | 2027-11-10 | 1) Baldia Permit required to avoid any delay in civil activities. Discussion under process. 2) AES to expedite submission of remaining Telecom drawings & also to close SE comments for submitted drawings to avoid any delay in material delivery. 3) AES to expedite to close SE comments for Protection Relay List to avoid any delay in material delivery. Protection Detail Design to be submitted. 4) AES to expedite submission of Switchgear Detail Design.
88 | PE-312 | Const of Southern 380KV BSP ¦ Al Ula | Pervaiz Akbar | 2024-01-08 | 98.64% | 96.15% | -2.49% | SEC | Western | Al Ula | Under Approval | 2026-01-08 | 2026-06-30 | 2026-06-30 | 1) TCC received. 2) External road: Road marking 3) Testing 85% completed. 4)Finishing work and punch points in progress.
89 | PE-314 | Expansion of Tabuk BSP & Duba BSP | Shafqat Zia | 2024-01-14 | 92.23% | 91.98% | -0.25% | SEC | Western | Tabuk & Duba | Under Approval | 2026-01-14 | 2026-11-30 | 2026-11-30 | EOT: EOT approved with revised TCC date of 30-Nov-26. 1) Duba BSP: C5 Dia. SEC granted outage on 30-Apr-26. Dismantling of Reactor, dismantling civil foundation removal completed & construction of new foundation under progress & to be completed before 28-Sep-26. Energization as per revised TCC 30-Nov-26. 2) Tabuk BSP C02 Dia: Outage for bus-bar coupling submitted to SE, however SE informed outage will not be received during current season due to peak load. Expected outage will be around Sep’26. Hence, TCC Request submitted to SE for C02 Dia & under review
90 | PE-319 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 | Khaled Abdelaty Hassan Emara Shehata | 2024-06-27 | 97.17% | 94.34% | -2.83% | SEC | Western | Jeddah | N/A | 2026-12-31 | 2026-12-31 | 2027-01-21 | 1) Remote end works. 2) Pole 1 & Pole 2 valve hall equipment installation. 3) Pending materials delivery (CET partial materials and FF Materials).
91 | PE-324 | Stage-2 HVDC OHTL COA-WOA | Ahmed Radwan | 2024-08-22 | 96.3% | 82% | -14.3% | SEC | Western | Jeddah | N/A | 2026-08-22 | 2026-12-31 | 2027-02-22 | 1) EOT has been submitted to SE on 07-Jul-26 with TCC date 22-Jan-27 under approval with SE. 2) Variation order for increase of Route length is in under approval stage with Rev TCC date 31-Dec-26. 3) Proposed FAT for remaining Combined Towers tentatively by 10-Aug which will affect TCC by 5 Months. 4) Delay in delivery of E & D SPL Tower material (Proposed date by supplier Nov-26). 5) The outage for the diversion scope is expected to occur in October 2026, which is expected to delay the TCC completion to Feb 2027.
92 | PE-329 | SEC ¦ 132KKV OHTL Tabuk | Mohan | 2024-11-05 | 99.5% | 94.93% | -4.57% | SEC | Western | Tabuk | Approved | 2026-04-05 | 2026-06-05 | 2026-08-02 | 1)TCC Received on 02-Aug-26 2)Acceleration in Mechanical works inside Tunnel Buhaira BSP 3) Acceleration in Access road & Structure Pad final layer
93 | PE-331 | UMM AL-QURA CEMENT OHTL | Sudhakar | 2024-11-05 | 100% | 74.55% | -25.45% | SEC | Western | Makkah | Under Approval | 2026-03-05 | 2026-03-05 | 2026-11-26 | 1)Slow Rate in Tower Erection & Stringing Works 2)Change order and EOT approvals to be expedited for new revised milestones.
94 | PE-332 | 110KV OHTL FOR MAADEN-AL MAHAD | Abdelazeem Morsy | 2024-12-22 | 99.83% | 69.36% | -30.47% | SEC | Western | Madinah | N/A | 2026-05-22 | 2026-05-22 | 2026-12-31 | 1) Revised EOT Submitted to SEC on 21-Jun-26 with TCC date 10-Mar-27 under approval with SEC 2) SE notified of Required route deviation due to future plans for a factory, required reworks (Dismantling of erected towers) & additional qty. 3) Foundation concrete works delayed due to late delivery of concrete. 4) Angle Towers erection should expedite to avoid further delay in stringing works 5) Delay in Commencement of Stringing works due to Tower shortage material
95 | PE-338 | Battery Energy (BESS) -Rabigh | Mohamed Elmazawy | 2024-12-16 | 100% | 98.67% | -1.33% | SEC | Western | Rabigh | N/A | 2026-05-16 | 2026-05-16 | 2026-05-10 | Energization done
96 | PE-345 | Arafat SS | Mostafa Ayop | 2025-03-10 | 87.06% | 70.51% | -16.55% | SEC | Western | Makkah | N/A | 2026-09-10 | 2026-09-10 | 2026-11-10 | 1. EOT submitted on 20-May-26 with TCC upto 8-Oct-26, SE comments received on 4th Jun 26 need to be resubmit the EOT. 2. Shutdown required from SE by Oct-26.
97 | PE-347 | Construction of Tabuk Substation for BESS | Amin El sayed | 2025-07-03 | 100% | 75.42% | -24.58% | SEC | Western | Tabuk | N/A | 2026-06-03 | 2026-06-03 | 2026-09-08 | 1. Approval Detailed Design for switchgear, ACDB & PDMS 2. Delay in Delivering HGIS from Hitachi for second bay 3. Delay in Delivering for 125v DC System 4. Approval for FEED package 5. Delay in Inputs for Grid Studies from BYD 6. FAT confirmation for Auxiliary Transformer, Lighting Panels, ACDB, DSM, TFR 7. PDC Support required for approval of DSM & TFR. 8. AMI DESIGN APPROVAL 9. FIBER OPTIC ROUTE PLAN. 10. BASE DESIGN APPROVAL FOR TRANSFORMER. 11. DELIOVERY CONFRIATION OF FIRE PUMP MATERIAL
98 | PE-328 | CONSTRUCTION OF ALWESSAM TAIF 110/13.SKV SUBSTATION IN TAIF | Mostafa Elkayal | 2025-07-22 | 55.45% | 26.41% | -29.04% | SEC | Western | Taif | N/A | 2027-01-22 | 2027-01-22 | 2027-06-30 | 1) Delay notification sent to SEC, Due to delay in issuance of construction permit & delay in design (08 Months) 2) Steel binding work & formwork for Main Building wall in progress 3) Structural design approval needs to be expedited
99 | PE-368 | CONSTRUCTION OF A NEW 132/13.8KV SUBSTATION RABIAH TABUK (RBTBK) & ITS 132KV INTERCONNECTION IN TABUK | Shafqat Zia | 2025-09-11 | 35.83% | 31.3% | -4.53% | SEC | Western | Tabuk | N/A | 2027-03-11 | 2027-03-11 | 2027-08-11 | 1) Delay in commencement of OHTL works due to SE E&DD's new requirements and involvement of SE S&SD. 2) Power Transformer delivery requires advancement by at least two months to meet the energization target. The supplier is not agreeing to/confirming the expected FAT and delivery dates before Dec-26. Due to the current global situation, the supplier has indicated that the FAT/delivery may be delayed until Jan./Feb. 2027. 3) Delay in submission and approval of Remote End design and drawings due to delay from SE in providing the existing data. 4) OHTL Line Strings have a long delivery lead time, and SE has been requested to provide the material on a borrowing basis from the SE store, subject to availability. 5) Delay in OHTL Tower works.
100 | PE-369 | CONSTRUCTION OF A NEW 110/13.8 kV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammad Ilyas | 2025-10-07 | 38.26% | 22.91% | -15.35% | SEC | Western | Taif | N/A | 2027-04-07 | 2027-04-07 | 2027-07-05 | 1) Construction Sub Structure forecast completion date: 23-Sep-26. 2) Construction Super Structure forecast completion date: 26-Nov-26.
101 | PE-346 | Installation of New STATCOM ±300MV AR At 132kV Level At Northern BSP | Pervaiz Akbar | 2025-10-29 | 20.02% | 14.51% | -5.51% | SEC | Western | Al Ula | N/A | 2028-07-29 | 2028-07-29 | 2028-05-10 | 1) Vendor finalization is pending for Lightning Protection, HVAC, and Cable Trays; respective design approvals/offers are under process. DPOs for Post Insulator and Crane are with SCD. 2) STATCOM Building foundation works are delayed due to delay in finalization of the STATCOM Building Architectural & Precast drawings (inputs) by the designer (DAR).
102 | PE-359 | CONSTRUCTION OF A NEW 110KV D/C OHTL FOR A NEW 110/13.8KV SUBSTATION Al-Arfa (ARFA-G) IN TAIF UNDER GRANT SCHEMES PROGRAM | Muhammad Ilyas | 2025-10-16 | 51.21% | 19.83% | -31.38% | SEC | Western | Taif | N/A | 2027-03-16 | 2027-03-16 | 2027-07-16 | 1) Delay in GAFM for Insulator. 2) Delay in GAFM for Hardware Fittings. 3) Delay in Soil investigation and Foundation work Design.
103 | PE-365 | CONSTRUCTION OF A NEW SUBSTATION KHR-1 380/110 KV BSP & EXP OF EXISTING MHR BSP UNDER RENEWABLE ENERGY | Ahmed Abdel Hady Sayed | 2025-10-29 | 25.81% | 25.83% | 0.02% | SEC | Western | Taif | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 1) P.O issued for GIS in expansion scope to Hitachi,BD modified after site visit and proposal of reactor location and GIB routing under review 2) Reactors BD with tbea, trench china Bushing under sec review waiting confirmation of delivery date 3) Substructure 110kv building-2 not yet approved. 4) NGR P.O issuance pending due toNGR study
104 | PE-370 | CONSTRUCTION OF A NEW SUBSTATION KHR-2 380/110 KV BSP UNDER RENEWABLE ENERGY POWER PLANT (WOA) | Hossam Amin | 2025-10-29 | 25.85% | 25.5% | -0.35% | SEC | Western | Taif | N/A | 2027-07-29 | 2027-07-29 | 2027-07-29 | 1) Reactors BD with tbea, TEBA as unified desing with SEC, but now changed the BD format it will take one month to modify, it will impact GAFM issues and delivery - TBEA confirmed to deliver equipment within time limit of PO issued. 2) Control Room Building Slab completed
105 | PE-380 | AL JAMOOM 110/33/13.8KV SUBSTATION (Te3830) | Bander Khalid Al Qalah | 2026-01-15 | 2% | 1% | -1% | SEC | Western | Makkah | N/A | 2027-07-15 | 2027-07-15 | 2027-12-15 | 1) SE delayed in site hand over and still site co-ordinate not yet confirmed by SE. It will impact the design submission and site commencing works. 2) Delay in issuing BD for main equipment 3) Delay in engineering Phase
106 | PE-388 | CONSTRUCTION OF HENAKIYAH-3 PV |  | 2026-05-05 | 6.52% | 6.34% | -0.18% | SEC | Western | Madinah | N/A | 2028-05-05 | 2028-05-05 | 2028-05-05 | 1)BL submitted to SE for Approval 2) GLO Approval 3) delay in site office preparations and mobilization
SOUTHERN REGION UNIT (MOHAMMED ALBAZIE)
107 | PE-282 | 2X25 MVAR 33KV STATCOM | Ahmed Hussein | 2024-02-01 | 100% | 99.79% | -0.21% | SEC | Southern | Al Baha | Under Approval | 2025-10-01 | 2025-10-01 | 2026-01-29 | TCC Certificate Received, working on Punch list & As-Buildt ongoing
108 | PE-283 | Al-Kara 132/33 kV SS in Baha Region | Ahmed Hussein | 2023-11-12 | 100% | 96.57% | -3.43% | SEC | Southern | Al Baha | Under Approval | 2025-07-12 | 2025-07-12 | 2026-08-31 | Delayed in Delivery of GIS,Power Transformer,SIS,SAS, SWGR. Delayed in T&C part where Remote end provision is yet to provided by Client, T&C almost done waiting for some items which require Shutdown by SE
109 | PE-284 | Qilwah North 132-33kV SS in Tihama | Khawaja Fayyaz | 2023-11-12 | 100% | 96.28% | -3.72% | SEC | Southern | Al Baha | Under Approval | 2025-07-12 | 2026-03-12 | 2026-03-12 | Delayed in Delivery of GIS,Power Transformer,SIS,SAS, SWGR. Delayed in T&C part where Remote end provision is yet to provided by Client, T&C almost done waiting for some items which require Shutdown by SE TCC received in on 14-July with certificate date 12-March-2026
110 | PE-298 | 132KV JCDPI- Jazan SS ¦ RC | Nadim Shaikh | 2024-05-21 | 99.72% | 97.85% | -1.87% | SEC | Southern | Jizan | Approved | 2026-02-10 | 2026-09-17 | 2026-11-19 | Working now on T&C and expected to be finished by Sep-26
111 | PE-297 | Battery Energy Storage for BISHA | Ahmad Abdel Hady | 2024-02-05 | 100% | 99.96% | -0.04% | SEC | Southern | Al Baha | N/A | 2025-01-05 | 2025-01-05 | 2025-02-10 | SEC Reject descoping spare part scope
112 | PE-311 | New Samtah-PV 380/132kV BSP & OHTL | Amr Sennara | 2024-10-02 | 99.83% | 88.07% | -11.76% | SEC | Southern | Jizan | Under Approval | 2026-05-02 | 2026-05-02 | 2026-10-28 | Delay OHTL Road Crossing special towers approval ,Delay in lapp insulator FAT , Delay in SP tower procurement
113 | PE-313 | New Dhahyah 380/132/13.8KV BSP | Ahmed Sadek | 2024-04-25 | 86.78% | 89.42% | 2.64% | SEC | Southern | Jizan | Approved | 2026-01-25 | 2026-12-24 | 2026-10-30 | Delay in delivery of main materials 132KV GIS, 132 Power transformers and CTs (all delivered on May-26), working on internal crashed plan to energize by end of Oct-2026
114 | PE-320 | Aqabah (PS-AQB) 380/132/13.8KV | ON HOLD | 2025-03-06 | On Hold | 0% | #VALUE! | SEC | Southern | Abha | N/A | Contract Not Signed (2Y From Signing Contract) | 0 | 0 | -
115 | PE-325 | Construction of New SS for Darb-PV | Musab Ismail | 2024-10-02 | 99.97% | 85.3% | -14.67% | SEC | Southern | Abha | N/A | 2026-05-02 | 2026-05-02 | 2026-12-30 | Delay in OHTL change order , Delay in Civil design , Delay in AES material delivery , Delay in construction work. after new plan for OHTL Expected TCC Date is 15-Dec-26
116 | PE-327 | 132KV OHTL & UGC Najran | Ayman Elattar | 2024-10-24 | 99.99% | 75.07% | -24.92% | SEC | Southern | Najran | Under Approval | 2026-03-24 | 2026-03-24 | 2026-12-29 | 1. Incomplete delivery of Angle towers from SE Energya will hinder the commencement stringing works in Portion -3 (<30km) 2. Transposition tower technical submittals, design engineering, needs to be expidted for submission as PO created on 17-May-2026, impacts material testing & delivery delay 3.UG Cable Construction needs to be start as it delayed. 4. Balance 20% material follow up with SE is required to prevent the project from delay.
117 | PE-343 | Const. Albaha ¦ Add. Scope UG Cable | Hany Kamal Elsherbini | 2024-10-17 | 100% | 96.3% | -3.7% | SEC | Southern | Al Baha | Approved | 2024-07-24 | 2026-02-17 | 2025-07-24 | Delay in removal of existing utilities & blasting works for the remaining works
118 | PE-333 | NEW DHAHRAN ALJANOUB-2 SS | Mohammad Monawwar Eqbal | 2025-01-15 | 99.25% | 70.94% | -28.31% | SEC | Southern | Dhahran | Under Approval | 2026-07-15 | 2026-07-15 | 2026-12-16 | OHTL portion delayed due to change order and shutdown Huge Delay in Delivery of Power Transformer, SAS & Gantry
119 | PE-341 | EXP. THE EXISTING KHM, ABHE & BISHA | Shawkat Alrjoub | 2025-01-26 | 71% | 42% | -29% | SEC | Southern | Abha | Under Approval | 2026-12-26 | 2026-12-26 | 2027-05-01 | For Civil works : -Delay in Gatepasses issuance, working 5 days a week for risky civil activities. -Low Manpower deployment from FGC (Civil Subcontractor) side -GIS Building opennings design delay approval for bisha which delays GIS Modification works For Electrical Installation : -Delay delivery schedule from Hitachi for : (Reactors in Abha -Delayed FAT for GIS in bisha as it was planned on 4-Jun-26) -Delay fdelivery schedule from trench for (NGR - FS CT) -Delay delivery schedule from GE for HGIS (30-Sep-26) in Khamis and delay in FAT for LCC as it was planned to be on 19-May-268 (most critical)
120 | PE-340 | JIZAN OHTL ¦ 132 KV LINE | Amir Aboumansour | 2025-03-27 | 89.92% | 40.67% | -49.25% | SEC | Southern | Jizan | Under Approval | 2026-09-26 | 2026-09-26 | 2027-04-08 | 1.Delay in FAT conduction for GIS with variance 5 months than planned FAT date. 2.Delay in submission & approval of foundation design which is affecting start of foundation works. 3.Delay in submission & approval of full plan & profile. 4.Delay in access road & structure pad progress.
121 | PE-342 | Refurbishment of 132kV Najran East Substation in SOA & Refurbishment of 132/33 kV Salwah Substation in SOA. | Akram Kamal | 2025-04-17 | 86.27% | 31.48% | -54.79% | SEC | Southern | Najran | N/A | 2026-10-17 | 2026-10-17 | 2027-06-21 | 1- Delay of start manufacturing of Protection 2- PO of Batteries & Battery Chargers issued with long Manufacturing Duration (35 weeks) 3- Delay in shifting live MV cables to start construction activities 4- Delay in site handing over
122 | PE-330 | Construction of OTOUD (Khamis South-2) 132/13.8KV SS & Interconnections in Asir Region SOA | Ahmed Hussein | 2025-06-29 | 56.27% | 29.18% | -27.09% | SEC | Southern | KHM | N/A | 2026-12-29 | 2026-12-29 | 2027-10-16 | *Long Manufacturing Duration of Power Transformers (SPTC) due to Non-Unified Design *Delay in All UGC Scope due to Municipality Permit Rejection for Single Circuit and Design Submittal for Double Circuit *Civil Readiness Delay due to Delayed Municipality Permits and Improper Store Location at Site
123 | PE-278 | Construction 132kv OHTL between baish west and ss1a at Jazan economic city in Jazan region-SOA | Adil Bashir | 2025-08-14 | 75.54% | 50.58% | -24.96% | SEC | Southern | Jizan | N/A | 2027-02-13 | 2027-02-13 | 2027-01-14 | 1.Delay in access road & structure pads works. 2. Delay in GAFM for Gantry Structure material 3.Delay in GAFM for Protection 4. Delay in delivery of Tower structure Material 5. Dealy in PO issuance for Earthing & Bonding cables
124 | PE-222 | PE-222: Najran DRPC | Hany Kamal | 2021-01-04 | 100% | 100% | 0% | SEC | Southern | Najran | N/A | 2023-03-03 | 2023-03-03 | 2024-09-30 | -
125 | PE-230 | PE-230: Wadi Eldawasser | Hany Kamal | 2021-07-15 | 100% | 100% | 0% | SEC | Southern | Wadi Eldawasser | N/A | 2023-01-15 | 2023-01-15 | 2024-06-20 | -
126 | PE-237 | PE-237: Al BAHA | Hany Kamal | 2022-01-25 | 100% | 99.55% | -0.45% | SEC | Southern | ALBAHA | N/A | 2024-07-24 | 2024-07-24 | 2025-09-09 | -
127 | PE-234 | PE-234: Najran-2 | Ahmed Abdelhady | 2022-01-18 | 100% | 98.36% | -1.64% | SEC | Southern | Najran | Approved | 2023-07-17 | 2026-11-17 | 2025-12-30 | shutdown received and work ongoing for the works during shutdown
128 | PE-236 | PE-236: New Sharorah | Ahmed Abdelhady | 2022-01-18 | 100% | 99.9% | -0.1% | SEC | Southern | Sharorah | N/A | 2023-07-17 | 2023-07-17 | 2024-01-17 | -
129 | PE-318 | HVDC-3 ¦ COA-SOA ¦ KUDMI | Mohamed Sabri | 2024-06-27 | 56.24% | 56.26% | 0.02% | SEC | Southern | jazan | N/A | 2026-12-31 | 2026-12-31 | 2026-12-31 | -
130 | PE-321 | 380kV OHTL Between 1A BSP & Kudmi BSP (Approx. 47Km)¦ JCPDI P-4007 1A | Adil Bashir | 2025-10-27 | 69.88% | 29.35% | -40.53% | RC | Southern | Jizan | N/A | 2028-08-24 | 2028-08-24 | 2027-04-28 | - Plan & Profile submission & Approval delayed. - Foundation design drawing submission delayed due to Geo-tech soil investigation on going. - Access road and structure PAD works on hold due to trees cutting/NCEC permit. - Delay in Delivery of Insulator by Mar-27
131 | PE-322 | Design and construction of a buried cable to feed the industrial area | Nadim Shaikh | 2025-11-27 | 32.06% | 18.97% | -13.09% | RC | Southern | Jizan | N/A | 2027-08-18 | 2027-08-18 | 2027-04-25 | .Key Rout plan approval finilaiz & need to expdite reamining material POs & Power cable Manfufacturing
132 | PE-323 | Design & Construction of Electricity Substation 5E - Residential Area 132KV GIS + UGC | L1 | L1 | 0% | 0% | 0% | - | Southern | - | N/A | 0 | 0 | 0 | -
133 | PE-358 | Power supply to Saad water facility Project (new 132 kV substation project) | L1 | L1 | 0% | 0% | 0% | - | Southern | - | N/A | 0 | 0 | 0 | -
134 | PE-364 | PE364 - 380KV OHTL HDN-2 & BAHA BSP | Mohamed Eltohfa | 2025-10-15 | 62.35% | 47.59% | -14.76% | SEC | Southern | TAIF - BAHA | N/A | 2027-04-15 | 2027-04-15 | 2027-08-15 | - Contract Amendment of Rerouting Received 19-Aug that will require Change Order & Impact on time and cost. - On-Hold shipping for the Insulators & Hardware due to the additional shipping cost imposed by the vendor is impacting stringing start by Oct-26. - Manpower shortage for Assembly / Erection works impacting the site productivity. - Delayed finalization of Stringing Subcontractor, impacting the readiness for stringing activities by Oct-26 - Delayed concreting readiness in the western area due to the availability of a batching plant (First, under relocation / Second, PO under finalization)
135 | PE-374 | 132KV Ad Dayir SS | Moazam Ali Sayed | 2026-01-08 | 27% | 14% | -13% | SEC | Southern | Jizan | N/A | 2027-07-08 | 2027-07-08 | 2027-09-01 | -Delay in mobilization and site works as site handover given on 12-Feb-26 -Delay in RFM for protection,SST, HV Cables, and MV Cables due to delay in design submission from AES for SST & Protection -Delay in power source identification for auxiliary transformers which delay relocation of existing transformers and delays excavation works for the main building -Delay in precast supplier confirmation as for using precast slap or cast in situ, due to hard access to the site as it is on a mountainous area which will hinder supplying of precast slap. late confirmation impacts civil design and civil works. -Delay in manpower supplier prequalification approval for civil works -GIS GAFM released 1.5 months later than planned and no manufacturing schedule received yet from siemens
136 | PE-375 | 132KV Ayban SS | Khawaja Fayyaz | 2025-12-09 | 40.22% | 19.8% | -20.42% | SEC | Southern | Jizan | N/A | 2027-06-09 | 2027-06-09 | 2027-08-09 | Presence of existing feeders, dead Gantry structures and cables causing delay in start of excavation
137 | PE-376 | 132KV Al-Haqu SS | L1 | L1 | 0% | 0% | 0% | - | Southern | - | N/A | 0 | 0 | 0 | -
138 | PE-382 | REFURBISHMENT OF 132 KV ASIR CPS SUBSTATION IN SOUTHERN OPERATING AREA | N/A | L1 | 0% | 0% | 0% | SEC | Southern | - | N/A | 0 | 0 | 0 | -
139 | PE-383 | CONVERT SAMAKH SUBSTATION TO A CONVENTIONAL SUBSTATION IN BISHA REGION-SOA | N/A | L1 | 0% | 0% | 0% | SEC | Southern | - | N/A | 0 | 0 | 0 | -
140 | PE-390 | CONST. NEW AD‑DARB S/S 132/33KV | N/A | 2026-04-12 | 7.73% | 7.37% | -0.36% | SEC | Southern | Jizan | N/A | 2028-04-12 | 2028-04-12 | 2028-04-12 | -
141 | PE-392 | New 380KV Shunt Reactors at JRP 380KV SS & Abha 380KV BSP in SOA | N/A | L1 | 0% | 0% | 0% | SEC | Southern | Jizan | N/A | 0 | 0 | 0 | 0
142 | PE-400 | 132KV OHTL BETWEEN SAMITAH PV AND MOKTARA SUBSTATION IN JAZAN– SOA | N/A | 2026-05-13 | 11.37% | 5.18% | -6.19% | SEC | Southern | Jizan | N/A | 2027-11-13 | 2027-11-13 | 2027-11-13 | -
INFRA UNIT (ALAA SAAD)
143 | PE-244 | Steel Factory - DOOSAN | Ahmed Shebl | 2022-04-28 | 99.97% | 96.52% | -3.45% | Doosan | Eastern | Ras Al Khair | N/A | 2025-01-16 | 2025-01-16 | 2025-04-30 | -
144 | PE-249 | NEOM Village NRC-11 | Kamran Ali | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
145 | PE-250 | NEOM Village NRC-13 | Mohammd Elshafie | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
146 | PE-251 | NEOM Village NRC-17 | Abdelhadi Abdulhalim Kassem | 2022-04-28 | 100% | 99.99% | -0.01% | AGD | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
147 | PE-252 | NEOM Village NRC-19 | Fahed Al Malki |  | 100% | 99.99% | -0.01% | AGD | Western | NEOM | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | -
148 | PE-253 | NEOM Village NRC-26 | Mohamed Shokry | 2022-11-20 | 100% | 99.99% | -0.01% | AGD | Western | NEOM | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | -
149 | PE-268 | SEVEN JIZAN Project | Khalid Khalil | 2023-05-28 | 100% | 60.28% | -39.72% | SEVEN | Southern | Jizan | N/A | 2025-05-27 | 2025-05-27 | 2026-09-29 | -
150 | PE-269 | NEOM Community 1 expansion | Mohammed Khurbush | 2023-06-01 | 100% | 100% | 0% | NEOM | Western | NEOM | N/A | 2024-04-04 | 2024-06-24 | 2025-05-15 | -
151 | PE-289 | SWRO Des. Plant ¦ Shoaibha PP | Fathi Mousa | 2024-12-16 | 100% | 82.84% | -17.16% | SEC | Western | Shoaibha | Under Approval | 2026-05-16 | 2026-08-30 | 2026-09-30 | * Conditions Approval received TCC 30-Aug-26 *Neutralization Pit : SE to review and approve the required Variation Order * PO for Existing MV switchgear CT : Expedite the delivery of the CT *Outdoor Works Permit : approve 24h working outside the fence. Pipe and cable routing activities are delayed *Tank No. 3 Outage Required: Delay on tie-in works
152 | PE-349 | SABGS - Phase IV Schools-Central | Ahmed Shebl | 2025-02-09 | 32.4% | 21.49% | -10.91% | Aramco | Eastern | Dammam | N/A | 2027-09-27 | 2027-09-27 | 2029-02-15 | -
153 | PE-350 | SABGS - Phase IV Schools-Southern | Ahmed Shebl | 2025-02-09 | 32.04% | 19.14% | -12.9% | Aramco | Eastern | Hofuf | N/A | 2027-09-27 | 2027-09-27 | 2028-01-29 | -
154 | PE-293 | SWRO Des. Plant- Shuqaiq Power Plant | Fathi Mousa | 2025-04-28 | 80.45% | 60.06% | -20.39% | SEC | Southern | Shuqaiq | N/A | 2026-10-26 | 2026-10-26 | 2026-12-15 | *Outdoor Works Permit : approve 24h working outside the fence *Conflict Regarding Chemical Bulk Storage Tanks: There exists a direct and material conflict between the two documents: Schedule B (Cl. 5.1.10) – Contractor to utilise existing bulk tanks; no new tanks required. Post-Bid Clarification (Point 2) – Contractor to supply new NaOH and H₂SO₄ bulk storage tanks with all associated equipment. * AES arabia Material Delivery: AES to officially confirm and expedite delivery dates no later than 20-Aug-26.
155 | PE-303 | Water Treatment Plant & Tank - Jeddah | Fathi Mousa | 2025-03-19 | 100% | 70.55% | -29.45% | SEC | Western | Jeddah | Under Approval | 2026-05-20 | 2026-05-20 | 2026-10-30 | *Revised Schedule Submitted with TCC 30-Oct-26, Under SEC approval *Pipe and cable routing activities are currently slow due to pending outdoor work permits: SE to expedite the issuance of all required permits for outdoor works & Allow working 24h for outdoor works * NAOH Pipeline Hold: Finalize the pending technical decision to release the activity.
156 | PE-352 | Main Construction Work for Al Ahsa Entertainment Complex | Fahed Al Malki | 2025-05-01 | 11.44% | 11.89% | 0.45% | SEVEN | Eastern | Alahsa | N/A | 2027-10-28 | 2027-10-28 | 2027-10-28 | -
MEP UNIT (MAZEN MOSTAFA)
157 | EL-059 | Rehab & Development of Ohud Hospital | Ghaleb | 2021-10-19 | 100% | 97.44% | -2.56% | MOH | Western | Madinah | N/A | 2024-04-18 | 2025-10-18 | 2026-08-31 | -
158 | EL-060 | CONST OF COLLEGE -Faculty of Science – Univ of Tabuk. | AbdelHafez Mousa | 2022-07-18 | 100% | 94.09% | -5.91% | University of Tabuk | Western | Tabuk - KSA. | Under Approval | 2024-01-09 | 2026-05-26 | 2026-08-15 | -
159 | EL-062 | Four Season Resort, Triple Bay, Amaala | Raja Naveed | 2023-08-31 | 100% | 98.71% | -1.29% | AMAALA | Western | Al Wajh | Approved | 2024-12-17 | 2025-08-30 | 2026-08-30 | -
160 | EL-063 | NEOM MEP ¦ NRC-11 | Hashem Mohamed | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
161 | EL-064 | NEOM MEP ¦ NRC-13 | Hashem Mohamed | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
162 | EL-065 | NEOM MEP ¦ NRC-17 | Hashem Mohamed | 2022-10-06 | 100% | 99.99% | -0.01% | Alfanar EC | Western | NEOM | N/A | 2024-06-06 | 2024-06-06 | 2025-12-31 | -
163 | EL-066 | NEOM MEP ¦ NRC-19 | Hashem Mohamed | 2022-11-20 | 100% | 99.99% | -0.01% | Alfanar EC | Western | NEOM | N/A | 2024-07-21 | 2024-07-21 | 2025-12-31 | -
164 | EL-067 | NEOM MEP ¦ NRC-26 | Hashem Mohamed | 2022-11-20 | 100% | 99.99% | -0.01% | Alfanar EC | Western | NEOM | N/A | 2024-09-04 | 2024-09-04 | 2025-12-31 | -
165 | EL-068 | MEP Works for AMAALA YACHT CLUB | Hashem Mohamed | 2024-09-14 | 100% | 99.9% | -0.1% | AMAALA | Western | Al Wajh | N/A | 2025-02-27 | 2025-10-30 | 2026-07-31 | -
166 | EL-069 | NEOM - BMS FOR 5 VILLAGES | Hashem Mohamed | 2024-12-15 | 100% | 100% | 0% | ALFANAR - AGD | Western | NEOM | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
167 | EL-070 | ALFANAR HEALTH CARE - BIM SERVICE | Hashem Mohamed | 2024-12-05 | 100% | 100% | 0% | Alfanar Health Care | Western | Amaala | N/A | 2025-05-01 | 2025-05-01 | 2025-12-31 | -
168 | EL-071 | NEOM Expansion - (PE-269 Project) | Hashem Mohamed | 2025-04-14 | 100% | 100% | 0% | Alfanar EC | Western | NEOM | N/A | 2025-05-31 | 2025-05-31 | 2025-05-31 | -
169 | EL-072 | HVDC-1 ¦ COA-WOA ¦ RUH-9022 - MEP WORKS | Hashem Mohamed | 2025-05-15 | 96.02% | 74.75% | -21.27% | Alfanar EC | Central | Dhurma | N/A | 2026-04-23 | 2026-04-23 | 2026-09-14 | -
170 | EL-073 | HVDC-2 ¦ COA-SOA ¦ RUH-9041 - MEP WORKS | Hashem Mohamed | 2025-05-15 | 95.29% | 67.57% | -27.72% | Alfanar EC | Central | Kharj | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
171 | EL-074 | HVDC-3 ¦ COA-SOA ¦ KUDMI - MEP WORKS | Hashem Mohamed | 2025-05-15 | 100% | 73.83% | -26.17% | Alfanar EC | Southern | Kudmi | N/A | 2026-10-29 | 2026-10-29 | 2026-11-22 | -
172 | EL-075 | HVDC-4 ¦ COA-WOA ¦ JED-HHR1 - MEP WORKS | Hashem Mohamed | 2025-05-15 | 100% | 76.64% | -23.36% | Alfanar EC | Western | Jeddah | N/A | 2026-10-29 | 2026-10-29 | 2026-10-29 | -
173 | EL-076 | MEP WORKS FOR SEVEN - AL AHSA (Same as PE-352) | Hashem Mohamed | 2025-05-01 | 32.8% | 28.7% | -4.1% | SEVEN | Eastern | Alahsa | N/A | 2027-10-28 | 2027-10-28 | 2028-04-04 | -
174 | EL-077 | MEP WORKS Amaala Wellness | Hashem Mohamed | 2025-08-06 | 94% | 92% | -2% | AMAALA | Western | Al Wajh | N/A | 2025-12-31 | 2026-02-11 | 2026-08-31 | -
Formulas:
TCC = VLOOKUP([Project Code],'Detailed Update'!B:T,11,FALSE)
Revised Date = VLOOKUP([Project Code],'Detailed Update'!B:T,12,FALSE)
Forecast Date = VLOOKUP([Project Code],'Detailed Update'!B:T,13,FALSE)
Start Date = VLOOKUP([Project Code],'Detailed Update'!B:D,3,FALSE)

## Completed Milestones
ALFANAR COMPLETED MILESTONES - MAY-26 UPDATE
Year | S.N | 2024 |  |  | 2025 |  |  | 2026
Region |  | TCC | PAC | FAC | TCC | PAC | FAC | TCC | PAC | FAC | TOTAL PER YEAR | NUMBER OF PROJECTS UPTO APRIL26
Center | 1 | PE-212 | PE-212 | PE-231 | PE-228 |  | PE-212 | PE-273 | PE-235 | PE-232 |  | TCC | PAC | FAC
| 2 | PE-215 | PE-215 |  |  |  | PE-215 | PE-274 |  |  | 2024 | 15 | 7 | 3
| 3 | PE-216 | PE-216 |  |  |  | PE-216 |  |  |  | 2025 | 17 | 5 | 16
| 4 | PE-231 | PE-232 |  |  |  | PE-211 |  |  |  | 2026 | 9 | 7 | 4
| 5 | PE-232 | [8 empty] | TOTAL | 41 | 12 | 19
| 6 | PE-233
| 7 | PE-235
| 8 | PE-226
9
10
11
12
13
14
15
East | 1 | PE-214 | PE-214 | PE-224 | PE-213 | PE-213 | PE-181
| 2 |  |  | PE-225 |  |  | PE-199
| 3 | [5 empty] | PE-213
| 4 | [5 empty] | PE-214
| 5 | [5 empty] | PE-229
| 6 | [5 empty] | PE-238
| 7 | [5 empty] | PE-239”Jubai”
| 8 | [5 empty] | PE-240
9
10
11
12
13
14
15
South | 1 | PE-222 | PE-222 |  |  |  | PE-222
| 2 | PE-230 | PE-230 |  |  |  | PE-230
| 3 | PE-236 |  |  |  | PE-236 | PE-236
| 4 | PE-297
| 5 |  |  |  | PE-237
| 6 |  |  |  | PE-234
| 7 | [6 empty] | PE-282
8
9
10
11
12
13
14
15
West | 1 | PE-242 |  |  | PE-221 | PE-221 | PE-221 | PE-295 | PE-315 | PE-254
| 2 | PE-241 |  |  | PE-257 | PE-270 |  | PE-267 | PE-280 | PE-280
| 3 |  |  |  | PE-270 | PE-290 |  | PE-338 | PE-281 | PE-257
| 4 |  |  |  | PE-290 |  |  | PE-263 | PE-254
| 5 |  |  |  | PE-254 |  |  | PE-291 | PE-257
| 6 |  |  |  | PE-260 |  |  | PE-312 | PE-241
| 7 |  |  |  | PE-262
| 8 |  |  |  | PE-296
| 9 |  |  |  | PE-281
| 10 |  |  |  | PE-280
| 11 |  |  |  | PE-315
| 12 |  |  |  | PE-243
| 13 |  |  |  | PE-261
14
15
|  | 15 | 7 | 3 | 17 | 5 | 16 | 9 | 7 | 4